## Worksheet
admin.Charmaine F. Layawon Delayed Request
Reference # | Process | Requestor | Date Request | Date Needed | Date Done | Site | Category | Details | Status | Assigned to
CSR-1420-19 | CSR | Charmaine F. Layawon | 2019-10-30 14:15:00 | 2019-12-11 21:00:00 | 0000-00-00 00:00:00 | HO | Software Purchase | Acquire Software development related training courses from online training sites (BIT Team) Use HO training budget for month of Oct 2019 | Assigned | admin.Charmaine F. Layawon
CSR-1549-19 | CSR | Stiffany Grace B. Jorge | 2019-11-29 16:33:00 | 2019-12-02 21:00:00 | 0000-00-00 00:00:00 | BO | Transfer PC location | 1. Change Of Computer & Telephone Layout 2. Additional Of Light Up For 10.49.130.85 3. Transfer Of CADRA & RRJ093 To 10.49.130.84 Need to deploy tonight after work. Please See Attached. | Assigned | admin.Charmaine F. Layawon
CSR-1545-19 | CSR | Cecil T. Morales | 2019-12-05 09:42:00 | 2019-12-06 09:42:00 | 0000-00-00 00:00:00 | HO | Transfer Software location | Please transfer KD VIEWER SOFTWARE FROM IP 10.49.7.100 TO IP 10.49.5.241 | Work in Progress | admin.Charmaine F. Layawon
CSR-1536-19 | CSR | Michelle Anne A. Celoso | 2019-12-10 08:16:00 | 2019-12-12 21:00:00 | 0000-00-00 00:00:00 | BO | PC Configuration | Install ASL-Thin Client, SAP Configure ODBC connection, Seine2 drawing view Install shared Extes | Work in Progress | admin.Charmaine F. Layawon
CPR-0181-19 | CPR | Charmaine F. Layawon | 2019-12-10 13:24:00 | 2019-12-09 09:30:00 | 0000-00-00 00:00:00 | BO | WS Power Supply | cannot boot workstation with power but no display, no peripherals, no network | Work in Progress | admin.Charmaine F. Layawon
CSR-1547-19 | CSR | Jesrel F. Casabuena | 2019-12-11 12:51:00 | 2019-12-16 21:00:00 | 0000-00-00 00:00:00 | BO | Add Internet Connection | Add Internet Connection on PC(10.49.130.128) For Reasearch Purpose Only (c/o Sir Ruzzel) | Work in Progress | admin.Charmaine F. Layawon
CPR-0183-19 | CPR | Kerby Joy S. Yu | 2019-12-12 13:52:00 | 2019-12-12 13:52:00 | 0000-00-00 00:00:00 | BO | MS Office | kerbyjoy.yu@ph.yazaki.com IP Address 10.49.130.42 Retrieval of Password outlook account | Work in Progress | admin.Charmaine F. Layawon