## Worksheet
BO November 2019
New Request | Assigned | Work in Progress | Done | Closed | Total
0 | 3 | 3 | 30 | 59 | 95
| Completed Request | On-going Request | Delay Request | Total Request | Completion % | On Time %
CSR | 31 | 3 | 13 | 37 | 83.78 | 58.06
CPR | 2 | 0 | 0 | 2 | N/A | N/A
DRR | 3 | 0 | 0 | 3 | N/A | N/A
Member | Assigned | Work in Progress | Done | Closed
admin.Abel D. Chaves | 0 | 0 | 13 | 0
admin.Charmaine F. Layawon | 0 | 0 | 2 | 27
admin.Corazon A. Coronel | 0 | 0 | 1 | 1
admin.Donald Kerby L. Manejero | 0 | 0 | 0 | 23
admin.Joe Nico T. Geronimo | 2 | 3 | 1 | 0
admin.Joel Jr. M. Chavez | 0 | 0 | 11 | 8
admin.Kiel Antaran | 0 | 0 | 1 | 0
admin.Patrick Robin Vinas | 1 | 0 | 0 | 0
admin.Reymark B. Evangelista | 0 | 0 | 1 | 0
Reference # | Process | Requestor | Date Request | Date Needed | Date Done | Site | Category | Details | Status | Assigned to
QA-1791-19 | QA | Joycee Marie G. Bautista | 2019-10-16 08:15:00 | 2019-10-16 08:15:00 | 2019-10-16 08:20:00 | BO | CAE-Extes | set default config for extes | Closed | admin.Charmaine F. Layawon
CSR-1313-19 | CSR | Rudy S. Obina | 2019-10-16 15:56:00 | 2019-10-17 21:00:00 | 2019-11-11 08:43:00 | BO | Backup CAE file/s | 10.49.128.11,CAE folder creation and files back-up export/home/eucoodb/model/work/HONDA/ TDK | Assigned | admin.Patrick Robin Vinas
CSR-1302-19 | CSR | Jesrel F. Casabuena | 2019-10-17 06:52:00 | 2019-10-18 21:00:00 | 2019-10-24 07:40:00 | BO | Access Request | Extraction of access list records of 2 SCD staff that can access CON Folders. 1. Ma. Filipina del Rosario (HO) 2. Rhea Joy Alminaza (BO) Need for ISMS CPAR of CON BO (ISMS-CPAR-CON-BO-20190905-01) access list will be reflected on 201 file of 2 SCD staff. Attach excel file are the list of location to be extracted. Thank you. | Done | admin.Abel D. Chaves
QA-1792-19 | QA | Elrick Van C. Estrera | 2019-10-17 12:46:00 | 2019-10-17 12:46:00 | 2019-10-17 12:48:00 | BO |  | Transfer of Pictures from Camera to EI common folder. | Closed | admin.Donald Kerby L. Manejero
CPR-0151-19 | CPR | Nikko Matthew L. Eulatic | 2019-10-17 14:10:00 | 2019-10-24 17:06:00 | 2019-10-24 07:40:00 | BO | Mouse | Mouse do not click well. | Done | admin.Abel D. Chaves
CSR-1288-19 | CSR | Jona Christine N. Hugo | 2019-10-17 14:40:00 | 2019-11-28 21:00:00 | 2019-10-29 07:27:00 | BO | Install Software | video recording for Training Purposes. (Showing how to execute the program/application) | Done | admin.Joel Jr. M. Chavez
CSR-1287-19 | CSR | Ian Gabriel P. Tranco | 2019-10-18 13:57:00 | 2019-10-25 21:30:00 | 2019-10-25 12:51:00 | BO | Install Software | Installation of Solidworks Simulation Professional(Linear) | Done | admin.Joel Jr. M. Chavez
CSR-1286-19 | CSR | Ian Gabriel P. Tranco | 2019-10-18 16:03:00 | 2019-10-25 21:30:00 | 2019-10-25 12:50:00 | BO | Install Software | Installation of Solidworks Simulation Premium(Non-Linear) | Done | admin.Joel Jr. M. Chavez
QA-1793-19 | QA | Ma. Noela F. Escote | 2019-10-21 09:45:00 | 2019-10-21 09:45:00 | 2019-10-21 10:00:00 | BO |  | change system locale to japanese for macro tool | Closed | admin.Charmaine F. Layawon
CPR-0156-19 | CPR | Donald Kerby L. Manejero | 2019-10-21 12:17:00 | 2019-10-21 10:00:00 | 2019-11-14 18:32:00 | BO | Printer/Plotter | Fuji-Xerox Docuwide 6055 with Serial Number 400925 cause Dirty Print output. | Done | admin.Abel D. Chaves
CSR-1314-19 | CSR | Marilou P. De Luna | 2019-10-21 17:17:00 | 2019-10-30 21:00:00 | 2019-10-25 08:05:00 | BO | Account Request | Email address for the checker in branch for job coordination. Refer to the attachment. | Done | admin.Abel D. Chaves
QA-1794-19 | QA | Desiree Joy B. Gomito | 2019-10-21 12:30:00 | 2019-10-21 12:30:00 | 2019-10-21 12:45:00 | BO |  | Downloaded Japanese Manual for Renesas | Closed | admin.Joel Jr. M. Chavez
QA-1795-19 | QA | Daryll M. Alorro | 2019-10-21 12:45:00 | 2019-10-21 12:45:00 | 2019-10-21 12:50:00 | BO |  | Input Admin account for environment variables | Closed | admin.Joel Jr. M. Chavez
QA-1796-19 | QA | Jona Christine N. Hugo | 2019-10-21 15:30:00 | 2019-10-21 15:30:00 | 2019-10-21 15:45:00 | BO |  | Check CCTV for Time in | Closed | admin.Joel Jr. M. Chavez
QA-1797-19 | QA | Michelle C. Dela Cruz | 2019-10-21 19:15:00 | 2019-10-21 19:15:00 | 2019-10-21 19:25:00 | BO |  | Assist on File too long error on file server | Closed | admin.Joel Jr. M. Chavez
QA-1798-19 | QA | Mae B. Domines | 2019-10-22 13:25:00 | 2019-10-22 13:25:00 | 2019-10-22 13:28:00 | BO |  | RRJ Reset. request YC for restart. | Closed | admin.Donald Kerby L. Manejero
QA-1799-19 | QA | Jayson P. Gabilo | 2019-10-22 13:35:00 | 2019-10-22 13:35:00 | 2019-10-22 13:38:00 | BO |  | Transfer of Pictures from Digital Camera. | Closed | admin.Donald Kerby L. Manejero
QA-1800-19 | QA | Jayson P. Gabilo | 2019-10-22 13:35:00 | 2019-10-22 13:35:00 | 2019-10-22 13:38:00 | BO |  | Transfer of Pictures from Digital Camera. | Closed | admin.Donald Kerby L. Manejero
QA-1801-19 | QA | Jayson P. Gabilo | 2019-10-22 13:35:00 | 2019-10-22 13:35:00 | 2019-10-22 13:38:00 | BO |  | Transfer of Pictures from Digital Camera. | Closed | admin.Donald Kerby L. Manejero
QA-1802-19 | QA | Christianne Anne J. Pimentel | 2019-10-22 10:00:00 | 2019-10-22 10:00:00 | 2019-10-22 13:40:00 | BO |  | transfer finance apps (ebir,etc) from 10.49.130.56 to file server | Closed | admin.Charmaine F. Layawon
QA-1803-19 | QA | Christian Dell S. Tablac | 2019-10-22 17:10:00 | 2019-10-22 17:10:00 | 2019-10-22 17:15:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
DRR-0146-19 | DRR | Shiela T. Baytic | 2019-10-23 06:25:00 | 2019-10-23 06:25:00 | 2019-11-12 12:37:00 | BO | Cae | X41985-MN01R#00#.SLDDRW;\\10.49.128.7\ev_(branch)\â‘¢ JOB_ORDERS\EV_CON\â‘ªNOVEMBER 2019\PZ1A\EVA1-1910005_12A_AOSHIMA_R-DWG\5 WORKING DATA\X41985-MN01R#00#;Original Directory;Yes;Corrupted file, please recover last saved data. | Done | admin.Abel D. Chaves
CSR-1331-19 | CSR | Ian Gabriel P. Tranco | 2019-10-23 07:54:00 | 2019-10-31 21:00:00 | 2019-10-24 11:47:00 | BO | Printer Configuration | Request for redirecting of scanned files to Common/Personal E-mails. shiela.baytic@ph.yazaki.com - 1188 smb_evcon01-ev.peti@ph.yazaki.com - 1437, 1439, 6019, 6054, 6055, 6056, 6057 smb_evbox01-ev.peti@ph.yazaki.com - 6020, 6021, 6042, 6115, 6116, 6117, 6169, 6170, 6171 | Done | admin.Abel D. Chaves
QA-1805-19 | QA | Robel P. Ganzon | 2019-10-22 17:30:00 | 2019-10-22 17:30:00 | 2019-10-22 17:40:00 | BO |  | register tap card on wh_dcvi5571 | Closed | admin.Charmaine F. Layawon
QA-1806-19 | QA | Albert L Tallafer | 2019-10-23 10:45:00 | 2019-10-23 10:45:00 | 2019-10-23 10:48:00 | BO |  | transfer pics to server | Closed | admin.Charmaine F. Layawon
QA-1807-19 | QA | Princess Mae F. Punsalan | 2019-10-23 11:20:00 | 2019-10-23 11:20:00 | 2019-10-23 11:28:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
QA-1808-19 | QA | Catherine U. Bulalacao | 2019-10-23 10:20:00 | 2019-10-23 10:20:00 | 2019-10-23 10:26:00 | BO |  | reserve video con system for 10/29 meeting | Closed | admin.Charmaine F. Layawon
QA-1809-19 | QA | Adrian N. Quiambao | 2019-10-23 11:00:00 | 2019-10-23 11:00:00 | 2019-10-23 11:15:00 | BO |  | assist scanning on oce plotter | Closed | admin.Charmaine F. Layawon
CSR-1358-19 | CSR | Charibelle L. Ferrer | 2019-10-23 16:52:00 | 2019-10-31 21:00:00 | 2019-11-04 15:49:00 | BO | Backup to CD/DVD | REQUEST FOR BACK UP FOR MODULAR \\Petifssvr\wh_(branch)\TOYOTA\â˜…FROM MANILA DOCUMENTS\DONE\DONE\2019\JULY 2019 FOR CONVENTIONAL \\Petifssvr\wh_(branch)\TOYOTA\â˜…FROM MANILA DOCUMENTS\DONE\DONE (CONVENTIONAL)\JULY 2019 FOR MOCHIKIN \\Petifssvr\wh_(branch)\TOYOTA\â˜…FROM MANILA DOCUMENTS\DONE\DONE(MOCHIKIN)\2019\JULY | Done | admin.Abel D. Chaves
QA-1810-19 | QA | Albert L Tallafer | 2019-10-23 16:55:00 | 2019-10-23 16:55:00 | 2019-10-23 16:58:00 | BO |  | Transfer of Pictures from Cellphone to Admin folder. | Closed | admin.Donald Kerby L. Manejero
QA-1811-19 | QA | Darlene G. Bicodo | 2019-10-23 16:55:00 | 2019-10-23 16:55:00 | 2019-10-23 17:05:00 | BO |  | Installation of Printers and Coloured printer access. | Closed | admin.Donald Kerby L. Manejero
CSR-1347-19 | CSR | Shenie Lou G Besa | 2019-10-24 08:08:00 | 2019-11-21 18:00:00 | 2019-11-12 09:16:00 | BO | Access Request | Request for folder access rights of the following members, 1. pet0954 2. pet1450 3. pet1539 4. pet1712 5. pet1718 6. pet1895 7. pet1899 8. pet1969 | Closed | admin.Joel Jr. M. Chavez
QA-1812-19 | QA | Mae B. Domines | 2019-10-24 08:30:00 | 2019-10-24 08:30:00 | 2019-10-24 08:45:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
QA-1813-19 | QA | Rechielyn B. Trabado | 2019-10-24 10:00:00 | 2019-10-24 10:00:00 | 2019-10-24 10:15:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
CSR-1346-19 | CSR | Shenie Lou G Besa | 2019-10-24 13:47:00 | 2019-11-04 21:00:00 | 2019-10-28 15:33:00 | BO | Account Request | Request for deletion of windows log in and folder access rights of resigned employee. 1. pet6195 | Done | admin.Abel D. Chaves
CSR-1345-19 | CSR | Mark John A. Tiongson | 2019-10-24 14:03:00 | 2019-11-21 17:00:00 | 2019-11-07 15:31:00 | BO | Install Software | Install LT Spice Software on the following EI-Hardware Group PCs. 10.49.130.186 10.49.130.169 10.49.130.185 10.49.131.97 10.49.130.184 10.49.131.107 Laptops on Evaluation Room 10.49.131.94 10.49.130.182 10.49.131.92 Please install per user. | Closed | admin.Joel Jr. M. Chavez
CSR-1341-19 | CSR | Troy C. Gatchalian | 2019-10-24 17:31:00 | 2019-10-25 21:00:00 | 2019-10-28 15:39:00 | BO | Borrow | Laptop to be used in meeting with ISAT University | Done | admin.Charmaine F. Layawon
CSR-1344-19 | CSR | Johansson L. Binalla | 2019-10-25 09:33:00 | 2019-12-06 21:00:00 | 2019-11-05 19:24:00 | BO | Install Software | I would like to request for the installation of XAMPP software version 7.3.10(please see attached file) at Ip Address 10.49.130.126, in preparation for developing a new web browser based application for CON department for the improvement of Job Operations. | Closed | admin.Joel Jr. M. Chavez
CSR-1343-19 | CSR | Ronalyn G. Imana | 2019-10-25 10:58:00 | 2019-11-07 07:19:00 | 2019-11-08 07:43:00 | BO | Access Request | Request of folder access for Hardware BO in details below EMPLOYEE ID NAME 1442 Tiongson, Mark John 6063 Rodas, Rutchard Jhon 6065 Tejada, Jenielyn 6174 Colago, Adrian Cris 6176 Lima, Lenard O. 6177 Ta-asan, Roylin L. 6191 Daryll M. Alorro -Access in folder \\10.49.1.97\ei\31 ECIâ†’PET\ECIâ†’PET(BMS) -Access in folder \\10.49.1.97\ei\32 PETâ†’ECI\PETâ†’ECI(BMS) -Access in folder \\10.49.1.97\EI Archive\Hardware -Restriction in folder \\10.49.1.97\ei\12 HomePage | Done | admin.Reymark B. Evangelista
CSR-1451-19 | CSR | Charibelle L. Ferrer | 2019-10-25 11:38:00 | 2019-10-28 21:00:00 | 2019-11-20 21:28:00 | BO | Backup to CD/DVD | REQUEST FOR BACK UP FOR MODULAR \\Petifssvr\wh_(branch)\TOYOTA\â˜…FROM MANILA DOCUMENTS\DONE\DONE\2019\JUNE 2019 FOR CONVENTIONAL \\Petifssvr\wh_(branch)\TOYOTA\â˜…FROM MANILA DOCUMENTS\DONE\DONE (CONVENTIONAL)\JUNE 2019 | Done | admin.Abel D. Chaves
CSR-1361-19 | CSR | Nhey Mar G. Mazo | 2019-10-25 14:58:00 | 2019-11-05 21:00:00 | 2019-10-30 18:23:00 | BO | Access Request | I need to request the persons to Access all folder at location \\10.49.1.97\cdd\Common\â‘£ORDER SHEET, Purpose of access to delegate the duties and responsibilities to this persons(CON Orderload fill-in and save, Part-B fill-in and save) | Done | admin.Abel D. Chaves
CSR-1352-19 | CSR | Mary Kathleen D. Brotonel | 2019-10-28 11:16:00 | 2019-11-04 21:00:00 | 2019-11-11 14:43:00 | BO | Install Software | Additional 1 VNC server for Toyota-Niimi group to be use during harness checking. IP address - 10.49.131.73 | Closed | admin.Corazon A. Coronel
QA-1814-19 | QA | Princess Mae F. Punsalan | 2019-10-28 09:30:00 | 2019-10-28 09:30:00 | 2019-10-28 10:00:00 | BO |  | reset windows account password | Closed | admin.Charmaine F. Layawon
QA-1815-19 | QA | Princess Mae F. Punsalan | 2019-10-28 09:15:00 | 2019-10-28 09:15:00 | 2019-10-28 09:30:00 | BO |  | configure printer settings, set default apps | Closed | admin.Charmaine F. Layawon
QA-1816-19 | QA | Princess Mae F. Punsalan | 2019-10-28 09:30:00 | 2019-10-28 09:30:00 | 2019-10-28 09:45:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
QA-1817-19 | QA | Ma. Victoria Fleur B. B. Flores | 2019-10-28 10:45:00 | 2019-10-28 10:45:00 | 2019-10-28 11:00:00 | BO |  | reset windows account passsword | Closed | admin.Charmaine F. Layawon
QA-1818-19 | QA | Ma. Victoria Fleur B. B. Flores | 2019-10-28 13:05:00 | 2019-10-28 13:05:00 | 2019-10-28 13:15:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
CSR-1348-19 | CSR | Ronalyn G. Imana | 2019-10-28 13:13:00 | 2019-11-06 21:00:00 | 0000-00-00 00:00:00 | BO | Access Request | Request of access in the ff. folder of Mechanical group, details below 0779 Facundo, Mark Julius 1176 Avena, Francis 1193 Dayapan, April 1443 Azucena , Joseph 1588 Velasquez, Gilbert 1659 Salcedo, Ivy 6005 Duro, Winston 6051 Estorque, Glenn 6059 Carag, Phincy Roy 6064 Siva, Rommer 6069 Diaz, Renea Marie 6070 Juridico, Aileen 6092 Sumagaysay, Benny 1963 Santiago, Neil Joshua C. Access in folder \\10.49.1.97\EI Archive\Mechanical Access in folder \\10.49.1.97\ei\31 ECIâ†’PET\ECIâ†’PET(GSD) Access in folder \\10.49.1.97\ei\32 PETâ†’ECI\ECIâ†’PET(GSD) Restriction in folder \\10.49.1.97\EI Archive\Hardware Restriction in folder \\10.49.1.97\EI Archive\Software Restriction in folder \\10.49.1.97\ei\12 HomePage | Work in Progress | admin.Joe Nico T. Geronimo
QA-1819-19 | QA | John Anthony G. Presas | 2019-10-28 16:40:00 | 2019-10-28 16:40:00 | 2019-10-28 16:47:00 | BO | CAE-Others | refresh tab sym M75 | Closed | admin.Charmaine F. Layawon
QA-1820-19 | QA | Krystine Mae B. Gale | 2019-10-28 16:45:00 | 2019-10-28 16:45:00 | 2019-10-28 16:48:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
QA-1821-19 | QA | Ma. Victoria Fleur B. B. Flores | 2019-10-28 17:25:00 | 2019-10-28 17:25:00 | 2019-10-28 17:33:00 | BO |  | assist printing custom size on ricoh | Closed | admin.Charmaine F. Layawon
QA-1824-19 | QA | Shenie Lou G Besa | 2019-10-28 16:30:00 | 2019-10-28 16:30:00 | 2019-10-28 17:00:00 | BO |  | generate wh_dw6055 plotter logs aug to oct2019 | Closed | admin.Charmaine F. Layawon
QA-1825-19 | QA | Shenie Lou G Besa | 2019-10-29 08:30:00 | 2019-10-29 08:30:00 | 2019-10-29 08:50:00 | BO |  | Inquiry about media roll length | Closed | admin.Charmaine F. Layawon
CSR-1356-19 | CSR | Melissa R. Talabong | 2019-10-29 11:13:00 | 2019-11-11 21:00:00 | 2019-11-11 07:29:00 | BO | Borrow | Borrow computer from Nov 11-15 to be used by Finance Staff. Please set up in Finance table. | Done | admin.Joel Jr. M. Chavez
CSR-1367-19 | CSR | Jake Anthony A. Belano | 2019-10-29 12:29:00 | 2019-10-30 21:00:00 | 2019-11-05 19:23:00 | BO | Install Software | YSCP crimp simulation (LS-PrePost installation) | Done | admin.Joel Jr. M. Chavez
QA-1826-19 | QA | Ma. Victoria Fleur B. B. Flores | 2019-10-29 12:48:00 | 2019-10-29 12:48:00 | 2019-10-29 12:53:00 | BO | CAE-CAE | refresh tab sym M36 | Closed | admin.Charmaine F. Layawon
CSR-1360-19 | CSR | Edvin B. Pantoni | 2019-10-30 10:36:00 | 2019-11-08 21:00:00 | 2019-10-30 18:29:00 | BO | Access Request | Need connection for this directory (\\10.49.1.97\common\â˜…â˜…YC EVP Mr. Watanabe Projectâ˜…â˜… ) To get the efficiency of EV department based on Vehicle Event. | Done | admin.Abel D. Chaves
CSR-1359-19 | CSR | Abel D. Chaves | 2019-10-30 12:48:00 | 2019-10-31 21:00:00 | 0000-00-00 00:00:00 | BO | Hardware Purchase | Purchase x1 48Port PoE Cisco Switch for BO. Investment no 2020/1-6#5 | Work in Progress | admin.Joe Nico T. Geronimo
QA-1827-19 | QA | Mae B. Domines | 2019-10-31 09:15:00 | 2019-10-31 09:15:00 | 2019-10-31 09:25:00 | BO |  | show extes app shortcut on desktop | Closed | admin.Charmaine F. Layawon
QA-1828-19 | QA | Albert L Tallafer | 2019-10-31 09:30:00 | 2019-10-31 09:30:00 | 2019-10-31 09:45:00 | BO |  | transfer pics to server | Closed | admin.Charmaine F. Layawon
QA-1829-19 | QA | Jane D. Amboy | 2019-10-31 10:55:00 | 2019-10-31 10:55:00 | 2019-10-31 11:10:00 | BO |  | update excel for macro | Closed | admin.Charmaine F. Layawon
QA-1830-19 | QA | Jane D. Amboy | 2019-10-31 10:55:00 | 2019-10-31 10:55:00 | 2019-10-31 11:10:00 | BO |  | update excel for macro | Closed | admin.Charmaine F. Layawon
QA-1831-19 | QA | Hazel S. Poblacion | 2019-10-31 13:20:00 | 2019-10-31 13:20:00 | 2019-10-31 13:23:00 | BO |  | access door access system | Closed | admin.Charmaine F. Layawon
CSR-1442-19 | CSR | Annie C. Palo | 2019-11-05 12:35:00 | 2019-11-06 21:00:00 | 2019-11-15 10:43:00 | BO | Backup CAE file/s | Please create folder in the below directory /export/home/eucoodb/model/work/HONDA Folder Name - 3M1A | Done | admin.Corazon A. Coronel
CSR-1394-19 | CSR | Francis Razel R. YbaÃ±ez | 2019-11-05 12:39:00 | 2019-12-06 18:50:00 | 2019-12-05 21:33:00 | BO | Install Software | Transfer the CANalyzer Version 8.5 from 10.49.130.178 to 10.49.131.93. Install CANalyzer version 8.2 in 10.49.130.178. Installer are in EI area | Done | admin.Joel Jr. M. Chavez
CSR-1393-19 | CSR | Mark John A. Tiongson | 2019-11-06 08:13:00 | 2019-11-08 21:00:00 | 2019-11-11 19:02:00 | BO | Install Software | Install the following Softwares on 10.49.131.109. 1. Mentor Graphics Expedition 2. LT Spice 3. DocuWorks Viewer Light 4. LP Wizard | Done | admin.Abel D. Chaves
CSR-1396-19 | CSR | Francis Razel R. YbaÃ±ez | 2019-11-06 11:15:00 | 2019-12-18 21:00:00 | 0000-00-00 00:00:00 | BO | Software Purchase | Purchase 2 Microsoft office 2010 for the 2 unit Z240 workstation for Kakotora Equipment. | Work in Progress | admin.Joe Nico T. Geronimo
CSR-1395-19 | CSR | Jenielyn B. Tejada | 2019-11-06 12:29:00 | 2019-11-21 18:00:00 | 2019-11-12 08:43:00 | BO | Install Software | Install VisECAD in 10.49.130.169 at EI Hardware area. https://www.mentorg.co.jp/pcb/downloads/visecad-viewer/ | Closed | admin.Joel Jr. M. Chavez
CSR-1447-19 | CSR | Grace A. Rivera | 2019-11-08 16:37:00 | 2019-11-19 21:00:00 | 2019-11-25 12:35:00 | BO | Access Request | - Restriction of â‘¢ JOB_ORDERS folders in EV Folder (BO) for Ms. Grace Rivera Ms. Rhea Joy Alminaza Ms. Kristel Ann Villanueva Ms. Wennie Rose Camus | Done | admin.Abel D. Chaves
QA-1832-19 | QA | Winston S. Duro | 2019-11-11 08:20:00 | 2019-11-11 08:20:00 | 2019-11-11 08:22:00 | BO |  | Black Screen on Windows 10 background. | Closed | admin.Donald Kerby L. Manejero
QA-1834-19 | QA | Shenie Lou G Besa | 2019-11-11 08:25:00 | 2019-11-11 08:25:00 | 2019-11-11 08:26:00 | BO |  | Black Screen at Windows 10. | Closed | admin.Donald Kerby L. Manejero
QA-1835-19 | QA | Lawrence Nico L. Alejano | 2019-11-11 09:45:00 | 2019-11-11 09:45:00 | 2019-11-11 09:52:00 | BO |  | Reset PET Login Password. | Closed | admin.Donald Kerby L. Manejero
QA-1836-19 | QA | Jeremias F. Gante | 2019-11-11 10:01:00 | 2019-11-11 10:01:00 | 2019-11-11 10:10:00 | BO |  | Dual Monitor Problem. No Driver installed. | Closed | admin.Donald Kerby L. Manejero
QA-1837-19 | QA | Albert L Tallafer | 2019-11-11 10:25:00 | 2019-11-11 10:25:00 | 2019-11-11 10:30:00 | BO |  | Transfer of Pictures from Cellphone to admin folder | Closed | admin.Donald Kerby L. Manejero
QA-1838-19 | QA | Charibelle L. Ferrer | 2019-11-11 10:40:00 | 2019-11-11 10:40:00 | 2019-11-11 10:47:00 | BO |  | REset of RRJ printer. | Closed | admin.Donald Kerby L. Manejero
DRR-0155-19 | DRR | Danica Mae T. Embate | 2019-11-11 11:06:00 | 2019-11-22 12:35:00 | 2019-11-21 12:35:00 | BO | Windows | APPD_AB1626BE80_00000_n_1-1.20191106_163723;\\Petifssvr\wh_(branch)\TOYOTA\Conventional\AP CHECKING\W19-H-P-296 (702W)\AB162-6BE80-00000\1ST;Original Directory;No;This TIFF file will be used for Light-up during AP checking. | Closed | admin.Donald Kerby L. Manejero
CSR-1392-19 | CSR | Annie C. Palo | 2019-11-11 11:35:00 | 2019-11-12 21:00:00 | 2019-11-11 13:05:00 | BO | Backup CAE file/s | Please create folder in the below directory /export/home/eucoodb/model/work/HONDA Folder Name - TZXA | Done | admin.Kiel Antaran
QA-1839-19 | QA | Danica Mae T. Embate | 2019-11-11 11:10:00 | 2019-11-11 11:10:00 | 2019-11-11 11:12:00 | BO |  | restore deleted data | Closed | admin.Donald Kerby L. Manejero
CSR-1401-19 | CSR | Charmaine F. Layawon | 2019-11-11 12:06:00 | 2019-11-20 21:00:00 | 2019-11-14 06:36:00 | BO | Account Request | request to allow admin account access on petsvr1097 and petsvr1100 | Done | admin.Joe Nico T. Geronimo
CSR-1400-19 | CSR | Charmaine F. Layawon | 2019-11-11 12:13:00 | 2019-11-12 21:00:00 | 2019-12-13 13:37:00 | BO | Download | copy vm and netapp logs to phildata flash drive for diagnosis | Done | admin.Charmaine F. Layawon
QA-1840-19 | QA | Christian Dell S. Tablac | 2019-11-11 16:50:00 | 2019-11-11 16:50:00 | 2019-11-11 16:54:00 | BO |  | Reset of Symbol TAB M61. | Closed | admin.Donald Kerby L. Manejero
QA-1841-19 | QA | Mark John A. Tiongson | 2019-11-12 08:15:00 | 2019-11-12 08:15:00 | 2019-11-12 08:25:00 | BO |  | Reset frozen screen background. | Closed | admin.Donald Kerby L. Manejero
QA-1842-19 | QA | Albert L Tallafer | 2019-11-12 09:02:00 | 2019-11-12 09:02:00 | 2019-11-12 09:05:00 | BO |  | Transfer of Pictures from Cellphone to Admin folder. | Closed | admin.Donald Kerby L. Manejero
CSR-1429-19 | CSR | Roxyanne Grace R. Garcia | 2019-11-12 13:43:00 | 2019-12-24 21:00:00 | 0000-00-00 00:00:00 | BO | Renewal License | MicroCADAM License renewal for 2 PCs with IP Address 10.49.130.116 and 10.49.130.117 at Connector Branch Office. Please contact Roxy(HO) at loc 648 or Sir Bob(BO) at loc 418. | Assigned | admin.Joe Nico T. Geronimo
CSR-1554-19 | CSR | Melfred John J. Malfarta | 2019-11-13 07:43:00 | 2019-12-20 15:44:00 | 2019-12-17 09:22:00 | BO | PC Configuration | Delete JBRB Group and HONDA Folder in SCD (Branch) - \\10.49.128.7 | Done | admin.Joel Jr. M. Chavez
QA-1843-19 | QA | Racky E. Faisan | 2019-11-13 13:35:00 | 2019-11-13 13:35:00 | 2019-11-13 13:41:00 | BO |  | Reset of Parts Master @ 10.49.128.12 | Closed | admin.Donald Kerby L. Manejero
DRR-0152-19 | DRR | Glowe Dean P. Manderico | 2019-11-13 14:11:00 | 2019-11-13 14:11:00 | 2019-11-14 12:32:00 | BO | Windows | X41986-PM05E03#00#ETC;\\Petifssvr\cdd_(branch)\CDE\01CDC Start 16 June\42T\CE19-PK-0369(191031)M,Då›³â†’AJAãƒ»BOBãƒ»GELAIãƒ»T-KINGãƒ»YAN\â‘§WORKING DATA\E Drawing\X41986-PM05E#00#\X41986-PM05E#00#;Original Directory;Yes;the file was corrupted | Done | admin.Joel Jr. M. Chavez
QA-1844-19 | QA | George Vincent C. Cagape | 2019-11-13 15:45:00 | 2019-11-13 15:45:00 | 2019-11-13 15:53:00 | BO |  | Configure Printer settings. | Closed | admin.Donald Kerby L. Manejero
QA-1845-19 | QA | Mary Kathleen D. Brotonel | 2019-11-13 14:30:00 | 2019-11-13 14:30:00 | 2019-11-13 14:50:00 | BO |  | VNC problem. 10.49.132.28 | Closed | admin.Donald Kerby L. Manejero
CSR-1456-19 | CSR | Krispearl Joy E. Belano | 2019-11-13 17:55:00 | 2019-11-15 21:00:00 | 2019-12-17 15:27:00 | BO | Install Software | Auto delete of folder contents in BO common server EXCEPT EDSD folder. I attached file for details. Same file was attached in e-mail request. | Done | admin.Joel Jr. M. Chavez
CSR-1452-19 | CSR | Ian Gabriel P. Tranco | 2019-11-14 07:40:00 | 2019-11-25 21:00:00 | 2019-11-21 09:40:00 | BO | Access Request | Please remove access of everyone except for the following users on the list. Please see attached file. | Done | admin.Joel Jr. M. Chavez
QA-1846-19 | QA | Ma. Victoria Fleur B. B. Flores | 2019-11-14 08:22:00 | 2019-11-14 08:22:00 | 2019-11-14 08:26:00 | BO |  | Restart RRJ printer. | Closed | admin.Donald Kerby L. Manejero
QA-1847-19 | QA | Rosalinda P. Tayer | 2019-11-14 10:15:00 | 2019-11-14 10:15:00 | 2019-11-14 11:00:00 | BO |  | Downloading of Beams error. | Closed | admin.Donald Kerby L. Manejero
CSR-1458-19 | CSR | Donald Kerby L. Manejero | 2019-11-14 12:33:00 | 2019-12-26 21:00:00 | 0000-00-00 00:00:00 | BO | Renewal License | Annual Renewal of ESET Antivirus License at Banch Office. effective date December 30, 2019-December 30, 2020. date of license expiry is on December 29, 2019. | Assigned | admin.Joe Nico T. Geronimo
CSR-1428-19 | CSR | Shenie Lou G Besa | 2019-11-14 14:20:00 | 2019-11-25 21:00:00 | 2019-12-02 18:47:00 | BO | Access Request | Request for additional and deletion of folder access rights of pet1248. | Done | admin.Joel Jr. M. Chavez