## Worksheet
BO October 2019
New Request | Assigned | Work in Progress | Done | Closed | Total
0 | 1 | 9 | 19 | 123 | 152
| Completed Request | On-going Request | Delay Request | Total Request | Completion % | On Time %
CSR | 21 | 9 | 11 | 31 | 67.74 | 47.62
CPR | 5 | 0 | 0 | 5 | N/A | N/A
DRR | 3 | 0 | 0 | 3 | N/A | N/A
Member | Assigned | Work in Progress | Done | Closed
admin.Abel D. Chaves | 0 | 0 | 11 | 5
admin.admin.Donald Kerby L. Manejero | 0 | 0 | 0 | 7
admin.Charmaine F. Layawon | 0 | 0 | 0 | 36
admin.Donald Kerby L. Manejero | 0 | 0 | 0 | 17
admin.Greg Daniel E. Mojica | 0 | 0 | 1 | 0
admin.Jasper Labenia | 0 | 1 | 0 | 0
admin.Joe Nico T. Geronimo | 0 | 3 | 1 | 2
admin.Joel Jr. M. Chavez | 0 | 1 | 6 | 56
admin.Patrick Robin Vinas | 1 | 0 | 0 | 0
admin.Reymark B. Evangelista | 0 | 4 | 0 | 0
Reference # | Process | Requestor | Date Request | Date Needed | Date Done | Site | Category | Details | Status | Assigned to
CSR-1157-19 | CSR | Joseph B. Azucena | 2019-09-16 10:52:00 | 2019-09-17 21:00:00 | 2019-09-18 10:58:00 | BO | PC Configuration | Interchange PC Monitor(Pro Display P232) of 10.49.131.111 to PC Monitor(Pro Display P240va) of 10.49.131.170. This is to uniform the PC Monitor size of 10.49.131.111. | Done | admin.Abel D. Chaves
QA-1664-19 | QA | Christian E. Laurio | 2019-09-16 13:00:00 | 2019-09-16 13:00:00 | 2019-09-16 13:08:00 | BO |  | large desktop icons, revert to smaller icons. disable hookup video mv driver | Closed | admin.Abel D. Chaves
QA-1665-19 | QA | Michelle C. Dela Cruz | 2019-09-16 07:00:00 | 2019-09-16 07:00:00 | 2019-09-16 07:20:00 | BO |  | Register Tap Card | Closed | admin.Joel Jr. M. Chavez
QA-1666-19 | QA | Melfred John J. Malfarta | 2019-09-16 07:46:00 | 2019-09-16 07:46:00 | 2019-09-16 08:10:00 | BO |  | Troubleshoot IP Phone | Closed | admin.Joel Jr. M. Chavez
QA-1667-19 | QA | Aloysius D. Probadora | 2019-09-16 08:30:00 | 2019-09-16 08:30:00 | 2019-09-16 08:40:00 | BO |  | Email password search | Closed | admin.Joel Jr. M. Chavez
CSR-1181-19 | CSR | Grace A. Rivera | 2019-09-17 08:18:00 | 2019-10-29 21:00:00 | 0000-00-00 00:00:00 | BO | Software Purchase | Kindly purchased the following Software - Solidworks Workstations (Software) - SolidWorks Simulation Linear (Software) - SolidWorks Simulation Non-Linear (Software) | Work in Progress | admin.Reymark B. Evangelista
CSR-1200-19 | CSR | Johanna Marie C. Dandan | 2019-09-17 08:24:00 | 2019-10-29 21:00:00 | 0000-00-00 00:00:00 | BO | Software Purchase | 2019/7-12#5 CATIA MD2 License Software (1) for PRT dept. BO Please see attached file for Details. | Work in Progress | admin.Joe Nico T. Geronimo
CSR-1182-19 | CSR | Grace A. Rivera | 2019-09-17 08:27:00 | 2019-12-24 21:00:00 | 0000-00-00 00:00:00 | BO | Hardware Purchase | Kindly purchased the following Hardware - Solidworks Workstations (Hardware) | Work in Progress | admin.Reymark B. Evangelista
CSR-1199-19 | CSR | Johanna Marie C. Dandan | 2019-09-17 08:29:00 | 2019-12-24 21:00:00 | 2019-10-01 06:55:00 | BO | Hardware Purchase | 2019/7-12#6 CATIA Workstation (Hard) (1) for PRT dept. Please see attached file for Details. | Work in Progress | admin.Joe Nico T. Geronimo
QA-1668-19 | QA | Shine Hope M. Casador | 2019-09-17 08:45:00 | 2019-09-17 08:45:00 | 2019-09-17 08:55:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
QA-1669-19 | QA | Aljon A. Jiloca | 2019-09-16 10:30:00 | 2019-09-16 10:30:00 | 2019-09-17 11:00:00 | BO |  | Error when running initialize tool in VCAD. 10.49.130.79 The tasks could not be finished, for unexpected errors. It strongly recommended to finish VCAD immediately. | Closed | admin.Charmaine F. Layawon
QA-1670-19 | QA | Toni Rose T. Chua | 2019-09-17 11:20:00 | 2019-09-17 11:20:00 | 2019-09-17 11:25:00 | BO |  | setup printer properties > accounting settings for pet6023 | Closed | admin.Charmaine F. Layawon
QA-1671-19 | QA | Albert L Tallafer | 2019-09-17 10:15:00 | 2019-09-17 10:15:00 | 2019-09-17 10:30:00 | BO |  | assist nurse on photocopying long size output | Closed | admin.Charmaine F. Layawon
QA-1672-19 | QA | Ma. Victoria Fleur B. B. Flores | 2019-09-17 13:00:00 | 2019-09-17 13:00:00 | 2019-09-17 13:10:00 | BO |  | change system local to japanese for HLC tool in 10.49.130.78 | Closed | admin.Charmaine F. Layawon
QA-1673-19 | QA | Ma. Victoria Fleur B. B. Flores | 2019-09-17 13:15:00 | 2019-09-17 13:15:00 | 2019-09-17 13:20:00 | BO |  | configure trust center settings for HLC tool | Closed | admin.Charmaine F. Layawon
QA-1674-19 | QA | John Paul L. Castro | 2019-09-17 13:12:00 | 2019-09-17 13:12:00 | 2019-09-17 13:22:00 | BO | CAE-CAE | refresh parts master | Closed | admin.Charmaine F. Layawon
QA-1675-19 | QA | Ma. Victoria Fleur B. B. Flores | 2019-09-17 13:28:00 | 2019-09-17 13:28:00 | 2019-09-17 13:43:00 | BO |  | macro is not running in excel. enable macro worksheet[compatibility settings] | Closed | admin.Abel D. Chaves
QA-1677-19 | QA | Susan V. Malijoc | 2019-09-17 08:10:00 | 2019-09-17 08:10:00 | 2019-09-17 08:15:00 | BO |  | Lync not launching | Closed | admin.Joel Jr. M. Chavez
QA-1678-19 | QA | Francis Razel R. YbaÃ±ez | 2019-09-17 09:00:00 | 2019-09-17 09:00:00 | 2019-09-17 09:15:00 | BO |  | outlook and Lync error, setup printer | Closed | admin.Joel Jr. M. Chavez
QA-1679-19 | QA | Racky E. Faisan | 2019-09-17 10:00:00 | 2019-09-17 10:00:00 | 2019-09-17 10:15:00 | BO | CAE-Cadra | Cadra Drive O not connecting | Closed | admin.Joel Jr. M. Chavez
QA-1680-19 | QA | Jojiemar A. Villapando | 2019-09-17 11:00:00 | 2019-09-17 11:00:00 | 2019-09-17 11:15:00 | BO | CAE-Cadra | Cadra Drive O not connecting | Closed | admin.Joel Jr. M. Chavez
QA-1681-19 | QA | Mark John A. Tiongson | 2019-09-17 15:00:00 | 2019-09-17 15:00:00 | 2019-09-17 15:05:00 | BO |  | Book Video Conference | Closed | admin.Joel Jr. M. Chavez
CSR-1193-19 | CSR | April D. Dayapan | 2019-09-17 16:15:00 | 2019-11-22 21:00:00 | 0000-00-00 00:00:00 | BO | Renewal License | CATIA Annual License Charge- Php 155,606.51 Software Usage Others Budget (EI_MT) November 2019 Budget | Work in Progress | admin.Jasper Labenia
QA-1682-19 | QA | Rhea Joy S. Alminaza | 2019-09-17 16:50:00 | 2019-09-17 16:50:00 | 2019-09-17 16:58:00 | BO |  | Support on opening of PDF download to view Digital Stamp. | Closed | admin.Donald Kerby L. Manejero
CSR-1245-19 | CSR | RBY E. Taberna | 2019-09-17 18:07:00 | 2019-09-18 21:00:00 | 2019-10-14 07:54:00 | BO | Install Software | Install CXPI software in laptop (IP addres 10.49.130.166). CXPI is needed for test and implementation. | Done | admin.Abel D. Chaves
QA-1683-19 | QA | Delbert BJ B. Beltran | 2019-09-18 08:30:00 | 2019-09-18 08:30:00 | 2019-09-18 08:37:00 | BO |  | Re Encode New ID card to access Multi-function printers ED_DocuCentreC5576 and ED1_ApeosPort-V5070 | Closed | admin.Donald Kerby L. Manejero
QA-1684-19 | QA | Carol Ann V. Dela Cruz | 2019-09-18 09:35:00 | 2019-09-18 09:35:00 | 2019-09-18 09:41:00 | BO |  | Installation of PDF-XChange Editor to insert Digital Stamp. | Closed | admin.admin.Donald Kerby L. Manejero
QA-1686-19 | QA | Rommer S. Siva | 2019-09-18 08:20:00 | 2019-09-18 08:20:00 | 2019-09-18 08:25:00 | BO |  | unreadable Japanese characters in cadra pc | Closed | admin.Abel D. Chaves
QA-1687-19 | QA | Mila Mae L Macabante | 2019-09-18 10:00:00 | 2019-09-18 10:00:00 | 2019-09-18 10:05:00 | BO |  | register id to printer | Closed | admin.Abel D. Chaves
CSR-1189-19 | CSR | Shenie Lou G Besa | 2019-09-18 13:41:00 | 2019-10-10 17:00:00 | 2019-10-09 17:43:00 | BO | Transfer PC location | Request for updating department lay-out (transfer of PCs and telephones) | Closed | admin.Joel Jr. M. Chavez
QA-1688-19 | QA | John Vincent J. Baclagon | 2019-09-18 14:57:00 | 2019-09-18 14:57:00 | 2019-09-18 15:02:00 | BO |  | register id in dc5576 | Closed | admin.Abel D. Chaves
QA-1689-19 | QA | Catherine U. Bulalacao | 2019-09-18 15:35:00 | 2019-09-18 15:35:00 | 2019-09-18 15:39:00 | BO |  | Assist Lync call problem. | Closed | admin.Donald Kerby L. Manejero
QA-1690-19 | QA | Rechielyn B. Trabado | 2019-09-19 08:35:00 | 2019-09-19 08:35:00 | 2019-09-19 08:42:00 | BO |  | Support on RRJ program restart call to Japan. | Closed | admin.Donald Kerby L. Manejero
QA-1691-19 | QA | Danica Mae T. Embate | 2019-09-18 14:00:00 | 2019-09-18 14:00:00 | 2019-09-18 14:05:00 | BO |  | Printer Plotter support for Ricoh copying of drawings. | Closed | admin.Donald Kerby L. Manejero
QA-1692-19 | QA | Maria Jessa P. Palec | 2019-09-19 09:35:00 | 2019-09-19 09:35:00 | 2019-09-19 09:40:00 | BO |  | configure wh colored printer | Closed | admin.Charmaine F. Layawon
QA-1693-19 | QA | Francis Razel R. YbaÃ±ez | 2019-09-19 11:02:00 | 2019-09-19 11:02:00 | 2019-09-19 11:10:00 | BO |  | Reservation of BT Conference. | Closed | admin.Donald Kerby L. Manejero
QA-1694-19 | QA | Anne Francine E. Almiranes | 2019-09-19 10:52:00 | 2019-09-19 10:52:00 | 2019-09-19 10:58:00 | BO |  | Download Pictures from Digital Camera to Toyota\common folder. | Closed | admin.admin.Donald Kerby L. Manejero
CSR-1316-19 | CSR | Francis Razel R. YbaÃ±ez | 2019-09-19 14:03:00 | 2019-11-21 17:00:00 | 2019-11-08 17:05:00 | BO | Install Software | Install CS+ in 10.49.131.93 and 49.131.108 | Closed | admin.Joel Jr. M. Chavez
QA-1695-19 | QA | Kristel Anne D. Villanueva | 2019-09-19 15:10:00 | 2019-09-19 15:10:00 | 2019-09-19 15:20:00 | BO |  | assist exporting pdf to excel | Closed | admin.Charmaine F. Layawon
QA-1696-19 | QA | John Carlo E. Dangan | 2019-09-19 12:30:00 | 2019-09-19 12:30:00 | 2019-09-19 12:40:00 | BO |  | Change display language to english | Closed | admin.Joel Jr. M. Chavez
QA-1697-19 | QA | Rhendell John M. PariÃ±o | 2019-09-19 13:00:00 | 2019-09-19 13:00:00 | 2019-09-19 13:15:00 | BO | CAE-Cadra | Reconnect Drive O and test license | Closed | admin.Joel Jr. M. Chavez
QA-1698-19 | QA | Rachel G. Lasotas | 2019-09-19 14:30:00 | 2019-09-19 14:30:00 | 2019-09-19 17:00:00 | BO |  | Troubleshoot CS+ Installation problem | Closed | admin.Joel Jr. M. Chavez
CSR-1211-19 | CSR | Rafael S. Fontenuela | 2019-09-20 10:59:00 | 2019-10-01 21:00:00 | 2019-09-26 14:50:00 | BO | Access Request | ANSYS Online Training | Done | admin.Abel D. Chaves
QA-1699-19 | QA | Jo-ed C. Gulmatico | 2019-09-23 08:05:00 | 2019-09-23 08:05:00 | 2019-09-23 08:09:00 | BO |  | transfer pics to server | Closed | admin.Charmaine F. Layawon
QA-1702-19 | QA | Princess Mae F. Punsalan | 2019-09-23 09:00:00 | 2019-09-23 09:00:00 | 2019-09-23 09:04:00 | BO | CAE-Extes | restart remote printer r371 | Closed | admin.Charmaine F. Layawon
QA-1703-19 | QA | Edvin B. Pantoni | 2019-09-23 09:02:00 | 2019-09-23 09:02:00 | 2019-09-23 09:05:00 | BO |  | DeskNet's Neo Password recovery. | Closed | admin.Donald Kerby L. Manejero
QA-1704-19 | QA | Christianne Anne J. Pimentel | 2019-09-23 08:35:00 | 2019-09-23 08:35:00 | 2019-09-23 08:42:00 | BO |  | Recovery of Desktop Screen Blackout. | Closed | admin.Donald Kerby L. Manejero
CSR-1221-19 | CSR | Rhea Joy S. Alminaza | 2019-09-23 13:16:00 | 2019-10-02 21:00:00 | 2019-10-15 07:25:00 | BO | Access Request | Please give access rights to Ms. Ramona Chariz Amon mirror access of Mr. Rolando Miguel. | Closed | admin.Joe Nico T. Geronimo
CSR-1230-19 | CSR | Albert L Tallafer | 2019-09-23 18:03:00 | 2019-09-24 21:00:00 | 2019-10-15 09:47:00 | BO | Modify Software | Additional IVMS viewer on the following areas 1.)Canteen Area 2.)Locker Area 3.)Shredding Room | Done | admin.Abel D. Chaves
QA-1708-19 | QA | Daryll M. Alorro | 2019-09-23 12:30:00 | 2019-09-23 12:30:00 | 2019-09-23 12:35:00 | BO |  | Input admin account for environment variables | Closed | admin.Joel Jr. M. Chavez
QA-1709-19 | QA | Mark John A. Tiongson | 2019-09-23 13:00:00 | 2019-09-23 13:00:00 | 2019-09-23 13:10:00 | BO |  | Inquiry for video con | Closed | admin.Joel Jr. M. Chavez
QA-1710-19 | QA | Mary Kathleen D. Brotonel | 2019-09-23 14:00:00 | 2019-09-23 14:00:00 | 2019-09-23 14:10:00 | BO | CAE-Extes | Reboot EXTES | Closed | admin.Joel Jr. M. Chavez
QA-1711-19 | QA | Rudy S. Obina | 2019-09-23 16:30:00 | 2019-09-23 16:30:00 | 2019-09-23 16:40:00 | BO | CAE-Extes | EXTES output faded | Closed | admin.Joel Jr. M. Chavez
QA-1712-19 | QA | Maria Josefa G. Samson | 2019-09-24 08:20:00 | 2019-09-24 08:20:00 | 2019-09-24 08:28:00 | BO |  | generate EMD branch quota | Closed | admin.Charmaine F. Layawon
QA-1713-19 | QA | Jayson P. Gabilo | 2019-09-24 09:22:00 | 2019-09-24 09:22:00 | 2019-09-24 09:28:00 | BO |  | Inquiry of Data Backup for overwrite file | Closed | admin.Joel Jr. M. Chavez
DRR-0130-19 | DRR | Jayson P. Gabilo | 2019-09-24 09:28:00 | 2019-09-24 09:28:00 | 2019-10-15 20:34:00 | BO | Windows | MHT.xls;Y:\01_JBRB_Design\02_DESIGNERS\6186_GERSON;Original Directory;No;Need to recover deleted items inside the excel file. | Done | admin.Joel Jr. M. Chavez
QA-1714-19 | QA | Hazel S. Poblacion | 2019-09-24 09:40:00 | 2019-09-24 09:40:00 | 2019-09-24 09:47:00 | BO |  | assist printing a3 size to a4 | Closed | admin.Charmaine F. Layawon
QA-1715-19 | QA | Jayson P. Gabilo | 2019-09-24 09:50:00 | 2019-09-24 09:50:00 | 2019-09-24 09:53:00 | BO |  | Inquiry for Time in | Closed | admin.Joel Jr. M. Chavez
DRR-0136-19 | DRR | Adrian N. Quiambao | 2019-09-24 13:46:00 | 2019-09-24 13:46:00 | 2019-10-15 20:35:00 | BO | Cae | PD_M22003V0AZZ002_0200A.ModelRoot;/export/home/eucoodb/model/work/HONDA/3V0A/ENG_ROOM/ZZ02;Original Directory;No;Overwrited data | Done | admin.Joel Jr. M. Chavez
QA-1716-19 | QA | John Anthony G. Presas | 2019-09-24 14:45:00 | 2019-09-24 14:45:00 | 2019-09-24 14:51:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
QA-1717-19 | QA | Jashen B. Eduque | 2019-09-24 14:35:00 | 2019-09-24 14:35:00 | 2019-09-24 14:40:00 | BO |  | Assist on RICOH paper roll loading | Closed | admin.Joel Jr. M. Chavez
CSR-1210-19 | CSR | Shenie Lou G Besa | 2019-09-24 15:18:00 | 2019-10-03 21:00:00 | 2019-10-01 12:41:00 | BO | Account Request | Request for deletion of Windows log in and folder access rights of end of contract employee. 1. pet6188 | Closed | admin.Joel Jr. M. Chavez
QA-1718-19 | QA | Lanz Miguel S. Zaldivar | 2019-09-24 15:30:00 | 2019-09-24 15:30:00 | 2019-09-24 15:35:00 | BO |  | Assist on DCVI5571 printing error | Closed | admin.Joel Jr. M. Chavez
QA-1719-19 | QA | Adrian N. Quiambao | 2019-09-24 15:15:00 | 2019-09-24 15:15:00 | 2019-09-24 15:42:00 | BO | CAE-CAE | Check data for recover of CAE file | Closed | admin.Joel Jr. M. Chavez
QA-1720-19 | QA | Kristel Anne D. Villanueva | 2019-09-25 08:59:00 | 2019-09-25 08:59:00 | 2019-09-25 09:02:00 | BO |  | allow remote desktop connection in 10.49.130.251 for pet6052 | Closed | admin.Charmaine F. Layawon
QA-1722-19 | QA | Hazel S. Poblacion | 2019-09-25 09:20:00 | 2019-09-25 09:20:00 | 2019-09-25 09:24:00 | BO |  | restart lync communicator services | Closed | admin.Charmaine F. Layawon
QA-1723-19 | QA | Albert L Tallafer | 2019-09-20 12:00:00 | 2019-09-20 12:00:00 | 2019-09-20 12:30:00 | BO |  | print department layout for BOC inspection | Closed | admin.Charmaine F. Layawon
QA-1724-19 | QA | Albert L Tallafer | 2019-09-24 16:45:00 | 2019-09-24 16:45:00 | 2019-09-24 17:10:00 | BO |  | print revised as built plan layout for PEZA inspection | Closed | admin.Charmaine F. Layawon
QA-1725-19 | QA | Cindy S. Antonillas | 2019-09-25 11:00:00 | 2019-09-25 11:00:00 | 2019-09-25 11:04:00 | BO |  | setup auto sync of lync conversation to outlook | Closed | admin.Charmaine F. Layawon
QA-1726-19 | QA | Jayson P. Gabilo | 2019-09-25 09:00:00 | 2019-09-25 09:00:00 | 2019-09-25 09:05:00 | BO |  | Assist on Lync Meeting | Closed | admin.Joel Jr. M. Chavez
QA-1727-19 | QA | Cesar Ian S Banquillo | 2019-09-25 09:30:00 | 2019-09-25 09:30:00 | 2019-09-25 09:55:00 | BO |  | Assist on Solidworks .IGS default file association | Closed | admin.Joel Jr. M. Chavez
QA-1728-19 | QA | Daryll M. Alorro | 2019-09-25 12:25:00 | 2019-09-25 12:25:00 | 2019-09-25 12:30:00 | BO |  | Input Admin Accounts for Environment Variables | Closed | admin.Joel Jr. M. Chavez
QA-1729-19 | QA | Adrian N. Quiambao | 2019-09-25 13:15:00 | 2019-09-25 13:15:00 | 2019-09-25 13:25:00 | BO | CAE-Extes | Reboot EXTES Printer | Closed | admin.Joel Jr. M. Chavez
QA-1730-19 | QA | Albert L Tallafer | 2019-09-25 11:00:00 | 2019-09-25 11:00:00 | 2019-09-25 11:15:00 | BO |  | Download Pictures from Office CP to Admin folder. | Closed | admin.Donald Kerby L. Manejero
QA-1731-19 | QA | Edvin B. Pantoni | 2019-09-23 10:08:00 | 2019-09-23 10:08:00 | 2019-09-23 10:15:00 | BO |  | Reservation of BT Conferencing Schedule. | Closed | admin.admin.Donald Kerby L. Manejero
QA-1732-19 | QA | Rommel E. Aguilon | 2019-09-26 09:00:00 | 2019-09-26 09:00:00 | 2019-09-26 09:15:00 | BO |  | Borrow and setup 1 unit laptop @ Admin Office. | Closed | admin.admin.Donald Kerby L. Manejero
CSR-1232-19 | CSR | Klyde Vincent N. LosbaÃ±es | 2019-09-26 11:10:00 | 2019-09-27 21:00:00 | 2019-10-03 14:42:00 | BO | Install Software | ODBC installation for Excel macro execution. | Done | admin.Joel Jr. M. Chavez
DRR-0139-19 | DRR | Rizza B. Bragancia | 2019-09-26 13:14:00 | 2019-11-21 17:00:00 | 2019-11-14 12:24:00 | BO | Cae | 1105_MARRON 1209_ãƒ•ãƒ©ãƒ³ã‚·ã‚¹;\\10.49.128.7\jbrb_(branch)\01_JBRB_Design\02_DESIGNERS;Original Directory;Yes;Was deleted a month ago prior to ISMS Audit in BO | Closed | admin.Joel Jr. M. Chavez
QA-1733-19 | QA | Anne Francine E. Almiranes | 2019-09-26 14:00:00 | 2019-09-26 14:00:00 | 2019-09-26 14:10:00 | BO |  | Reset of RRJ to YC Japan. | Closed | admin.admin.Donald Kerby L. Manejero
QA-1734-19 | QA | Christian Dell S. Tablac | 2019-09-26 17:10:00 | 2019-09-26 17:10:00 | 2019-09-26 17:15:00 | BO |  | Reset RRJ Extes at YC Japan | Closed | admin.admin.Donald Kerby L. Manejero
QA-1735-19 | QA | Noime V Balleser | 2019-09-27 15:45:00 | 2019-09-27 15:45:00 | 2019-09-27 16:00:00 | BO |  | reserve video con system | Closed | admin.Charmaine F. Layawon
QA-1736-19 | QA | Shenie Lou G Besa | 2019-09-27 16:30:00 | 2019-09-27 16:30:00 | 2019-09-27 16:40:00 | BO |  | assist changing email password | Closed | admin.Charmaine F. Layawon
CSR-1268-19 | CSR | Rosalinda P. Tayer | 2019-09-27 19:35:00 | 2019-10-22 20:22:00 | 2019-10-21 20:55:00 | BO | Transfer Software location | Request to Transfer PDF Foxit and Adobe Acrobat from 10.49.131.39 to 10.49.131.38 and from 10.49.131.40 to 10.49.131.37 | Done | admin.Joel Jr. M. Chavez
QA-1738-19 | QA | George Vincent C. Cagape | 2019-09-30 09:05:00 | 2019-09-30 09:05:00 | 2019-09-30 09:15:00 | BO |  | Assistance on Printer Config due to upgrade of Windows 10 OS. | Closed | admin.admin.Donald Kerby L. Manejero
QA-1739-19 | QA | John Michael V. Remo | 2019-09-30 09:15:00 | 2019-09-30 09:15:00 | 2019-09-30 09:25:00 | BO |  | Assistance on Printer Access dur to upgrade of Windows 10 OS. | Closed | admin.Donald Kerby L. Manejero
QA-1740-19 | QA | Carol Ann V. Dela Cruz | 2019-09-30 09:30:00 | 2019-09-30 09:30:00 | 2019-09-30 09:40:00 | BO |  | Assistance on FAX machine operation. | Closed | admin.Donald Kerby L. Manejero
QA-1741-19 | QA | Hazel S. Poblacion | 2019-09-30 09:40:00 | 2019-09-30 09:40:00 | 2019-09-30 09:45:00 | BO |  | Assistance on printing size ouput reduction (ratio). | Closed | admin.Donald Kerby L. Manejero
QA-1742-19 | QA | Albert L Tallafer | 2019-09-30 08:30:00 | 2019-09-30 08:30:00 | 2019-09-30 08:32:00 | BO |  | Assistance on transfer of pictures from Cellphone to Admin folder. | Closed | admin.Donald Kerby L. Manejero
QA-1743-19 | QA | Danica Mae T. Embate | 2019-10-01 08:15:00 | 2019-10-01 08:15:00 | 2019-10-01 08:27:00 | BO | CAE-Extes | restart remote printer r371 | Closed | admin.Charmaine F. Layawon
CSR-1238-19 | CSR | Donald Kerby L. Manejero | 2019-10-01 10:28:00 | 2019-10-10 21:00:00 | 2019-10-22 15:17:00 | BO | Access Request | Requesting Access to TDC folder for Expense and Investment Monitoring. | Closed | admin.Joe Nico T. Geronimo
QA-1744-19 | QA | Jeremias F. Gante | 2019-10-01 12:40:00 | 2019-10-01 12:40:00 | 2019-10-01 13:00:00 | BO |  | assist on Setup document camera and projector conf room | Closed | admin.Joel Jr. M. Chavez
QA-1745-19 | QA | Kim Carlo T. Alinguera | 2019-10-01 13:10:00 | 2019-10-01 13:10:00 | 2019-10-01 13:20:00 | BO | CAE-Extes | Reboot extes printer emulator | Closed | admin.Joel Jr. M. Chavez
CSR-1228-19 | CSR | Jennilyn C Dumancas | 2019-10-01 15:36:00 | 2019-10-17 17:00:00 | 2019-10-11 14:09:00 | BO | Access Request | Add access to PET-YGP Shared folder PET-YGP Shared (secret) | Closed | admin.Joel Jr. M. Chavez
QA-1746-19 | QA | Lanz Miguel S. Zaldivar | 2019-10-01 14:30:00 | 2019-10-01 14:30:00 | 2019-10-01 14:40:00 | BO |  | Assist on OCE mot plotting | Closed | admin.Joel Jr. M. Chavez
QA-1747-19 | QA | Joseph B. Azucena | 2019-10-02 12:35:00 | 2019-10-02 12:35:00 | 2019-10-02 12:40:00 | BO |  | Configure printer drivers | Closed | admin.Joel Jr. M. Chavez
QA-1748-19 | QA | Joseph B. Azucena | 2019-10-02 16:20:00 | 2019-10-02 16:20:00 | 2019-10-02 16:30:00 | BO |  | Allow Imaging device on 131.111 | Closed | admin.Joel Jr. M. Chavez
QA-1749-19 | QA | Krystine Mae B. Gale | 2019-10-02 19:30:00 | 2019-10-02 19:30:00 | 2019-10-02 19:40:00 | BO | CAE-Extes | Reboot Extes remote printer | Closed | admin.Joel Jr. M. Chavez
QA-1750-19 | QA | George Vincent C. Cagape | 2019-10-02 20:20:00 | 2019-10-02 20:20:00 | 2019-10-02 20:30:00 | BO |  | Assist on printer driver config | Closed | admin.Joel Jr. M. Chavez
CSR-1315-19 | CSR | Francis Razel R. YbaÃ±ez | 2019-10-03 08:50:00 | 2019-10-04 21:00:00 | 2019-10-28 14:49:00 | BO | PC Configuration | transfer internet access from 10.49.130.172 to 10.49.131.112 | Done | admin.Abel D. Chaves
CPR-0143-19 | CPR | Abel D. Chaves | 2019-10-03 09:38:00 | 2019-10-03 09:38:00 | 2019-10-23 10:28:00 | BO | PC Harddisk | very slow on booting up. almost no response | Done | admin.Abel D. Chaves
CPR-0142-19 | CPR | Charmaine F. Layawon | 2019-10-03 10:00:00 | 2019-10-02 08:00:00 | 2019-10-03 14:44:00 | BO | WS Harddisk | cannot boot OS | Done | admin.Joel Jr. M. Chavez
QA-1751-19 | QA | Daryll M. Alorro | 2019-10-03 14:00:00 | 2019-10-03 14:00:00 | 2019-10-03 14:05:00 | BO |  | Input Admin account for Environment Variables | Closed | admin.Joel Jr. M. Chavez
QA-1752-19 | QA | Aileen S. Juridico | 2019-10-03 14:05:00 | 2019-10-03 14:05:00 | 2019-10-03 14:30:00 | BO |  | reinstall and configure Java to allow IPMS | Closed | admin.Joel Jr. M. Chavez
QA-1753-19 | QA | Jesca Rose G. Muzones | 2019-10-03 18:00:00 | 2019-10-03 18:00:00 | 2019-10-03 18:05:00 | BO | CAE-CAE | Refresh Parts Master | Closed | admin.Joel Jr. M. Chavez
QA-1754-19 | QA | Kristie Marie S. Fabresis | 2019-10-03 18:05:00 | 2019-10-03 18:05:00 | 2019-10-03 18:10:00 | BO | CAE-CAE | Refresh Symbol Master | Closed | admin.Joel Jr. M. Chavez
QA-1755-19 | QA | Danica Mae T. Embate | 2019-10-03 18:15:00 | 2019-10-03 18:15:00 | 2019-10-03 18:25:00 | BO | CAE-Extes | Reboot EXTES Printer emulator | Closed | admin.Joel Jr. M. Chavez
QA-1756-19 | QA | Kim Carlo T. Alinguera | 2019-10-03 19:00:00 | 2019-10-03 19:00:00 | 2019-10-03 19:10:00 | BO |  | Assist on OCE not Plotting | Closed | admin.Joel Jr. M. Chavez
QA-1757-19 | QA | Toni Rose T. Chua | 2019-10-03 09:15:00 | 2019-10-03 09:15:00 | 2019-10-03 09:45:00 | BO |  | configure excel for shiteijikou tools | Closed | admin.Charmaine F. Layawon
QA-1758-19 | QA | Angelica Panes | 2019-10-02 13:35:00 | 2019-10-02 13:35:00 | 2019-10-02 13:45:00 | BO |  | configure tap card on wh_dcvi5571 | Closed | admin.Charmaine F. Layawon
QA-1759-19 | QA | Donabeth Jarabelo | 2019-10-02 13:45:00 | 2019-10-02 13:45:00 | 2019-10-02 13:55:00 | BO |  | configure tap card on wh_dcvi5571 | Closed | admin.Charmaine F. Layawon
QA-1760-19 | QA | Toni Rose T. Chua | 2019-10-03 13:50:00 | 2019-10-03 13:50:00 | 2019-10-03 14:00:00 | BO |  | change pdf xchange editor lang from jap to eng | Closed | admin.Charmaine F. Layawon
QA-1761-19 | QA | Mary Kathleen D. Brotonel | 2019-10-04 09:20:00 | 2019-10-04 09:20:00 | 2019-10-04 09:30:00 | BO |  | configure accounting settings dcvi5571 | Closed | admin.Charmaine F. Layawon
QA-1762-19 | QA | Mila Mae L Macabante | 2019-10-04 09:15:00 | 2019-10-04 09:15:00 | 2019-10-04 09:20:00 | BO |  | configure accounting settings dcvi5571 | Closed | admin.Charmaine F. Layawon
CSR-1253-19 | CSR | Marfel R. Dela Cruz | 2019-10-04 15:47:00 | 2019-10-07 21:00:00 | 2019-11-20 15:58:00 | BO | Transfer PC location | Transfer of PC location to smoothly perform assigned functions | Done | admin.Abel D. Chaves
CSR-1256-19 | CSR | Francis Razel R. YbaÃ±ez | 2019-10-07 08:17:00 | 2020-01-31 11:29:00 | 0000-00-00 00:00:00 | BO | Hardware Purchase | Purchase 2 units of Z240 for Kakotora Evaluation in Branch Office with EP no. 2020_1-6#2. refer to the attach file for the quotation. | Work in Progress | admin.Reymark B. Evangelista
CSR-1241-19 | CSR | Shenie Lou G Besa | 2019-10-07 10:35:00 | 2019-10-11 10:00:00 | 2019-10-11 11:42:00 | BO | Transfer Telephone location | Request for updating Telephone Locals | Done | admin.Abel D. Chaves
CSR-1246-19 | CSR | Via Camille B. Fernandez | 2019-10-07 13:38:00 | 2019-10-16 21:00:00 | 2019-10-09 10:38:00 | BO | Access Request | REQUEST: Access of PET6192 and PET6190 to \\\10.49.1.97\emd\EMD1102\Resource Center\YC-Parts\01_LONG COMPONENT\REQUEST MONITORING REASON: Requirement to do the job IP address: 10.49.130.45 and 10.49.130.42 | Done | admin.Abel D. Chaves
CSR-1243-19 | CSR | Marfel R. Dela Cruz | 2019-10-07 15:16:00 | 2019-11-21 17:00:00 | 2019-11-21 09:38:00 | BO | PC Configuration | Configuration of ODBC for the PC of Ms. Via Camille Fernandez (10.49.130.45) to perform YGP GPDB registration. ODBC GPDB (not KK) | Closed | admin.Joel Jr. M. Chavez
QA-1763-19 | QA | Sheena Mae B. Sadava | 2019-10-07 16:30:00 | 2019-10-07 16:30:00 | 2019-10-07 16:33:00 | BO |  | re-install printer connection due to Windows 10 upgrade. | Closed | admin.Donald Kerby L. Manejero
CPR-0153-19 | CPR | Luvlyn C. De Los Santos | 2019-10-07 21:09:00 | 2019-11-21 17:00:00 | 2019-10-25 13:20:00 | BO | Mouse | Slow response of Mouse (especially when dragging a model in Solidworks) | Closed | admin.Joel Jr. M. Chavez
CSR-1318-19 | CSR | Anna Liza E. Ilusorio | 2019-10-08 13:00:00 | 2020-01-15 13:00:00 | 0000-00-00 00:00:00 | BO | Hardware Purchase | 1 Desktop (July Budget) for New employee 1 MS Office Professional (July Budget) See attached budget and layout for deployment | Work in Progress | admin.Reymark B. Evangelista
QA-1764-19 | QA | Toni Rose T. Chua | 2019-10-08 11:00:00 | 2019-10-08 11:00:00 | 2019-10-08 11:15:00 | BO |  | excel macro crashes after processing | Closed | admin.Charmaine F. Layawon
CSR-1254-19 | CSR | Donald Kerby L. Manejero | 2019-10-08 16:13:00 | 2019-10-09 21:00:00 | 0000-00-00 00:00:00 | BO | Plotter Configuration | Annual Preventive Maintenance Checking of Ricoh Printer Plotter at Branch Office. Only Transportation Expenses will be shouldered by PET due to Warranty of the unit is until October 26, 2019. please see attached quotation. | Work in Progress | admin.Joe Nico T. Geronimo
CPR-0147-19 | CPR | Krispearl Joy E. Belano | 2019-10-09 14:41:00 | 2019-10-07 14:41:00 | 2019-11-19 18:40:00 | BO | Printer/Plotter | There is problem with BO-RRJ030. There is warning that terminal emulator stopped working. | Done | admin.Greg Daniel E. Mojica
QA-1765-19 | QA | Dioza C. Mula Cruz | 2019-10-09 14:15:00 | 2019-10-09 14:15:00 | 2019-10-09 14:25:00 | BO |  | change scan address of ford branch on wh_dcvi5571 | Closed | admin.Charmaine F. Layawon
QA-1766-19 | QA | Charibelle L. Ferrer | 2019-10-10 13:04:00 | 2019-10-10 13:04:00 | 2019-10-10 13:08:00 | BO |  | Reset of TABM61773 @ 10.49.128.12 | Closed | admin.Donald Kerby L. Manejero
QA-1767-19 | QA | Jayson P. Gabilo | 2019-10-10 09:00:00 | 2019-10-10 09:00:00 | 2019-10-10 09:05:00 | BO |  | Support for Printer Setup due to new Windows 10 upgrade. | Closed | admin.Donald Kerby L. Manejero
QA-1768-19 | QA | Rosalinda P. Tayer | 2019-10-10 08:30:00 | 2019-10-10 08:30:00 | 2019-10-10 08:35:00 | BO |  | Setup of Printer, Email and default pdf viewer and search engine due to new Windows 10 upgrade. | Closed | admin.Donald Kerby L. Manejero
CSR-1266-19 | CSR | Rudy S. Obina | 2019-10-11 09:52:00 | 2019-10-14 21:00:00 | 2019-10-16 06:51:00 | BO | Backup CAE file/s | 10.49.128.11,CAE folder creation and files back-up export/home/eucoodb/model/work/HONDA/ TMC T5NR S0PA T5N TFSS | Assigned | admin.Patrick Robin Vinas
CSR-1260-19 | CSR | Via Camille B. Fernandez | 2019-10-11 13:29:00 | 2019-10-14 21:00:00 | 2019-10-14 21:35:00 | BO | Install Software | Software installation of SAP GUI for 10.49.130.45 and 10.49.130.42. | Done | admin.Joel Jr. M. Chavez
QA-1769-19 | QA | Glenn L. Fabian | 2019-10-11 12:35:00 | 2019-10-11 12:35:00 | 2019-10-11 12:45:00 | BO |  | Add Tap CARD to DCV5576 | Closed | admin.Joel Jr. M. Chavez
QA-1770-19 | QA | Marfel R. Dela Cruz | 2019-10-11 12:45:00 | 2019-10-11 12:45:00 | 2019-10-11 13:05:00 | BO |  | Verify SAP GUI not running | Closed | admin.Joel Jr. M. Chavez
QA-1771-19 | QA | Wennie Rose C. Camus | 2019-10-11 13:30:00 | 2019-10-11 13:30:00 | 2019-10-11 13:50:00 | BO |  | Assist on Excel page customization | Closed | admin.Joel Jr. M. Chavez
QA-1772-19 | QA | Kristie Marie S. Fabresis | 2019-10-11 14:00:00 | 2019-10-11 14:00:00 | 2019-10-11 14:05:00 | BO | CAE-CAE | Refresh Tab Symbol | Closed | admin.Joel Jr. M. Chavez
QA-1773-19 | QA | Racky E. Faisan | 2019-10-11 14:10:00 | 2019-10-11 14:10:00 | 2019-10-11 14:15:00 | BO | CAE-Extes | Reboot RRJ Printer Emulator | Closed | admin.Joel Jr. M. Chavez
QA-1774-19 | QA | Princess Mae F. Punsalan | 2019-10-11 15:00:00 | 2019-10-11 15:00:00 | 2019-10-11 15:05:00 | BO | CAE-CAE | Refresh Tab Symbol | Closed | admin.Joel Jr. M. Chavez
QA-1775-19 | QA | Mila Mae L Macabante | 2019-10-11 15:30:00 | 2019-10-11 15:30:00 | 2019-10-11 15:35:00 | BO |  | Assist on Printing DCVI5571 | Closed | admin.Joel Jr. M. Chavez
CPR-0154-19 | CPR | RBY E. Taberna | 2019-10-14 09:37:00 | 2019-10-08 09:37:00 | 2019-10-23 11:27:00 | BO | Mouse | right click options of the mouse keep on appearing even though you only use the left click. Also, sometimes it directly open files with one click which can be only open by double clicking. | Done | admin.Abel D. Chaves
CSR-1339-19 | CSR | Rhea Joy S. Alminaza | 2019-10-14 10:44:00 | 2019-10-30 11:52:00 | 2019-10-28 11:52:00 | BO | Access Request | Please give full access to 7 employees, name was indicated in UARF and also give access to CONN members of HO only, they can access and write to their respective folders but they cannot see the other folders of members. Location= \\Petsvr1097\cdd\Performance Dashboard | Done | admin.Joe Nico T. Geronimo
CSR-1303-19 | CSR | Rhea Joy S. Alminaza | 2019-10-14 10:56:00 | 2019-11-21 17:00:00 | 2019-10-24 13:31:00 | BO | Access Request | Please give full access to 7 employees, name was indicated in UARF and also give access to CONN members of BO only, they can access and write to their respective folders but they cannot see the other folders of members, kindly see the new location below. Location= \\Petsvr1097\cdd\Performance Dashboard | Closed | admin.Joel Jr. M. Chavez
QA-1777-19 | QA | Princess Mae F. Punsalan | 2019-10-14 08:00:00 | 2019-10-14 08:00:00 | 2019-10-14 08:15:00 | BO |  | Reset windows password for MHT | Closed | admin.Charmaine F. Layawon
QA-1778-19 | QA | Albert L Tallafer | 2019-10-14 08:30:00 | 2019-10-14 08:30:00 | 2019-10-14 08:40:00 | BO |  | transfer pics to server | Closed | admin.Charmaine F. Layawon
QA-1779-19 | QA | Jane D. Amboy | 2019-10-14 11:00:00 | 2019-10-14 11:00:00 | 2019-10-14 11:30:00 | BO | CAE-Extes | restart remote printer R371 | Closed | admin.Charmaine F. Layawon
QA-1780-19 | QA | Ana Ceniza M. Abarca | 2019-10-14 09:30:00 | 2019-10-14 09:30:00 | 2019-10-14 10:00:00 | BO |  | configure odbc gpdb settings on 10.49.130.38 for pet6163 | Closed | admin.Charmaine F. Layawon
QA-1781-19 | QA | Hazel S. Poblacion | 2019-10-14 10:00:00 | 2019-10-14 10:00:00 | 2019-10-14 10:25:00 | BO |  | access timekeeping server | Closed | admin.Charmaine F. Layawon
QA-1782-19 | QA | Kristie Marie S. Fabresis | 2019-10-11 15:50:00 | 2019-10-11 15:50:00 | 2019-10-14 16:00:00 | BO | CAE-CAE | refresh tab sym M61 | Closed | admin.Charmaine F. Layawon
CSR-1283-19 | CSR | Kerby Joy S. Yu | 2019-10-14 14:06:00 | 2019-10-15 21:00:00 | 0000-00-00 00:00:00 | BO | Account Request | modify seine2 account access rights for accessing component drawings. the same SEINE2 account with (PET0813) Mr. Marfel Dela Cruz | Work in Progress | admin.Joel Jr. M. Chavez
CSR-1267-19 | CSR | Shenie Lou G Besa | 2019-10-14 16:04:00 | 2019-10-23 21:00:00 | 2019-10-25 13:42:00 | BO | Account Request | Request for SEINE2 account of Toyota member. 1. pet6187 | Done | admin.Abel D. Chaves
QA-1783-19 | QA | Jayson P. Gabilo | 2019-10-14 12:45:00 | 2019-10-14 12:45:00 | 2019-10-14 12:55:00 | BO |  | Register Tap CArd | Closed | admin.Joel Jr. M. Chavez
QA-1784-19 | QA | Jhomar M. Miquiabas | 2019-10-14 13:15:00 | 2019-10-14 13:15:00 | 2019-10-14 13:30:00 | BO |  | Reserve video conference | Closed | admin.Joel Jr. M. Chavez
QA-1785-19 | QA | Rhea Joy S. Alminaza | 2019-10-14 13:40:00 | 2019-10-14 13:40:00 | 2019-10-14 14:00:00 | BO |  | Verify and Config Con Branch dashboard access | Closed | admin.Joel Jr. M. Chavez
QA-1786-19 | QA | Danica Mae T. Embate | 2019-10-14 14:50:00 | 2019-10-14 14:50:00 | 2019-10-14 15:20:00 | BO |  | Reboot Extes printer emulator | Closed | admin.Joel Jr. M. Chavez