## Worksheet
HO December 2019
New Request | Assigned | Work in Progress | Done | Closed | Total
0 | 3 | 6 | 95 | 4 | 108
| Completed | On-going | Delay | Total Request | Completion % | On Time %
CSR | 79 | 5 | 4 | 88 | 89.77 | 94.94
CPR | 14 | 0 | 0 | 14 | N/A | N/A
DRR | 6 | 0 | 0 | 6 | N/A | N/A
Member | Assigned | Work in Progress | Done | Closed
admin.Aaron Jet N. Sarreal | 0 | 0 | 4 | 0
admin.Abel D. Chaves | 0 | 0 | 2 | 0
admin.Charmaine F. Layawon | 0 | 0 | 1 | 0
admin.Christ John Dela Cruz | 0 | 0 | 3 | 0
admin.Corazon A. Coronel | 0 | 0 | 0 | 0
admin.Greg Daniel E. Mojica | 0 | 0 | 3 | 0
admin.Jasper Labenia | 2 | 2 | 16 | 2
admin.Joe Nico T. Geronimo | 1 | 1 | 20 | 0
admin.Joel Jr. M. Chavez | 0 | 0 | 1 | 0
admin.John Christian Lovitos | 0 | 2 | 3 | 0
admin.Kiel Antaran | 0 | 0 | 0 | 1
admin.Patrick Robin Vinas | 0 | 0 | 1 | 0
admin.Reymark B. Evangelista | 0 | 1 | 35 | 0
admin.Willem R. Leonardo | 0 | 0 | 6 | 2
Reference # | Process | Requestor | Date Request | Date Needed | Date Done | Site | Category | Details | Status | Assigned to
DRR-0156-19 | DRR | Mae Anne B. Tabasin | 2019-11-18 09:13:00 | 2019-11-18 09:13:00 | 2019-12-02 22:09:00 | HO | Cae | PD_JV20C1ULS300-D0000.ModelRoot;/export/home/eucoodb/model/work/TRAINING/2019/GMT/SEPH/JV_20C1ULS300;Original Directory;Yes;Corrupted file. | Done | admin.John Christian Lovitos
CSR-1510-19 | CSR | Francis Benjamin C. Cagampan | 2019-11-18 10:14:00 | 2019-11-19 21:00:00 | 2019-12-04 18:51:00 | HO | Transfer PC location | Storage request of PC to MIS Department. Since the PC is no longer being used, However the PC is still under monitoring of JBRB IP Addresses - 10.49.3.250 - 10.49.1.155 - 10.49.7.226 (MIS borrowed Unit) | Done | admin.Jasper Labenia
CSR-1453-19 | CSR | Francis Benjamin C. Cagampan | 2019-11-18 11:00:00 | 2019-11-19 21:00:00 | 2019-12-09 14:50:00 | HO | Transfer PC location | Storage request of PC to MIS department. the PC is no longer being used, however, the UNIT is still under the Monitoring of JBRB department IP Addresses - 10.49.1.155 - 10.49.7.226 - 10.49.3.250 | Done | admin.Jasper Labenia
CSR-1578-19 | CSR | Roda A. Dela Pena | 2019-11-18 11:13:00 | 2019-11-19 21:00:00 | 2019-12-17 08:08:00 | HO | Install Software | Please install Bandicam for the followin addresses 10.49.3.8 10.49.3.227 We need the bandicam to explain how the tube was input. | Done | admin.Reymark B. Evangelista
CSR-1507-19 | CSR | Jerald F. Dizon | 2019-11-18 14:15:00 | 2019-11-19 21:00:00 | 2019-12-03 10:54:00 | HO | Backup CAE file/s | /export/home/eucoodb/model/work/HONDA/3S5F | Done | admin.Greg Daniel E. Mojica
CSR-1467-19 | CSR | Jeffrey S. Bernales | 2019-11-18 14:08:00 | 2019-11-19 21:00:00 | 2019-11-25 11:05:00 | HO | Backup CAE file/s | *CAE Honda file for creation & backup. /export/home/eucoodb/model/work/HONDA/3S6A | Done | admin.John Christian Lovitos
CSR-1579-19 | CSR | Grace A. Rivera | 2019-11-18 14:24:00 | 2019-11-27 21:00:00 | 2020-01-14 12:35:00 | HO | Account Request | Request of Reset Password in CMMS and SEINE2 for the following EV members - Julius Gambon (1196) - Lucindo Sofronio Valenciano (1472) - Jeffrey Macarayon (1685) - Clariza Capones (1801) - Faustino Santos Jr. (1820) | Done | admin.Joe Nico T. Geronimo
CSR-1483-19 | CSR | Belinda C. Cabico | 2019-11-18 16:38:00 | 2019-11-27 21:00:00 | 2020-01-02 06:35:00 | HO | Access Request | Deletion of Windows Log-in, Seine2 and Design Source Web, OMS | Done | admin.Joe Nico T. Geronimo
CSR-1454-19 | CSR | Francis Benjamin C. Cagampan | 2019-11-18 16:35:00 | 2019-11-27 21:00:00 | 2019-12-06 13:41:00 | HO | Install Software | JBRB department would like to ask for upgrade the Service Pack of CATIA version on our side. from CATIA V5-R25 âž” CATIA V5-R2, this is for All CATIA workstation. however, please keep the CATIA V5-R25 version in workstation 10.49.2.242 and 10.49.2.227. in these 2, there will be 2 available version. as for the others only 1 version will be kept. | Done | admin.Jasper Labenia
CPR-0176-19 | CPR | Katherine Q. Ronquillo | 2019-11-18 18:33:00 | 2019-11-18 18:33:00 | 2020-01-06 18:09:00 | HO | Mouse | Faulty mouse. | Done | admin.Willem R. Leonardo
CSR-1466-19 | CSR | Rudy S. Obina | 2019-11-19 07:29:00 | 2019-11-20 21:00:00 | 2019-12-19 21:53:00 | HO | Backup CAE file/s | 10.49.1.50,CAE folder creation and files back-up export/home/eucoodb/model/work/HONDA/ 3V5F | Closed | admin.Kiel Antaran
CSR-1455-19 | CSR | Jovielet B. Caintoy | 2019-11-19 09:11:00 | 2019-11-28 21:00:00 | 2019-11-25 12:34:00 | HO | Access Request | Request folder access right | Done | admin.Abel D. Chaves
CSR-1576-19 | CSR | Ma. Reina Monserrat A. Abalos | 2019-11-19 09:25:00 | 2020-01-06 11:29:00 | 2020-01-03 11:29:00 | HO | Backup to CD/DVD | back up following files from 10.49.2.244\D | Done | admin.Joe Nico T. Geronimo
CSR-1492-19 | CSR | Rommel E. Aguilon | 2019-11-19 15:04:00 | 2019-12-04 06:58:00 | 2019-12-04 06:59:00 | HO | Account Request | Please delete windows log-in of Mr. Archie Huevos (end contract). All email will forwarded to Rommel Aguilon | Done | admin.Reymark B. Evangelista
CSR-1465-19 | CSR | Franz Myka M. Dumlao | 2019-11-20 14:14:00 | 2019-11-21 21:00:00 | 2019-11-25 11:12:00 | HO | Backup CAE file/s | CAE GM folder request for back up * /export/home/eucoodb/model/work/GM-YYA/B121S * /export/home/eucoodb/model/work/GM-YYA/C121 * /export/home/eucoodb/model/work/GM-YTM/C110 | Done | admin.John Christian Lovitos
CSR-1477-19 | CSR | Ruby A. Maghilum | 2019-11-20 15:18:00 | 2019-11-21 21:00:00 | 2019-11-26 16:24:00 | HO | Transfer PC location | My computer is running slow due to low memory. Request to switch CPU of R. Maghilum with IP address of 10.49.2.182 to Vacant PC beside G. Sore with IP address of 10.49.5.11. see attached file for details | Done | admin.Jasper Labenia
CPR-0171-19 | CPR | Charmaine F. Layawon | 2019-11-20 18:44:00 | 2019-11-19 14:00:00 | 2019-11-27 10:13:00 | HO | Printer/Plotter | Faded ouput | Done | admin.Reymark B. Evangelista
CPR-0170-19 | CPR | Charmaine F. Layawon | 2019-11-20 18:46:00 | 2019-11-19 14:00:00 | 2019-11-27 10:14:00 | HO | Printer/Plotter | paper guide misfeed / paper jam already reported to supplier Ref Number 92093802 | Done | admin.Reymark B. Evangelista
CPR-0172-19 | CPR | Charmaine F. Layawon | 2019-11-20 18:49:00 | 2019-11-20 14:00:00 | 2019-11-27 10:17:00 | HO | Printer/Plotter | paper jam (feeding media and printing) sent email to supplier - 11/20/2019 | Done | admin.Reymark B. Evangelista
CSR-1468-19 | CSR | Jenny Lyn G. Miranda | 2019-11-20 19:54:00 | 2019-11-22 21:00:00 | 2019-11-29 14:50:00 | HO | Modify Software | I would like to request for URGENT update of Catia machines to Version 2017. We've been receiving job requests from TBU customer that uses CATIA Version 2017. Here are the IP addresses of PCs to be update. 10.49.1.230 10.49.1.89 10.49.1.182 10.49.2.103 We need this update by 11/22 (earlier the better) Thank you very much in advance for your support! | Done | admin.Jasper Labenia
CSR-1512-19 | CSR | Franz Myka M. Dumlao | 2019-11-21 11:59:00 | 2020-01-06 11:21:00 | 2020-01-03 11:21:00 | HO | Backup to CD/DVD | Files for CD transfer \\10.49.1.97\wh\GMT\DOCUMENTS\FOR CD transfer\Progress List | Done | admin.Joe Nico T. Geronimo
CSR-1505-19 | CSR | John Erick A. Nombrefia | 2019-11-21 16:24:00 | 2019-11-22 21:00:00 | 2019-12-03 10:41:00 | HO | Backup CAE file/s | We are just starting to transfer our files to repository. As per information, to start it, we need to request to your department to create folders of all our models in work folder. So, please create Mazda folder in repository, copying all model (folders) in this location - /export/home/eucodb/model/work/MAZDA Thank you. | Done | admin.Greg Daniel E. Mojica
CSR-1480-19 | CSR | Kristine G. Boado | 2019-11-22 09:41:00 | 2020-01-06 08:00:00 | 2020-01-07 15:06:00 | HO | Software Purchase | Request for Purchase 1. Microsoft Lync for Johanna Marie Dandan (Budget January 2020 - P1,500) To be use for coordinating the KPI Monitoring of PRT HO/BO | Done | admin.Reymark B. Evangelista
CSR-1517-19 | CSR | Rommel E. Aguilon | 2019-11-22 09:52:00 | 2020-01-08 09:47:00 | 2020-01-08 09:47:00 | HO | Account Request | Please check access of PET nurse. They should NOT access PET Common Folder but upon checking in the ISMS Internal Audit they can access. | Done | admin.Reymark B. Evangelista
CSR-1575-19 | CSR | Grace A. Rivera | 2019-11-22 10:39:00 | 2019-12-03 21:00:00 | 2020-01-03 08:00:00 | HO | Account Request | Request Email Address for Mr. Janser Del-Isen (1230) | Done | admin.Joe Nico T. Geronimo
CPR-0175-19 | CPR | Redemptor C. Batiduan | 2019-11-22 10:48:00 | 2019-11-22 10:48:00 | 2019-12-04 12:25:00 | HO | Mouse | Mouse is for replacement. Left button is defective. | Closed | admin.Willem R. Leonardo
DRR-0160-19 | DRR | Melanie D. Crispino | 2019-11-22 13:11:00 | 2019-11-22 13:11:00 | 2020-01-08 13:10:00 | HO | Windows | CE19-PK-D108;X:\CDE\01CDC Start 16 June\YSCP\CE19-PK-D108(191004)\â‘¦OTHERS;Original Directory;No;Due to customer request | Done | admin.Jasper Labenia
CSR-1503-19 | CSR | Jason L Odtuhan | 2019-11-22 13:36:00 | 2019-11-25 21:00:00 | 2019-12-05 15:04:00 | HO | Install Software | WE WANT TO INSTALL ANOTHER CATIA 2016 VERSION BECAUSE WE HAVE TOO MANY REQUEST OF 3D MODEL AND THE COMPUTER THAT WE ONLY HAVE WITH 2016 VERSION HERE IS 2. (2 PC) IP = 10.49.3.83 IP = 10.49.2.23 | Done | admin.Jasper Labenia
CPR-0174-19 | CPR | Charmaine F. Layawon | 2019-11-22 14:00:00 | 2019-11-22 07:00:00 | 2019-12-17 09:17:00 | HO | Server | cannot boot 10.49.1.100 server | Done | admin.Joel Jr. M. Chavez
CSR-1476-19 | CSR | Johanna D. Santos | 2019-11-22 15:06:00 | 2019-11-25 15:06:00 | 2019-11-26 08:23:00 | HO | Install Software | Install electronic stamp for Mr. Ray Miguel B. Cornejo (HR-AM) under IP address 10.49.3.33 | Done | admin.Reymark B. Evangelista
CSR-1574-19 | CSR | Alvin B. Raposon | 2019-11-25 07:57:00 | 2019-12-19 10:47:00 | 2019-12-19 10:48:00 | HO | Download | Downloading of Material Specs for Design Study | Done | admin.Reymark B. Evangelista
CSR-1516-19 | CSR | John Kristoffer V. Versoza | 2019-11-25 08:34:00 | 2019-12-04 21:00:00 | 2019-12-03 14:27:00 | HO | Access Request | MHT, cannot access. Forgot password. | Done | admin.Willem R. Leonardo
CSR-1463-19 | CSR | Roner B. Paguirigan | 2019-11-25 08:42:00 | 2019-12-04 21:00:00 | 2019-12-02 13:36:00 | HO | Access Request | FULL ACCESS TO WHE_BO SERVER \\10.49.128.7\whe_(branch) need for documents approval in BO. | Done | admin.Abel D. Chaves
CSR-1464-19 | CSR | Belinda C. Cabico | 2019-11-25 09:21:00 | 2019-12-04 21:00:00 | 2019-11-25 13:57:00 | HO | Access Request | Access Request for pet0484 (Ms Rose Mary Grace B. Piquero) Full Access \\10.49.1.97\eed\EED_Hardisk 5S\YNA EDS \\10.49.1.97\eed\EED_Hardisk 5S\RNBU \\10.49.1.97\eed\HELP JOBS Read-only access \\10.49.1.97\eed\EDS (Non Sales) \\10.49.1.97\eed\home | Done | admin.Reymark B. Evangelista
CSR-1499-19 | CSR | Jan Ruwiltton N. Tropicales | 2019-11-25 09:27:00 | 2020-01-08 06:56:00 | 2020-01-08 06:58:00 | HO | Account Request | Personal e-mail account request. | Done | admin.Reymark B. Evangelista
CSR-1482-19 | CSR | Jan Ruwiltton N. Tropicales | 2019-11-25 09:31:00 | 2019-12-04 21:00:00 | 2019-12-17 06:59:00 | HO | Access Request | Access to folder of MBU. I.D # 1560 For MDC/MBU job monitoring. \\10.49.1.97\eed\EED_Hardisk 5S\MBU | Done | admin.Reymark B. Evangelista
CSR-1522-19 | CSR | Rose Mary Grace B. Piquero | 2019-11-25 10:21:00 | 2019-12-04 21:00:00 | 2019-12-19 14:27:00 | HO | PC Configuration | Please transfer email configuration with email address rosemary.piquero@ph.yazaki.com from 10.49.5.241 to 10.49.2.55 due to transfer of member | Done | admin.Reymark B. Evangelista
CPR-0169-19 | CPR | Joe Nico T. Geronimo | 2019-11-25 10:55:00 | 2019-11-22 10:55:00 | 2019-11-25 12:00:00 | HO | Server | Problem in Active Directory | Done | admin.Joe Nico T. Geronimo
CSR-1523-19 | CSR | Redemptor C. Batiduan | 2019-11-25 13:53:00 | 2019-11-26 21:00:00 | 2020-01-15 12:25:00 | HO | Install Software | Upgrade the version of Enovia DMU Navigator from V5-6R2015 to V5-6R2017 in the following PCs. 1) 10.49.5.138 (license server) 2) 10.49.5.119 3) 10.49.1.189 4) 10.49.1.234 5) 10.49.1.209 6) 10.49.3.96 7) 10.49.1.161 Install Enovia DMU Navigator V5-6R2017 on this PC. 1) 10.49.3.82 2) 10.49.1.127 3) 10.49.2.194 | Closed | admin.Jasper Labenia
CSR-1502-19 | CSR | Ma. Kristela T. Meomeo | 2019-11-25 14:08:00 | 2020-02-24 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | Request for new PC (ProDesk 400 G4 SFF PC). PC replacement for pet2pc2185. | Work in Progress | admin.Joe Nico T. Geronimo
CSR-1573-19 | CSR | Rhiessa Sarah Z. Tuyor | 2019-11-25 15:18:00 | 2019-11-26 21:00:00 | 2020-01-02 13:07:00 | HO | Install Software | Transfer the Lync from IP 10.49.5.122 to my computer IP 10.49.3.200 | Done | admin.Joe Nico T. Geronimo
CPR-0178-19 | CPR | Jasper Labenia | 2019-11-25 21:16:00 | 2019-11-25 21:16:00 | 2019-12-06 13:40:00 | HO | Printer/Plotter | Paperjam | Done | admin.Jasper Labenia
CPR-0177-19 | CPR | Jasper Labenia | 2019-11-25 21:20:00 | 2019-11-25 21:20:00 | 2019-12-04 18:48:00 | HO | Printer/Plotter | Error 4533 | Done | admin.Jasper Labenia
CSR-1474-19 | CSR | Jennygene P. Toding | 2019-11-26 06:45:00 | 2020-02-28 06:46:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | Replacement CAE Server 2019/7-12#34 | Work in Progress | admin.John Christian Lovitos
CSR-1475-19 | CSR | Jennygene P. Toding | 2019-11-26 06:48:00 | 2020-02-28 06:49:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | CAE Replacement Server 2020/1-6#13 | Work in Progress | admin.John Christian Lovitos
CSR-1518-19 | CSR | Jeniline Trina M. Jamora | 2019-11-26 09:18:00 | 2020-04-06 08:00:00 | 0000-00-00 00:00:00 | HO | Install Software | Install AL2 License for CATIA to 10.49.1.55 for EEDS Training. | Work in Progress | admin.Jasper Labenia
CSR-1504-19 | CSR | Cecil T. Morales | 2019-11-26 09:23:00 | 2019-12-05 21:00:00 | 2019-12-13 12:12:00 | HO | Access Request | I would like to request an access to HINO folders. To be able to monitor job requests, update informations and members workload. | Done | admin.Reymark B. Evangelista
DRR-0161-19 | DRR | Rosalinda P. Tayer | 2019-11-26 09:23:00 | 2019-11-22 19:00:00 | 2019-12-03 14:07:00 | HO | Windows | 21B121100_G-G0000 (BODY).xls;\\Petsvr1097\wh\GMT\MONITORING SHEETS\SCHEDULE OF IN-CHARGE\JOB PLAN\December\ ;Original Directory;No;The file saved last Friday (11/22/19) were different from the latest file saved (11/25/19) in the server. | Done | admin.Willem R. Leonardo
CSR-1479-19 | CSR | Jaedicke C. Gaerlan | 2019-11-26 11:02:00 | 2019-12-05 21:00:00 | 2019-11-27 07:12:00 | HO | Access Request | Request to access the files in the folder mentioned below \\10.49.1.97\common\â˜…â˜…YC EVP Mr. Watanabe Projectâ˜…â˜… | Done | admin.Joe Nico T. Geronimo
CSR-1527-19 | CSR | Karl Christopher G. Abanto | 2019-11-26 11:13:00 | 2019-11-27 21:00:00 | 2019-12-10 09:10:00 | HO | Modify Software | Cannot log-in on VNC 10.49.0.100 and 10.49.0.96 due to there is no pop-up box log-in for password. | Done | admin.Christ John Dela Cruz
CSR-1494-19 | CSR | Joe Nico T. Geronimo | 2019-11-26 14:30:00 | 2019-12-05 21:00:00 | 2019-12-04 06:56:00 | HO | Account Request | Request for windows log in for new MIS Supervisor | Done | admin.Reymark B. Evangelista
CSR-1513-19 | CSR | Imee B. Briones | 2019-11-27 08:59:00 | 2019-11-28 21:00:00 | 2020-01-10 07:57:00 | HO | Backup to CD/DVD | Kindly transfer files to CD and delete in the network after copy. Thanks. | Done | admin.Aaron Jet N. Sarreal
CSR-1495-19 | CSR | Joan M. Rivera | 2019-11-27 09:47:00 | 2019-12-06 21:00:00 | 2020-01-03 10:12:00 | HO | Access Request | Jennifer Umali cannot save and edit on the below folder. We do not request access restriction for the below folder please delete access restriction on below folder \\petsvr1097\WH\COMMON\MS_Common This file is for common use of all wiring harness members. | Done | admin.Joe Nico T. Geronimo
CSR-1498-19 | CSR | Cecil T. Morales | 2019-11-27 10:04:00 | 2019-12-20 09:17:00 | 2019-12-18 09:50:00 | HO | Account Request | Request of new outlook email for Jenneth M. Luna (TYT-NIM) IP 10.49.2.89 Raymond M. Salta (HINO) IP 10.49.3.93 To be used for job coordination, sending and receiving of information from Japan customers and other PET departments. | Done | admin.Joe Nico T. Geronimo
CSR-1481-19 | CSR | Rhiessa Sarah Z. Tuyor | 2019-11-27 11:55:00 | 2019-11-28 21:00:00 | 2019-11-28 11:06:00 | HO | Access Request | I like to have an access to \\10.49.1.97\jbrb-ce. For job collaboration purposes | Done | admin.Reymark B. Evangelista
CSR-1484-19 | CSR | Joel Jr. M. Chavez | 2019-11-27 14:27:00 | 2019-11-28 21:00:00 | 2019-11-27 14:39:00 | HO | Account Request | Deletion of group without members in active directory | Done | admin.Reymark B. Evangelista
CPR-0173-19 | CPR | Alvin B. Raposon | 2019-11-28 07:38:00 | 2019-11-25 07:38:00 | 2019-12-12 12:55:00 | HO | PC Power Supply | DRIVER POWER STATE FAILURE | Done | admin.Willem R. Leonardo
CSR-1485-19 | CSR | Corazon A. Coronel | 2019-11-28 08:52:00 | 2020-02-27 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | Purchase 4 Projectors September Budget (156,000) | Assigned | admin.Jasper Labenia
CSR-1487-19 | CSR | John Erick A. Nombrefia | 2019-11-28 09:28:00 | 2019-12-09 21:00:00 | 2020-01-28 06:12:00 | HO | Access Request | Our counterpart (NIIMI) wants us to try RRJA02 Ato Hippari Application in Extes. Upon trying, it says that we have no permission from the factory. They asked us if you are able to check it and make a way for us to have access. I attached the Access Request form with screenshot of message from Extes. Thank you so much! | Done | admin.Christ John Dela Cruz
CSR-1490-19 | CSR | Rommel E. Aguilon | 2019-11-28 18:14:00 | 2019-12-09 21:00:00 | 2019-12-09 14:53:00 | HO | Account Request | account request for Mr. Paul Vincent Arceo (ADM Specialist) ** Same access right as Eric Nealega | Done | admin.Jasper Labenia
CSR-1515-19 | CSR | Rommel E. Aguilon | 2019-11-29 09:23:00 | 2019-12-02 21:00:00 | 2019-12-04 06:54:00 | HO | Outsources Request | Please order toner for 6055. please perform needed actions | Done | admin.Reymark B. Evangelista
CSR-1571-19 | CSR | Melisa T. Miguel | 2019-11-29 10:51:00 | 2019-12-02 21:00:00 | 2020-01-03 07:44:00 | HO | Add Internet Connection | access to www.misumi.co.jp For details of collar, nuts and bolts | Done | admin.Reymark B. Evangelista
QA-1856-19 | QA | Julie Anne T. Tud | 2019-11-29 12:51:00 | 2019-11-29 12:51:00 | 2019-11-29 14:00:00 | HO |  | mail box is full | Closed | admin.Willem R. Leonardo
CSR-1514-19 | CSR | Melissa R. Talabong | 2019-11-29 13:34:00 | 2019-12-02 21:00:00 | 2019-12-16 07:20:00 | HO | Guest Connection | Please provide internet access for our PWC auditor srating December 2, 2019. | Done | admin.Joe Nico T. Geronimo
CSR-1528-19 | CSR | Vicente Z. Nieto | 2019-12-02 14:24:00 | 2019-12-17 21:30:00 | 2019-12-17 08:31:00 | HO | Laptop Configuration | Kindly configure the laptop of our visitors (Mr. Kei Fukui and Mr. Haruto Masuda) they want to access their email and can access TBU folder. The said counterpart will teach PET TBU members for Costing job. | Done | admin.Aaron Jet N. Sarreal
CSR-1529-19 | CSR | Francis Benjamin C. Cagampan | 2019-12-02 15:38:00 | 2019-12-04 21:00:00 | 2020-01-16 21:19:00 | HO | Transfer Software location | Transfer PLOCOMP software from 10.49.5.189 to 10.49.1.194 transfer CATIA Viewer from 10.49.5.191 to 10.49.1.52 | Done | admin.Jasper Labenia
CSR-1519-19 | CSR | Ma. Filipina G. Del Rosario | 2019-12-02 15:29:00 | 2019-12-11 21:00:00 | 2019-12-04 06:52:00 | HO | Access Request | Please Grant access rights for 2 CON members(Please see attached). | Done | admin.Reymark B. Evangelista
CSR-1530-19 | CSR | Francis Benjamin C. Cagampan | 2019-12-02 15:50:00 | 2019-12-04 21:00:00 | 2019-12-13 12:36:00 | HO | Transfer Telephone location | Transfer of Telephone to new location for effeciency. 613, beside 10.49.3.66. rename telephone to Jhomar Miquiabas | Done | admin.Reymark B. Evangelista
CSR-1568-19 | CSR | Alvin O. Ramirez | 2019-12-03 08:26:00 | 2020-01-03 08:54:00 | 2020-01-03 08:56:00 | HO | Install Software | Need to install camera to meet the deadline cross section Area PC #6 | Done | admin.Reymark B. Evangelista
CSR-1520-19 | CSR | Vicente Z. Nieto | 2019-12-03 08:33:00 | 2019-12-04 21:00:00 | 2019-12-04 08:40:00 | HO | Borrow | WHE-TBU group would like to borrow 2 laptop to be used for Education of Costing preparation together with counterpart. | Done | admin.Aaron Jet N. Sarreal
CSR-1583-19 | CSR | Francis Benjamin C. Cagampan | 2019-12-03 09:56:00 | 2019-12-04 21:00:00 | 2020-02-04 07:17:00 | HO | Increase Capacity | i would like to request folder capacity transfer for the new Folder of JBRB. please move 50GB from jbrb/01_JBRB Design to jbrb/06_TBURB Common also, grant access for All RB members in 10.49.1.97/jbrb/06_TBURB Common access will be change in the future this is due to request of Customer | Done | admin.Joe Nico T. Geronimo
CSR-1591-19 | CSR | Sharmaine T. Ingles | 2019-12-03 12:43:00 | 2019-12-12 21:00:00 | 2019-12-20 07:55:00 | HO | Account Request | Windows Log In of TCE New Employee Jr. Testing Evaluator 1. Jelyn S. Trafanco (ID No. 2047) | Done | admin.Joe Nico T. Geronimo
CSR-1531-19 | CSR | Belinda C. Cabico | 2019-12-04 08:29:00 | 2019-12-05 21:00:00 | 0000-00-00 00:00:00 | HO | Modify Software | 1)Update NX 9.0 to NX 11. 2)Install Japanese Language in Excel to run macro. | Work in Progress | admin.Jasper Labenia
DRR-0162-19 | DRR | Edgar R. Medina | 2019-12-04 08:43:00 | 2019-12-04 08:43:00 | 2019-12-10 09:10:00 | HO | Cae | 8510B674-0B000, 8510B674-0C000 and 8510B674-0D000;/export/home/eucoodb/model/work/MITSU/H53;Original Directory;Yes;For mistake investigation | Done | admin.Christ John Dela Cruz
CSR-1521-19 | CSR | Francisco III T. Javines | 2019-12-04 11:29:00 | 2020-03-04 21:00:00 | 2020-02-11 12:39:00 | HO | Hardware Purchase | Replacement of broken printer for President, model Canon Pixma iX 6770 | Done | admin.Reymark B. Evangelista
CPR-0185-19 | CPR | Ann Margarett M. Barbacena | 2019-12-04 13:04:00 | 2019-12-04 12:30:00 | 2020-01-24 14:57:00 | HO | Mouse | The mouse malfunctioned. | Done | admin.Jasper Labenia
CSR-1582-19 | CSR | Franz Myka M. Dumlao | 2019-12-05 08:27:00 | 2019-12-16 21:00:00 | 2020-01-02 13:29:00 | HO | Access Request | Request for the access right of the below link for the following members only- \\10.49.1.97\wh\GMT\11. GL_SV Members that can access- Janice Darjuan Franz Myka Dumlao Miriam Esquivel Joelette Montemar Michelle Dela Cruz Rosalinda Tayer | Done | admin.Jasper Labenia
CSR-1584-19 | CSR | Franz Myka M. Dumlao | 2019-12-05 08:32:00 | 2019-12-06 21:00:00 | 2020-01-02 13:03:00 | HO | Borrow | Borrowing of Laptop for the list of Last two levels in every harnesses for archiving purposes. Location- Archive & GM group only Borrowed- 11/3 Return- 11/20 | Done | admin.Joe Nico T. Geronimo
CSR-1577-19 | CSR | Ann Gymverlyn O. Mendoza | 2019-12-05 08:37:00 | 2019-12-16 21:00:00 | 2020-02-04 11:17:00 | HO | Access Request | JBRB request of account and folder access right of Japanese Customer in TBURB common folder in PET server (See attached file for other details) | Done | admin.Reymark B. Evangelista
CSR-1545-19 | CSR | Cecil T. Morales | 2019-12-05 09:42:00 | 2019-12-06 09:42:00 | 2019-12-27 13:43:00 | HO | Transfer Software location | Please transfer KD VIEWER SOFTWARE FROM IP 10.49.7.100 TO IP 10.49.5.241 | Done | admin.Charmaine F. Layawon
CSR-1566-19 | CSR | Belinda C. Cabico | 2019-12-05 12:39:00 | 2019-12-06 21:00:00 | 2020-01-09 18:05:00 | HO | Install Software | Install NX to NEW PC to maximize PC Usage. 10.49.3.85 10.49.3.86 10.49.3.87 | Done | admin.Jasper Labenia
CSR-1560-19 | CSR | Johanna D. Santos | 2019-12-06 09:13:00 | 2020-01-03 07:37:00 | 2020-01-03 07:38:00 | HO | Access Request | Linkedin access for HR members Ray Miguel Cornejo, Johanna Santos, Helen Macasera, Analy Babatio (Recruitment purposes) | Done | admin.Reymark B. Evangelista
CSR-1532-19 | CSR | Francisco III T. Javines | 2019-12-06 11:49:00 | 2020-01-17 21:00:00 | 0000-00-00 00:00:00 | HO | Software Purchase | Please make PRIF for Windows 10 and Server upgrade activity by vendor. | Work in Progress | admin.Reymark B. Evangelista
CPR-0182-19 | CPR | Greg Daniel E. Mojica | 2019-12-06 15:06:00 | 2019-12-04 15:06:00 | 2019-12-11 16:36:00 | HO | Operating System | Solaris OS have problem on saving files, please reconfigure 10.49.0.22 | Done | admin.Patrick Robin Vinas
CSR-1535-19 | CSR | Cecil T. Morales | 2019-12-06 15:28:00 | 2019-12-17 06:52:00 | 2019-12-17 06:53:00 | HO | Backup to CD/DVD | Please transfer the following folders to CD/burn 2016-2018 MOCHIKIN DRAWING REFERENCE MOCHIKIN See attached file for reference directory. | Done | admin.Reymark B. Evangelista
CSR-1565-19 | CSR | Cecil T. Morales | 2019-12-09 08:37:00 | 2019-12-11 08:37:00 | 2020-02-11 18:11:00 | HO | Install Software | We would like to request software installation on the ff IP IP 10.49.3.88 and IP 10.49.3.75 EXTES access share from IP 10.49.5.241 LIGHT UP software It will be use for checking drawings. New deployed PC. | Done | admin.Greg Daniel E. Mojica
DRR-0166-19 | DRR | John Erick A. Nombrefia | 2019-12-09 09:04:00 | 2019-12-09 09:04:00 | 2020-01-24 13:56:00 | HO | Windows | P-D36H67050-15000.pdf;\\10.49.1.97\wh\MAZDA-FUSO\NIM-MAZDA\Scanned Drawings (NIM-Mazda)\CAE\J03K M\DD28T67050\17000\SENDING\D36H67050-15000;Original Directory;No;Please restore all drawings that has that filename prior to the last saved and please indicate user and IP who make or saved the file. This is inline with our mistake that needs asap investigation. This file was overwrite and the group sent a wrong file. Please create a restored folder and saved there all the drawings that has that filename from the date it was created. We want to see and check when that drawing was created and edited and who made and worked on that drawing. Thank you. | Done | admin.Jasper Labenia
CSR-1564-19 | CSR | Ronalyn G. Imana | 2019-12-09 09:41:00 | 2019-12-18 21:00:00 | 2020-01-03 09:47:00 | HO | Access Request | 1. Folder access of the ECI Members in the following folders Sugiura, Maki Y046950 ECI_CR23T Yamamoto, Kazuhiro Y049402 ECI_CR23T \\10.49.1.97\31 eciâ†’pet\ECIâ†’PET(HARDWARE)\COMMON \\10.49.1.97\31 eciâ†’pet\ECIâ†’PET(HARDWARE)\CR21T \\10.49.1.97\31 eciâ†’pet\ECIâ†’PET(HARDWARE)\CR22T \\10.49.1.97\31 eciâ†’pet\ECIâ†’PET(HARDWARE)\CR23T \\10.49.1.97\31 eciâ†’pet\ECIâ†’PET(HARDWARE)\CR24T \\10.49.1.97\32 petâ†’eci\PETâ†’ECI(HARDWARE)\COMMON \\10.49.1.97\32 petâ†’eci\PETâ†’ECI(HARDWARE)\CR21T \\10.49.1.97\32 petâ†’eci\PETâ†’ECI(HARDWARE)\CR22T \\10.49.1.97\32 petâ†’eci\PETâ†’ECI(HARDWARE)\CR23T \\10.49.1.97\32 petâ†’eci\PETâ†’ECI(HARDWARE)\CR24T 2. Delete folder access of Mr. Tomohiro Iida- Y039758 | Done | admin.Joe Nico T. Geronimo
CSR-1538-19 | CSR | Jerick D. Pinlac | 2019-12-09 10:32:00 | 2019-12-10 08:00:00 | 2019-12-11 09:34:00 | HO | Install Software | Sony Vegas for LED presentation | Done | admin.Aaron Jet N. Sarreal
CSR-1589-19 | CSR | Roner B. Paguirigan | 2019-12-09 12:45:00 | 2020-01-20 21:00:00 | 2020-01-18 08:29:00 | HO | Renewal License | Renewal of E3 software. | Done | admin.Joe Nico T. Geronimo
DRR-0164-19 | DRR | Francis Benjamin C. Cagampan | 2019-12-09 15:38:00 | 2019-12-09 15:38:00 | 2020-01-08 09:49:00 | HO | Cae | 7470-5930TY01#00#JB_COMP_ASSY.CATDrawing 7470-5930TY02#00#JB_COMP_ASSY.CATDrawing 7470-5930TY03#00#JB_COMP_ASSY.CATDrawing;\\10.49.1.97\jbrb\01_JBRB Design\00 JOB ORDERS\ECI-24T\TOYOTA\12_DEC\EKIK-1912007_435B_Kawazoe San\02_Output;Original Directory;No;Data Create over written the old version | Done | admin.Reymark B. Evangelista
CPR-0184-19 | CPR | Bryan Mar R. Alvarez | 2019-12-09 16:04:00 | 2019-12-09 16:04:00 | 2020-01-03 09:44:00 | HO | Mouse | scroll click not working properly | Done | admin.Joe Nico T. Geronimo
CSR-1563-19 | CSR | Melissa R. Talabong | 2019-12-10 09:18:00 | 2020-01-02 09:19:00 | 2020-01-06 14:13:00 | HO | Borrow | Borrow desktop monitor to be used by Finance trainee. | Done | admin.Jasper Labenia
CSR-1559-19 | CSR | Redemptor C. Batiduan | 2019-12-10 12:31:00 | 2020-03-10 21:00:00 | 2020-01-30 12:06:00 | HO | Hardware Purchase | Need 1 DVI-to-VGA adaptor for PC-to-monitor connection. PC has DVI port while monitor is VGA port. VGA-to-DVI adaptor will also do if DVI-to-VGA adaptor is not available in the market. | Done | admin.Joe Nico T. Geronimo
CSR-1562-19 | CSR | Jeziel Beatrix V. Nalupa | 2019-12-10 13:07:00 | 2019-12-11 21:00:00 | 2019-12-20 12:33:00 | HO | Modify Software | From Microsoft Office Professional (10.49.3.253) to Microsoft Office Standard (10.49.2.28) | Done | admin.Reymark B. Evangelista
CSR-1542-19 | CSR | John Kendryl O. Fernandez | 2019-12-11 09:33:00 | 2019-12-12 21:00:00 | 2020-01-31 16:32:00 | HO | Install Software | movie maker for parol presentation needed today 12/11/2019, urgent lang po thank you | Done | admin.Willem R. Leonardo
CSR-1540-19 | CSR | Takashi Watanabe | 2019-12-11 10:45:00 | 2019-12-20 21:00:00 | 2019-12-17 06:38:00 | HO | Account Request | Please add 1 new Windows account for YC ICT. This is for GPMS activity. He want to access our OMS server and File server. | Done | admin.Reymark B. Evangelista
CSR-1546-19 | CSR | Emiliano P. Mendoza | 2019-12-11 11:59:00 | 2019-12-20 21:00:00 | 2019-12-13 12:13:00 | HO | Access Request | \\10.49.1.97\Budget control | Done | admin.Reymark B. Evangelista
CSR-1558-19 | CSR | Rodelio Jr. A. Perin | 2019-12-11 12:31:00 | 2020-01-31 06:59:00 | 2020-01-08 09:15:00 | HO | Modify Software | Update latest version of .NET framework all connector pc | Done | admin.Joe Nico T. Geronimo
CSR-1552-19 | CSR | Ma. Reina Monserrat A. Abalos | 2019-12-11 13:42:00 | 2019-12-12 21:00:00 | 2020-01-06 18:02:00 | HO | PC Configuration | transfer all email content from 10.49.5.107 â‡’ 10.49.3.34 user PET0869 transfer all email content from 10.49.2.88 â‡’ 10.49.5.107 user PET1534 | Closed | admin.Jasper Labenia
CSR-1557-19 | CSR | Takashi Watanabe | 2019-12-11 11:44:00 | 2019-12-20 21:00:00 | 0000-00-00 00:00:00 | HO | Delete Software | I returned W-CAD dongle to YC on Dec. 11, 2019 because JBRB and WHE never use it. Please uninstall W-CAD from all Workstation that is installed. After that, please update software inventory list. Please input IP address in work log. | Assigned | admin.Jasper Labenia
CSR-1544-19 | CSR | Rhiessa Sarah Z. Tuyor | 2019-12-11 16:10:00 | 2019-12-12 21:00:00 | 2020-02-11 12:24:00 | HO | Add Internet Connection | Access to Internet browsing, because I need to search about chemical products for Oil resistance Testing | Done | admin.Willem R. Leonardo
CSR-1561-19 | CSR | Carlo Gringo O. Saballa | 2019-12-12 08:40:00 | 2019-12-13 21:00:00 | 0000-00-00 00:00:00 | HO | Backup to CD/DVD | BACK UP 2018/2019 SCANNED DETAIL DRAWING FORM/A3 CHECKING | Assigned | admin.Joe Nico T. Geronimo
CSR-0036-20 | CSR | Princess Ellaine C. Malanao | 2019-12-12 11:27:00 | 2019-12-13 21:00:00 | 2020-01-14 09:37:00 | HO | Outsources Request | Please order torner for plotter 6055 of WH-EDSD | Done | admin.Reymark B. Evangelista
CSR-1553-19 | CSR | Rafael O. Pangilinan | 2019-12-12 11:14:00 | 2019-12-13 21:00:00 | 2019-12-19 08:29:00 | HO | Access Request | Request for Omura Takako (ID No.Z012531) to have a Removal access Location - \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Material Request for Miki Warashina (ID No.Z020228) to have a Removal of access Location - \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Parts Request for Tomoya Hashimoto (ID No.Y057395) to have a Read/Write access Location - \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Parts | Done | admin.Joe Nico T. Geronimo
CSR-1586-19 | CSR | Jason L Odtuhan | 2019-12-12 16:44:00 | 2020-01-14 11:31:00 | 2020-01-14 11:31:00 | HO | Transfer Software location | WE WANT TO TRANSFER THE MICROSOFT LYNC FROM 10.49.1.161 TO 10.49.2.194 | Done | admin.Reymark B. Evangelista
CSR-1551-19 | CSR | Jennygene P. Toding | 2019-12-13 13:30:00 | 2020-03-13 21:00:00 | 2020-01-14 11:28:00 | HO | Hardware Purchase | This request is for purchase of B/W Multi Function Plotter(2019/7-12#35) for WHD. | Done | admin.Reymark B. Evangelista
CSR-1556-19 | CSR | Aumer A. Velasquez | 2019-12-13 13:19:00 | 2019-12-20 06:55:00 | 2019-12-19 14:28:00 | HO | Backup to CD/DVD | Good day, May we request for file transfer from network to CD. Please location below \\10.49.1.97\wh\COMMON\PTM\FOR CD TRANSFER CD 1 NIIMI (2015 & 2018) CD2 NIIMI (2019 & FROM NIIMI) CD3 SUZUKI (ALL Contents) Thank you very much. | Done | admin.Reymark B. Evangelista
CPR-0186-19 | CPR | Emiliano P. Mendoza | 2019-12-13 15:04:00 | 2019-12-11 15:04:00 | 2020-01-03 07:48:00 | HO | Printer/Plotter | 10.49.1.46 OCE colorwave repair and maintenance quotation | Done | admin.Reymark B. Evangelista