## Worksheet
HO January 2020
New Request | Assigned | Work in Progress | Done | Closed | Total
0 | 4 | 10 | 48 | 2 | 64
| Completed | On-going | Delay | Total Request | Completion % | On Time %
CSR | 42 | 8 | 4 | 54 | 77.78 | 90.48
CPR | 3 | 1 | 0 | 4 | N/A | N/A
DRR | 5 | 1 | 0 | 6 | N/A | N/A
Member | Assigned | Work in Progress | Done | Closed
admin.admin.John Christian Lovitos | 0 | 0 | 0 | 1
admin.admin.Reymark B. Evangelista | 0 | 0 | 0 | 1
admin.Christ John Dela Cruz | 1 | 0 | 0 | 0
admin.Jasper Labenia | 3 | 4 | 8 | 0
admin.Joe Nico T. Geronimo | 0 | 1 | 16 | 37
admin.John Christian Lovitos | 0 | 0 | 0 | 1
admin.Kiel Antaran | 0 | 2 | 1 | 0
admin.Reymark B. Evangelista | 0 | 3 | 20 | 29
admin.Willem R. Leonardo | 0 | 0 | 3 | 3
Reference # | Process | Requestor | Date Request | Date Needed | Date Done | Site | Category | Details | Status | Assigned to
DRR-0168-19 | DRR | Anna Liza E. Ilusorio | 2019-12-16 17:05:00 | 2019-12-16 17:05:00 | 2019-12-17 16:57:00 | HO | Windows | WHD3-MMF-F-79-11-71 (Short long cutting length);\\10.49.1.97\wh\COMMON\QUALITY\COUNTERMEASURE\CPAP-EXTERNAL- 79TH TERM\CPAP FINAL (with Manager's Approval);Original Directory;Yes;Accidentally delete files | Done | admin.Willem R. Leonardo
QA-1862-19 | QA | Rosano A. Buerano | 2019-12-19 08:20:00 | 2019-12-19 08:20:00 | 2019-12-19 08:27:00 | HO |  | configuration of expedition | Closed | admin.Joe Nico T. Geronimo
QA-1863-19 | QA | Aris D. Castro | 2019-12-19 09:00:00 | 2019-12-19 09:00:00 | 2019-12-19 09:12:00 | HO |  | problem in lync | Closed | admin.Joe Nico T. Geronimo
QA-1864-19 | QA | Jeffrey I. Jurada | 2019-12-19 09:15:00 | 2019-12-19 09:15:00 | 2019-12-19 09:30:00 | HO |  | quota in file server | Closed | admin.Joe Nico T. Geronimo
QA-1865-19 | QA | Milamari Q. Isidoro | 2019-12-19 09:00:00 | 2019-12-19 09:00:00 | 2019-12-19 09:05:00 | HO |  | Account disable in Active directory | Closed | admin.admin.Reymark B. Evangelista
QA-1866-19 | QA | Vicente Z. Nieto | 2019-12-19 09:30:00 | 2019-12-19 09:30:00 | 2019-12-19 09:34:00 | HO |  | reservation of video conference room | Closed | admin.Joe Nico T. Geronimo
QA-1867-19 | QA | Eron Jay T. Caballero | 2019-12-19 14:00:00 | 2019-12-19 14:00:00 | 2019-12-19 14:07:00 | HO |  | cannot close snipping tool | Closed | admin.Joe Nico T. Geronimo
CSR-0058-20 | CSR | Francis Benjamin C. Cagampan | 2019-12-16 09:31:00 | 2020-01-24 08:05:00 | 2020-01-24 08:07:00 | HO | Printer Configuration | please add \\10.49.1.97\jbrb\04_JBRB Common\(00)_Scans in the location for scanned data from Docuwide_6057 | Done | admin.Reymark B. Evangelista
CSR-0006-20 | CSR | Cris-Myla A. Orandain | 2019-12-17 09:18:00 | 2020-01-06 09:17:00 | 2020-01-03 09:22:00 | HO | Backup CAE file/s | We would like to request CAE back-up file for TYA model at /export/home/eucoodb/model/work/HONDA/TYA Thank you. | Done | admin.Kiel Antaran
CSR-0040-20 | CSR | Emmanuel Jr. C. Jimenez | 2019-12-17 09:28:00 | 2019-12-26 21:00:00 | 2020-01-15 07:24:00 | HO | Access Request | Access Right deletion of resigned CON member Vanessa Nacino(2045) | Done | admin.Reymark B. Evangelista
CPR-0001-20 | CPR | Cyrus John V. Ibea | 2019-12-17 14:30:00 | 2019-12-17 14:30:00 | 2020-01-20 14:48:00 | HO | PC Power Supply | Broken Power Button(CPU) | Done | admin.Jasper Labenia
CPR-0002-20 | CPR | Cyrus John V. Ibea | 2019-12-17 14:58:00 | 2019-12-17 14:58:00 | 2020-01-20 14:47:00 | HO | PC Power Supply | Noisy CPU Fan | Done | admin.Jasper Labenia
CSR-1590-19 | CSR | Ruby A. Maghilum | 2019-12-18 08:09:00 | 2019-12-27 21:00:00 | 2019-12-20 07:39:00 | HO | Access Request | Request to Access file location \\PETSVR1097\Budget Control\FY79_BUDGET\ENGINEERING\ for EA Monitoring / Update purposes | Done | admin.Joe Nico T. Geronimo
CSR-1592-19 | CSR | Ruby A. Maghilum | 2019-12-18 08:11:00 | 2019-12-27 21:00:00 | 2020-01-03 10:02:00 | HO | Access Request | Delete Access of Ms. Milamari Isidoro with ID number of pet1698 to \\PETSVR1097\Budget Control\FY79_BUDGET\ | Done | admin.Reymark B. Evangelista
DRR-0170-19 | DRR | Marie Rose A. Farala | 2019-12-18 08:22:00 | 2019-12-18 08:23:00 | 2020-01-02 06:16:00 | HO | Windows | ã€MBDç”¨ã€‘CBalCtrlApãƒ†ã‚¹ãƒˆã‚±ãƒ¼ã‚¹_Reviewed_01_Kaye.xlsx ã€MBDç”¨ã€‘CBalCtrlApãƒ†ã‚¹ãƒˆã‚±ãƒ¼ã‚¹_Reviewed_02_Carl.xlsx ã€MBDç”¨ã€‘CBalCtrlApãƒ†ã‚¹ãƒˆã‚±ãƒ¼ã‚¹_Reviewed_03_Kaye.xlsx;\\10.49.1.97\ei\25 MBD\01 JOBS\79th Term\2. EIMBD79002_BMU\04 Work Products\2. Cell Balance Control\00 Review Logs;Original Directory;No;It was accidentally deleted. | Done | admin.Reymark B. Evangelista
CSR-1595-19 | CSR | Takashi Watanabe | 2019-12-18 09:11:00 | 2020-01-07 09:57:00 | 2020-01-06 09:59:00 | HO | Access Request | This is for GPMS activity. Z023949 Hiroaki Takano is under MIS. (same as Mr. Takeshi Sugiyama) Please give him the folder access path. | Done | admin.Joe Nico T. Geronimo
CSR-0035-20 | CSR | Rommel E. Aguilon | 2019-12-18 10:47:00 | 2019-12-19 21:00:00 | 2020-01-14 09:42:00 | HO | Outsources Request | Please order toner for 6055 in EDS area. Please perform the necessary actions required by the supplier in order for them to deliver the needed consumables | Done | admin.Reymark B. Evangelista
DRR-0001-20 | DRR | Jovielet B. Caintoy | 2019-12-18 13:08:00 | 2019-12-18 13:08:00 | 2020-01-06 14:17:00 | HO | Windows | YTMI Consumed Manhrs ;\\10.49.1.97\wh\MS_PTM\MS FOLDER 2011\SALESHOUR Related\YTMI Consumed Hours\2019;Original Directory;Yes;Deleted | Done | admin.Jasper Labenia
CSR-0018-20 | CSR | Gilbert G. Velasquez | 2019-12-19 08:23:00 | 2019-12-20 21:00:00 | 2020-01-30 12:06:00 | HO | Add Internet Connection | Internet connection for Meter benchmarking until January 15, 2020 (1588) | Done | admin.Joe Nico T. Geronimo
CSR-0017-20 | CSR | Gilbert G. Velasquez | 2019-12-19 08:28:00 | 2019-12-20 21:00:00 | 2020-01-08 07:01:00 | HO | Download | (Downloading of Volkswagen Toureg 2019 meter cluster video in youtube) (For Meter Benchmarking reference) | Done | admin.Reymark B. Evangelista
CSR-0016-20 | CSR | Ma. Joelette L. Montemar | 2019-12-19 11:22:00 | 2020-01-15 07:25:00 | 2020-01-15 07:26:00 | HO | Add Internet Connection | to access YNA share point site, download files/drawings,etc. | Done | admin.Reymark B. Evangelista
CPR-0187-19 | CPR | Takashi Watanabe | 2019-12-19 16:42:00 | 2019-12-19 16:42:00 | 0000-00-00 00:00:00 | HO | Laptop | Lync meeting was down in Guest room due to LAN connection to laptop. (LAN port connection is not good.) Therefore please replace laptop. I think we can use Windows 10 testing laptop. (We have 5 laptops for Windows 10 testing.) Then please update Asset tagging list for new laptop and disposal old laptop. | Work in Progress | admin.Jasper Labenia
CSR-0015-20 | CSR | Almar Abner Q. Cenizal | 2019-12-20 07:18:00 | 2020-01-15 07:18:00 | 2020-01-18 08:27:00 | HO | Renewal License | Renewal of Icepak License | Done | admin.Joe Nico T. Geronimo
QA-1869-19 | QA | Marissa M. Santiagudo | 2019-12-20 07:15:00 | 2019-12-20 07:15:00 | 2019-12-20 07:26:00 | HO |  | PC wont boot | Closed | admin.Joe Nico T. Geronimo
QA-1870-19 | QA | Ann Gymverlyn O. Mendoza | 2019-12-20 07:20:00 | 2019-12-20 07:20:00 | 2019-12-20 07:29:00 | HO |  | black screen | Closed | admin.Joe Nico T. Geronimo
CSR-0001-20 | CSR | Lorenie M. Maullon | 2019-12-20 13:12:00 | 2020-01-03 13:12:00 | 2020-01-06 13:52:00 | HO | Transfer Software location | REQUEST TRANSFER => (1.)DRAWING TRUE VIEW ( 2.)BRAVA DESKTOP From IP 10.49.5.6 (PET2013-KD) TO IP 10.49.5.10 (PET1654 -JENNIE). | Done | admin.Jasper Labenia
QA-0000-20 | QA | Willem R. Leonardo | 2020-01-02 12:37:00 | 2020-01-03 21:00:00 | 2020-01-02 08:15:00 | HO | Borrow | borrowing | Closed | admin.Joe Nico T. Geronimo
QA-0002-20 | QA | Kristine Dianne Y Tecson | 2020-01-02 08:15:00 | 2020-01-02 08:15:00 | 2020-01-02 08:25:00 | HO |  | unable print | Closed | admin.Joe Nico T. Geronimo
QA-0003-20 | QA | Jennie S. Rodriguez | 2020-01-02 08:20:00 | 2020-01-02 08:20:00 | 2020-01-02 08:26:00 | HO |  | no internet | Closed | admin.Joe Nico T. Geronimo
QA-0004-20 | QA | Princess Ellaine C. Malanao | 2020-01-02 09:00:00 | 2020-01-02 09:00:00 | 2020-01-02 09:07:00 | HO |  | no network access | Closed | admin.Joe Nico T. Geronimo
QA-0005-20 | QA | Princess Ellaine C. Malanao | 2020-01-02 09:08:00 | 2020-01-02 09:08:00 | 2020-01-02 09:13:00 | HO |  | outlook problem | Closed | admin.Joe Nico T. Geronimo
QA-0006-20 | QA | Jennifer Joy D. Naputo | 2020-01-02 09:10:00 | 2020-01-02 09:10:00 | 2020-01-02 09:20:00 | HO |  | kd viewer default config | Closed | admin.Joe Nico T. Geronimo
CSR-0010-20 | CSR | Anna Liza E. Ilusorio | 2020-01-02 15:13:00 | 2020-01-13 15:13:00 | 2020-01-08 09:52:00 | HO | Account Request | Request new e-mail account for Dominic Meomeo for costumer communication | Done | admin.Reymark B. Evangelista
QA-0007-20 | QA | Vicente Z. Nieto | 2020-01-02 09:30:00 | 2020-01-02 09:30:00 | 2020-01-02 09:35:00 | HO |  | no internet access | Closed | admin.Joe Nico T. Geronimo
QA-0008-20 | QA | Agnes P. Javillonar | 2020-01-02 09:40:00 | 2020-01-02 09:40:00 | 2020-01-02 09:45:00 | HO |  | request for internet access | Closed | admin.Joe Nico T. Geronimo
QA-0009-20 | QA | Sarah Mae R. Bagis | 2020-01-02 10:00:00 | 2020-01-02 10:00:00 | 2020-01-02 10:18:00 | HO |  | unable to print. cannot access website | Closed | admin.Joe Nico T. Geronimo
CSR-0014-20 | CSR | Catherine U. Bulalacao | 2020-01-02 15:33:00 | 2020-01-03 21:00:00 | 2020-01-14 09:29:00 | HO | Transfer Software location | 1. transfer all email archives from 10.49.131.61(Branch Office) to 10.49.2.247( Head Office) 2. transfer all email archives from 10.49.3.142(Head Office) to 10.49.2.247( Head Office) | Done | admin.Joe Nico T. Geronimo
QA-0013-20 | QA | Mart Aviz Penamante | 2020-01-03 07:00:00 | 2020-01-03 07:00:00 | 2020-01-03 07:04:00 | HO |  | Register ID in printer | Closed | admin.Joe Nico T. Geronimo
QA-0014-20 | QA | Audrey D. Dizon | 2020-01-03 07:15:00 | 2020-01-03 07:15:00 | 2020-01-03 07:30:00 | HO |  | user profile cannot log-on | Closed | admin.Reymark B. Evangelista
CSR-0008-20 | CSR | Sharmaine T. Ingles | 2020-01-03 10:46:00 | 2020-01-14 21:00:00 | 2020-01-07 14:05:00 | HO | Account Request | Access Deletion of Resigned JTE Nanette Paunil ID No. pet1373 | Done | admin.Reymark B. Evangelista
CSR-0007-20 | CSR | Sharmaine T. Ingles | 2020-01-03 10:56:00 | 2020-01-14 21:00:00 | 2020-01-09 17:17:00 | HO | Account Request | Request for DMS Deletion of TCE Resigned Members 1) pet1675 Jeremeeh S. Ramuram 2) pet1868 Renalyn B. Alminaza | Closed | admin.Willem R. Leonardo
CSR-0055-20 | CSR | Gretchen C. Magsino | 2020-01-03 17:10:00 | 2020-01-14 21:00:00 | 2020-01-23 12:37:00 | HO | Access Request | Access rights for GL and SV only. | Done | admin.Joe Nico T. Geronimo
DRR-0004-20 | DRR | Annabelle D. Capada | 2020-01-03 19:23:00 | 2020-01-03 19:23:00 | 0000-00-00 00:00:00 | HO | Cae | (CADRA FILE) qd79f-056 ;O:\cadra\DRAW\CAE\PET\FUJIJU\NOTICE_OF_REVISION\MS2\qd79f-056;Original Directory;No;Cannot be open, file error after save as of 630pm on Jan 03,2020. First error (bad file) then File incomplete | Assigned | admin.Christ John Dela Cruz
QA-0019-20 | QA | John Mark A. Gregorio | 2020-01-06 08:00:00 | 2020-01-06 08:00:00 | 2020-01-06 08:15:00 | HO |  | register id in printer | Closed | admin.Joe Nico T. Geronimo
QA-0020-20 | QA | Marlon S. Estanque | 2020-01-06 08:15:00 | 2020-01-06 08:15:00 | 2020-01-06 08:25:00 | HO |  | register ID in printer | Closed | admin.Joe Nico T. Geronimo
QA-0021-20 | QA | John Vincent J. Baclagon | 2020-01-06 08:30:00 | 2020-01-06 08:30:00 | 2020-01-06 08:40:00 | HO |  | register ID in printer | Closed | admin.Joe Nico T. Geronimo
QA-0022-20 | QA | Domnino Jr. J. Liston | 2020-01-06 08:05:00 | 2020-01-06 08:05:00 | 2020-01-06 08:15:00 | HO |  | Plocom cannot open due to error encounter | Closed | admin.Reymark B. Evangelista
QA-0023-20 | QA | John Carlo E. Dangan | 2020-01-06 08:24:00 | 2020-01-06 08:24:00 | 2020-01-06 08:30:00 | HO |  | register ID in printer | Closed | admin.Joe Nico T. Geronimo
QA-0024-20 | QA | Mariel R. Santos | 2020-01-06 08:26:00 | 2020-01-06 08:26:00 | 2020-01-06 08:35:00 | HO |  | set up outlook | Closed | admin.Joe Nico T. Geronimo
QA-0025-20 | QA | Jomar T. Legaspi | 2020-01-06 08:28:00 | 2020-01-06 08:28:00 | 2020-01-06 08:30:00 | HO |  | no network access | Closed | admin.Joe Nico T. Geronimo
QA-0026-20 | QA | Francis Ryan L Bautista | 2020-01-06 08:41:00 | 2020-01-06 08:41:00 | 2020-01-06 08:46:00 | HO |  | register new regular ID to printer colored/black&white | Closed | admin.Reymark B. Evangelista
QA-0027-20 | QA | Emerson T. Chua | 2020-01-06 08:42:00 | 2020-01-06 08:42:00 | 2020-01-06 08:49:00 | HO |  | register regular ID to printer colored/black&white | Closed | admin.Reymark B. Evangelista
QA-0028-20 | QA | Joffa Dericka Raguindin | 2020-01-06 08:44:00 | 2020-01-06 08:44:00 | 2020-01-06 08:51:00 | HO |  | register regular id to printer Colored/black&white | Closed | admin.Reymark B. Evangelista
QA-0029-20 | QA | Catherine U. Bulalacao | 2020-01-06 08:53:00 | 2020-01-06 08:53:00 | 2020-01-06 08:59:00 | HO |  | unable to print(wrong paper size)` | Closed | admin.Joe Nico T. Geronimo
QA-0030-20 | QA | Acer Chael R. Dupaya | 2020-01-06 08:52:00 | 2020-01-06 08:52:00 | 2020-01-06 08:57:00 | HO |  | CMMS cannot open | Closed | admin.Reymark B. Evangelista
QA-0031-20 | QA | Neslie Borgonia | 2020-01-06 08:45:00 | 2020-01-06 08:45:00 | 2020-01-06 08:59:00 | HO |  | Register regular ID to printer colored/black&white | Closed | admin.Reymark B. Evangelista
CSR-0013-20 | CSR | April D. Dayapan | 2020-01-06 09:31:00 | 2020-04-06 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | HP Prodesk 400 G5 SFF PC Php 62,300 For CADRA replacement April 2020 Engineering Budget (EI_MT) | Work in Progress | admin.Kiel Antaran
CSR-0009-20 | CSR | Judelyn E. Rosales | 2020-01-06 10:18:00 | 2020-01-15 21:00:00 | 2020-01-06 12:08:00 | HO | Account Request | Deletion of User Account of Isidoro, Milamari Q. (pet1698). | Done | admin.Reymark B. Evangelista
CSR-0012-20 | CSR | Mary Katherine Kaye F. Decena | 2020-01-06 10:29:00 | 2020-01-09 08:00:00 | 2020-01-08 08:19:00 | HO | Install Software | Install MATLAB 2019b in 10.49.1.152 - will be used for technical exchange preparation | Done | admin.Reymark B. Evangelista
QA-0032-20 | QA | Princess Ellaine C. Malanao | 2020-01-06 12:00:00 | 2020-01-06 12:00:00 | 2020-01-06 12:01:00 | HO |  | replace toner for ADM printer | Closed | admin.Reymark B. Evangelista
CSR-0022-20 | CSR | Katherine Q. Ronquillo | 2020-01-06 14:47:00 | 2020-01-15 21:00:00 | 2020-01-14 11:24:00 | HO | Account Request | We need email address of Juline Pieza for receiveing and sending of Grommet Job Request from different requestors. Juline was assigned last 2019 as official in-charge in Grommet Calculation jobs that was transferred from WHD to PRT Dept. | Done | admin.Reymark B. Evangelista
CSR-0020-20 | CSR | Anthony N. Boado | 2020-01-06 16:47:00 | 2020-01-15 21:00:00 | 2020-01-08 12:21:00 | HO | Access Request | To reset my password on OWA account | Done | admin.Jasper Labenia
QA-0041-20 | QA | Aris D. Castro | 2020-01-07 08:20:00 | 2020-01-07 08:20:00 | 2020-01-07 08:23:00 | HO |  | Lync cannot open and log-in | Closed | admin.Reymark B. Evangelista
QA-0042-20 | QA | Patrick B. Martinez | 2020-01-07 10:20:00 | 2020-01-07 10:20:00 | 2020-01-07 10:27:00 | HO |  | allow remote desktop to 10.49.1.90 user remote from BO to HO | Closed | admin.Reymark B. Evangelista
QA-0043-20 | QA | Abigail E. Salas | 2020-01-07 13:25:00 | 2020-01-07 13:25:00 | 2020-01-07 13:35:00 | HO |  | outlook cannot open | Closed | admin.Willem R. Leonardo
CSR-0019-20 | CSR | Maria Josefa G. Samson | 2020-01-07 15:10:00 | 2020-04-07 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | Request for 2 Privacy Filters (24 inch size) 1 for 10.49.2.128 (Josefa Samson) 1 for 10.49.2.96 (Troy Gatchalian) | Work in Progress | admin.Reymark B. Evangelista
CSR-0029-20 | CSR | Rommel E. Aguilon | 2020-01-07 16:56:00 | 2020-01-08 21:00:00 | 2020-01-15 21:10:00 | HO | Install Software | Please install scanner (Scan Snap) in the computer of Edwin Fulgar - IP Address - 10.49.1.174 Noli Baldeviso - IP Adress - 10.49.2.36 | Done | admin.Jasper Labenia
QA-0048-20 | QA | Reyna Marie I. Sarra | 2020-01-07 07:20:00 | 2020-01-07 07:20:00 | 2020-01-07 07:24:00 | HO |  | map network drive | Closed | admin.Joe Nico T. Geronimo
QA-0049-20 | QA | Almar Abner Q. Cenizal | 2020-01-08 07:26:00 | 2020-01-08 07:26:00 | 2020-01-08 07:45:00 | HO |  | video conference reservation | Closed | admin.Joe Nico T. Geronimo
QA-0050-20 | QA | Francis Benjamin C. Cagampan | 2020-01-08 07:28:00 | 2020-01-08 07:28:00 | 2020-01-08 07:35:00 | HO |  | reservation video conference | Closed | admin.Joe Nico T. Geronimo
QA-0051-20 | QA | Dominic S. Baylon | 2020-01-08 07:29:00 | 2020-01-08 07:29:00 | 2020-01-08 07:36:00 | HO |  | jabra not working | Closed | admin.Joe Nico T. Geronimo
QA-0052-20 | QA | Troy C. Gatchalian | 2020-01-08 08:00:00 | 2020-01-08 08:00:00 | 2020-01-08 08:05:00 | HO |  | Computer black screen | Closed | admin.Reymark B. Evangelista
CSR-0054-20 | CSR | Johanna Marie C. Dandan | 2020-01-08 08:44:00 | 2020-02-19 21:00:00 | 2020-02-03 10:30:00 | HO | Software Purchase | Request for Purchase (PRT) 1. Microsoft Lync for Jathniel Lopez (Budget November 2019 - P1,500) To be use for coordinating 3D Checking & 3D CAD jobs explanation to PRT BO. and Job coordination with customer. | Done | admin.Joe Nico T. Geronimo
QA-0053-20 | QA | Mary Katherine Kaye F. Decena | 2020-01-08 08:45:00 | 2020-01-08 08:45:00 | 2020-01-08 09:30:00 | HO |  | install and configure mingw-w64 compiler for Matlab application | Closed | admin.Reymark B. Evangelista
CSR-0023-20 | CSR | Anabelle B. Albiola | 2020-01-08 09:30:00 | 2020-01-10 09:30:00 | 2020-01-30 12:06:00 | HO | Backup to CD/DVD | Please burn on the directory below \\10.49.1.97\wh\HONDA\Mailbox\FOR RENAMING-BELLE\2017 | Done | admin.Joe Nico T. Geronimo
QA-0054-20 | QA | Aumer A. Velasquez | 2020-01-08 09:32:00 | 2020-01-08 09:32:00 | 2020-01-08 09:40:00 | HO |  | cannot open file | Closed | admin.Joe Nico T. Geronimo
CSR-0053-20 | CSR | Maria Josefa G. Samson | 2020-01-08 12:47:00 | 2020-01-23 12:48:00 | 0000-00-00 00:00:00 | HO | Borrow | Borrow 1 Laptop to be use for BT (1/27 - 1/30) | Work in Progress | admin.Jasper Labenia
CSR-0043-20 | CSR | Roner B. Paguirigan | 2020-01-08 12:59:00 | 2020-04-08 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | Replacement of 2 old (more than 7yrs) NX work stations. IP. 10.49.2.180 & 10.49.2.210 | Assigned | admin.Jasper Labenia
CSR-0034-20 | CSR | Gelli A. Merene | 2020-01-08 14:01:00 | 2020-01-13 14:01:00 | 2020-01-14 11:22:00 | HO | Backup to CD/DVD | Scanned Checksheets (Drawing Data) location-\\10.49.1.97\emd\EMD1102\Resource Center\YC-Parts\DRAWING DATA\YC Job Requests (Drawing Data Scanned Check Sheets) From PDF=102819-110119 to 122319-122619 only. | Done | admin.Reymark B. Evangelista
CSR-0052-20 | CSR | Ronalyn G. Imana | 2020-01-08 14:15:00 | 2020-01-17 21:00:00 | 2020-01-29 07:37:00 | HO | Account Request | Request of New email account of the following members 1659-Ivy Salcedo 1964-Neil Joshua Santiago 1893-Gabriel Dominic Canilanza 1872-Louie Sablay 1914-Franklin Mark Lopez 1963-Jessa Juarez 1984-Noime Balleser | Done | admin.Joe Nico T. Geronimo
CSR-0044-20 | CSR | Mark Donne O. Opinio | 2020-01-08 14:20:00 | 2020-01-17 21:00:00 | 2020-01-16 08:14:00 | HO | Access Request | Need access rights in Branch office network for my ongoing automation project(CLICKer). | Done | admin.Joe Nico T. Geronimo
CSR-0031-20 | CSR | Kimberson M. Reyes | 2020-01-08 16:55:00 | 2020-01-09 21:00:00 | 2020-01-27 08:20:00 | HO | Borrow | Borrow laptop to be used for business trip from 1/10/2020 - 1/27/2020 | Done | admin.Joe Nico T. Geronimo
QA-0059-20 | QA | April D. Dayapan | 2020-01-09 08:30:00 | 2020-01-09 08:30:00 | 2020-01-09 08:51:00 | HO |  | cannot access IPMS | Closed | admin.Joe Nico T. Geronimo
QA-0060-20 | QA | Shiela Mae Anne R. R. Decena | 2020-01-09 09:00:00 | 2020-01-09 09:00:00 | 2020-01-09 09:04:00 | HO |  | reset password | Closed | admin.Joe Nico T. Geronimo
QA-0061-20 | QA | Shiela T. Baytic | 2020-01-09 09:00:00 | 2020-01-09 09:00:00 | 2020-01-09 09:06:00 | HO |  | unlock account | Closed | admin.Joe Nico T. Geronimo
CSR-0051-20 | CSR | Emiliano P. Mendoza | 2020-01-09 09:14:00 | 2020-01-10 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | OCE COLOWAVE 300 ASEANA 1 WITH SERIAL 330401058 FAN ASSEMBLY QUOTATION FOR PO | Assigned | admin.Jasper Labenia
CSR-0045-20 | CSR | Angelo I. Tajonera | 2020-01-09 09:25:00 | 2020-04-09 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | - HDMI to Displayport converter is not working for 2 workstations - HDMI to Displayport converter is easily broken - Need to replace HDMI to Displayport converters -> HDMI to Displayport cables - Purchase HDMI to Displayport cables for 3 monitors Ip address of workstations are as follows 10.49.1.163 10.49.1.152 10.49.3.15 | Work in Progress | admin.Reymark B. Evangelista
CSR-0025-20 | CSR | Judelyn E. Rosales | 2020-01-09 09:38:00 | 2020-01-20 21:00:00 | 2020-01-14 08:28:00 | HO | Account Request | Deletion of Account (M. Isidoro) | Done | admin.Reymark B. Evangelista
QA-0062-20 | QA | Edgardo Jr. O. Oracion | 2020-01-09 10:00:00 | 2020-01-09 10:00:00 | 2020-01-09 10:05:00 | HO |  | add remote desktop access to 10.49.1.180 | Closed | admin.Reymark B. Evangelista
QA-0063-20 | QA | Catherine Anne D. CaÃ±onero | 2020-01-09 10:01:00 | 2020-01-09 10:01:00 | 2020-01-09 10:09:00 | HO |  | Support in OCE plotter | Closed | admin.Reymark B. Evangelista
QA-0064-20 | QA | Takashi Watanabe | 2020-01-09 10:14:00 | 2020-01-09 10:14:00 | 2020-01-09 10:15:00 | HO |  | Communicate to Supplier regarding Main & backup internet connection | Closed | admin.Reymark B. Evangelista
QA-0065-20 | QA | Jeniline Trina M. Jamora | 2020-01-09 10:16:00 | 2020-01-09 10:16:00 | 2020-01-09 10:17:00 | HO |  | Dear Both, For your support please, I cannot saved file inside \\10.49.1.97\iso\QMS\Certificate of Understanding\2020\EA_Scanned_COU Thank you very much and have a nice day. All the best, Jeniline Trina Jamora EA Department | Closed | admin.Reymark B. Evangelista
QA-0066-20 | QA | Eobii Arre D. Austria | 2020-01-09 08:00:00 | 2020-01-09 08:00:00 | 2020-01-09 08:29:00 | HO |  | macro file not working | Closed | admin.Joe Nico T. Geronimo
CSR-0050-20 | CSR | Imee B. Briones | 2020-01-09 10:23:00 | 2020-01-17 10:23:00 | 2020-01-24 08:02:00 | HO | Increase Capacity | Provide data quota/restrictions under the folder 10.49.1.97/wh Kindly send the latest usage of each folder under the directory of wh. | Done | admin.Reymark B. Evangelista
CSR-0027-20 | CSR | Donn M. Carlos | 2020-01-09 13:15:00 | 2020-04-09 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | PC Replacement 10.49.2.230 10.49.2.231 | Work in Progress | admin.Kiel Antaran
QA-0067-20 | QA | Merry-Chris J. Dugan | 2020-01-09 14:00:00 | 2020-01-09 14:00:00 | 2020-01-09 14:01:00 | HO |  | add remote access to plocomp 10.49.1.12 | Closed | admin.Reymark B. Evangelista
CSR-0030-20 | CSR | Kristine G. Boado | 2020-01-09 14:01:00 | 2020-01-10 14:01:00 | 2020-01-10 08:07:00 | HO | Borrow | Request to borrow 1 PC Monitor to accomplish job order. | Done | admin.Joe Nico T. Geronimo
QA-0068-20 | QA | Mary Ann N. Javier | 2020-01-09 14:10:00 | 2020-01-09 14:10:00 | 2020-01-09 14:11:00 | HO |  | Laptop keyboard malfunction | Closed | admin.Reymark B. Evangelista
CSR-0046-20 | CSR | Jenny Lyn G. Miranda | 2020-01-09 15:38:00 | 2020-01-13 15:38:00 | 2020-01-15 12:04:00 | HO | Modify Software | I would like to request for an update of CATIA version 2015 to CATIA version 2017. CATIA PC is located in TBU Toyota room. We need the update as soon as possible since we are already receiving version 2017 data / job requests from our customer. Thank you very much in advance! | Done | admin.Jasper Labenia
QA-0069-20 | QA | Marie Rose A. Farala | 2020-01-09 16:05:00 | 2020-01-09 16:05:00 | 2020-01-09 16:06:00 | HO |  | connect to proxy | Closed | admin.Reymark B. Evangelista
DRR-0006-20 | DRR | Hansel M. Nablo | 2020-01-10 06:52:00 | 2020-01-10 06:52:00 | 2020-01-16 08:03:00 | HO | Windows | CE19-PK-0388(191216);\\10.49.1.97\cdd\CDE\01CDC Start 16 June\A2T\CE19-PK-0388(191118);\\10.49.1.97\cdd\CDE\01CDC Start 16 June\A2T\CE19-PK-0388(191118)\â‘§WORKING DATA\Hansel;Yes;Data maybe accidentally deleted by someone. | Done | admin.Joe Nico T. Geronimo
QA-0079-20 | QA | Eric T. Nealega | 2020-01-10 06:50:00 | 2020-01-10 06:50:00 | 2020-01-10 06:56:00 | HO |  | ã€ãƒ€ã‚¦ãƒ³ãƒ­ãƒ¼ãƒ‰URLã€‘ https://fileservice.jp.yazaki.com/adauth/request/CfHttpReqDownload.aspx?pass=96%2fYiMiUpvO3I9XxVCklwg%3d%3dw0gs1Khajyqssy8mte48wA%3d%3d Assist to DL the link | Closed | admin.Reymark B. Evangelista
QA-0080-20 | QA | Kristine Dianne Y Tecson | 2020-01-10 07:30:00 | 2020-01-10 07:30:00 | 2020-01-10 07:45:00 | HO |  | no connection | Closed | admin.Reymark B. Evangelista
QA-0081-20 | QA | Helen C. Macasera | 2020-01-10 07:50:00 | 2020-01-10 07:50:00 | 2020-01-10 07:55:00 | HO |  | Borrowed jabra | Closed | admin.Reymark B. Evangelista
CSR-0072-20 | CSR | Ma. Reina Monserrat A. Abalos | 2020-01-10 08:08:00 | 2020-01-14 21:00:00 | 2020-01-28 19:14:00 | HO | Install Software | extes installation | Closed | admin.John Christian Lovitos
QA-0082-20 | QA | Helen C. Macasera | 2020-01-10 08:00:00 | 2020-01-10 08:00:00 | 2020-01-10 08:09:00 | HO |  | PC black screen | Closed | admin.Reymark B. Evangelista
QA-0083-20 | QA | Mariel R. Santos | 2020-01-10 08:30:00 | 2020-01-10 08:30:00 | 2020-01-10 08:43:00 | HO |  | No signal monitor black screen | Closed | admin.Reymark B. Evangelista
QA-0084-20 | QA | Cecil T. Morales | 2020-01-10 09:00:00 | 2020-01-10 09:00:00 | 2020-01-10 09:30:00 | HO |  | Clover cannot access | Closed | admin.Reymark B. Evangelista
QA-0085-20 | QA | Michelle C. Dela Cruz | 2020-01-10 08:05:00 | 2020-01-10 08:05:00 | 2020-01-10 08:52:00 | HO |  | Lync Support | Closed | admin.Reymark B. Evangelista
QA-0086-20 | QA | Francis Benjamin C. Cagampan | 2020-01-10 09:15:00 | 2020-01-10 09:15:00 | 2020-01-10 09:27:00 | HO |  | no network connection | Closed | admin.Reymark B. Evangelista
QA-0087-20 | QA | Christian Saner | 2020-01-10 10:20:00 | 2020-01-10 10:20:00 | 2020-01-10 10:29:00 | HO |  | Desktop running slow as per checking the drive c is almost full so i suggest it to delete all resign users. | Closed | admin.Reymark B. Evangelista
QA-0088-20 | QA | Roda A. Dela Pena | 2020-01-10 10:22:00 | 2020-01-10 10:22:00 | 2020-01-10 10:38:00 | HO |  | Slow pc | Closed | admin.Joe Nico T. Geronimo
QA-0089-20 | QA | Helen C. Macasera | 2020-01-10 10:00:00 | 2020-01-10 10:00:00 | 2020-01-10 10:10:00 | HO |  | pc do not turn on | Closed | admin.Joe Nico T. Geronimo
QA-0090-20 | QA | Donald Kerby L. Manejero | 2020-01-10 10:50:00 | 2020-01-10 10:50:00 | 2020-01-10 10:55:00 | HO |  | teach sir donald on how to install omnitrus & configuration of IE | Closed | admin.Reymark B. Evangelista
CSR-0049-20 | CSR | Manuel Louie M. Soriano | 2020-01-10 10:32:00 | 2020-01-27 08:15:00 | 0000-00-00 00:00:00 | HO | PC Configuration | Request to create access limited folder for the following Simulation PC's exclusive to all EV members only. (this is for the countermeasure on our ISMS internal audit CPAR on handling secret data on simulation studies). 1. 10.49.1.90 -->10.49.2.121 2. 10.49.1.99 -->10.49.2.85 3. 10.49.1.168 -->10.49.1.99 4. 10.49.2.95 -->10.49.1.90 5. 10.49.2.121 -->10.49.2.95 6. 10.49.2.45 -->10.49.1.168 EV Members Names HO andBO Baylon, Dominic Robles, Alexander A. Domdom, Jose Jr. L. Gamboa, John Hennsy C. Soriano, Manuel Louie Samson, Jose Ching, Bryan Allan Calub, Ryan S. Guilao, Hanae Joyce Gambon, Julius G. Del-isen, Janser Jurada, Jeffrey Paredes, Mark Anthony Santos, Rens Nicko Guernaldo, Mae Anne Pualon, Ma. Rebecca Valenciano, Lucindo Sofronio Caballero, Eron Jay Macarayon, Jeffrey Martinez, Patrick David, Joanna Fernando, Salvador Jr. Silva, Fermin III Dumol, Anthony John Santos, Faustino Jr. Rosquillo, Maribel Razonable, Christal Joy Dionela, Vladimir De Jesus, Jhaennie Lyn Lopez, Christelle Joy D. Panganiban, Ayen G. Pantoni, Edvin B. Pauly, Joseph H. Gallares, Jay-Ar E. San Joaquin, Christian H. Higo, Meynard King B. Madrona, Charmine Lou G. Estrada, Quenie A. Albano, Maricar P. Miguel, Melisa T. Raposon, Alvin B. Oracion, Edgardo O. Jr. Aspa, Marvin Lee E. Bautista, Condrad V. Lupig, Edmar M. Santos, Reignwell J. Tan, Jaime P. Jr. Moncada , Gerald F. Barroga , Arjep P. Ragual, Natassja Jane L. Despabiladeras, Lorenzo E. Capones, Clariza B. Austria, Eobii Arre D. Pascual, Carlito N. Takahashi, Keiji P. Lanto, Jesril R. Lopez, Jethro M. De Leon, Mac Mhenard H. Alonsagay, Aldwin N. Bravo, Jikko G. Hallig, Marjhel G. Saner, Christian Irish A. PeÃ±amante, Mart Aviz L. Wage, Michael Joshua C. Servano, Jessie E Valguna, Mark Loren Sucaldito, Mark Da-anton, Arvin Jon P. Magarse, Kayzelle Shyne S. Lachica, Ariel L. CaÃ±a, Elizer Dominic L. Casas, Miel Roque M. Polutan, Jayson Kyrl F. Baytic, Shiela T. Cagape, George Vincent C. Tranco, Ian Gabriel Malijoc, Susan V. Laurio, Christian, E. Melendres, Ervin John D. Remo, John Michael V. Demetita, Kiss Thrill G. | Work in Progress | admin.Reymark B. Evangelista
CSR-0066-20 | CSR | Arlie F. Pida | 2020-01-10 11:15:00 | 2020-01-13 21:00:00 | 2020-01-18 10:30:00 | HO | Install Software | request to install excel camera feature in the excel application for production concept making purposes | Done | admin.Reymark B. Evangelista
CSR-0060-20 | CSR | Ann Gymverlyn O. Mendoza | 2020-01-10 12:47:00 | 2020-01-21 21:00:00 | 2020-01-20 15:58:00 | HO | Account Request | JBRB request of account for Japanese Customer in TBURB common folder in PET server (See attached file for other details) | Done | admin.Reymark B. Evangelista
CPR-0003-20 | CPR | Acer Chael R. Dupaya | 2020-01-10 15:05:00 | 2020-01-13 15:05:00 | 2020-01-16 11:03:00 | HO | Mouse | The Scroll button doesn't function properly. | Done | admin.Joe Nico T. Geronimo
CSR-0091-20 | CSR | Jojiemar A. Villapando | 2020-01-10 15:18:00 | 2020-01-21 21:00:00 | 2020-01-22 16:39:00 | HO | Access Request | Access right for GMT Folder. \\Petsvr1097\wh\GMT Jojiemar Villapando - 1643 | Done | admin.Willem R. Leonardo
CSR-0048-20 | CSR | Donn M. Carlos | 2020-01-10 15:34:00 | 2020-04-10 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | PC Replacement for September, November and May | Work in Progress | admin.Joe Nico T. Geronimo
QA-0095-20 | QA | Corazon A. Coronel | 2020-01-13 10:25:00 | 2020-01-13 10:25:00 | 2020-01-15 10:25:00 | HO | CAE-Others | Change of Department Layout of MIS (ISMS CPAR - Inventory ) | Closed | admin.admin.John Christian Lovitos
DRR-0005-20 | DRR | Victoria B. De Jesus | 2020-01-14 08:19:00 | 2020-01-13 16:00:00 | 2020-01-30 12:06:00 | HO | Windows | 2-5_PPAP;\\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Material\â˜…Manualsâ˜…;Original Directory;No;Accidentally deleted the folder. | Done | admin.Joe Nico T. Geronimo
CSR-0068-20 | CSR | Jovielet B. Caintoy | 2020-01-14 09:07:00 | 2020-01-23 21:00:00 | 2020-01-30 11:22:00 | HO | Account Request | Delete windows log-in and folder access right of resign employee 1.Genesis Bachiller 2. Kersteen Daoayen 3. Stephanie Pauline Cesa | Done | admin.Reymark B. Evangelista
QA-0096-20 | QA | Almar Abner Q. Cenizal | 2020-01-14 09:30:00 | 2020-01-14 09:30:00 | 2020-01-14 09:33:00 | HO |  | network problem | Closed | admin.Joe Nico T. Geronimo
QA-0097-20 | QA | Joana Marie C. Capinding | 2020-01-14 09:34:00 | 2020-01-14 09:34:00 | 2020-01-14 09:40:00 | HO |  | add japanesse language | Closed | admin.Joe Nico T. Geronimo
CSR-0042-20 | CSR | Melisa T. Miguel | 2020-01-14 09:40:00 | 2020-01-23 21:00:00 | 2020-01-30 12:06:00 | HO | Access Request | CMMS ACCESS | Done | admin.Joe Nico T. Geronimo
CSR-0047-20 | CSR | Melisa T. Miguel | 2020-01-14 09:42:00 | 2020-01-23 21:00:00 | 2020-01-15 12:12:00 | HO | Access Request | access on website https://jp.misumi-ec.com/ for collars bolts and nut reference | Done | admin.Reymark B. Evangelista
CSR-0067-20 | CSR | Rafael S. Fontenuela | 2020-01-14 10:28:00 | 2020-01-20 21:00:00 | 0000-00-00 00:00:00 | HO | Install Software | Currently using GLOBAL License for ANSYS. However, Local ANSYS license is missing. We need to also have local license in case of server shutdown and upon finishing of the GLOBAL license trial. â‘ 10.49.1.120 â‘¡10.49.1.188 â‘¢10.49.5.3 â‘£10.49.1.186 | Assigned | admin.Jasper Labenia
CSR-0069-20 | CSR | Redemptor C. Batiduan | 2020-01-14 13:02:00 | 2020-01-15 21:00:00 | 2020-01-20 14:02:00 | HO | Install Software | Install CATIA 2017. | Done | admin.Jasper Labenia
CSR-0076-20 | CSR | Johanna Marie C. Dandan | 2020-01-14 13:01:00 | 2020-02-25 21:00:00 | 0000-00-00 00:00:00 | HO | Renewal License | Request for CATIA License Renewal *CATIA Hybrid design 2 (HD2) *CATIA Knowledge Advisor 2 (KWA) *CATIA Step Core Interface (ST1) *Target ID = DDX-41681C4A3E7D2131 *IP Address = 10.49.2.193 *Date Covered = Feb. 10, 2020 to Feb. 09, 2021 Request for CATIA Mechanical Design 2 (MD2) *Target ID = ZAF-41F710481C79F421 *IP Address = 10.49.1.182 *Date Covered = Feb. 10, 2020 to Feb. 09, 2021 | Work in Progress | admin.Jasper Labenia
CSR-0065-20 | CSR | Ann Gymverlyn O. Mendoza | 2020-01-14 13:09:00 | 2020-02-25 21:00:00 | 0000-00-00 00:00:00 | HO | Renewal License | 1. Request of JBRB Catia License charge 150,500.59 Target ID MBD-441E108CFDDBECC9 Software Usage Others Budget Feb 2020 2. Request of JBRB Catia License charge 150,500.59 Target ID VWY-43491CB1D72C98EC Software Usage Others Budget Feb 2020 | Work in Progress | admin.Jasper Labenia
CSR-0070-20 | CSR | Jovielet B. Caintoy | 2020-01-14 13:05:00 | 2020-01-23 21:00:00 | 2020-01-22 08:09:00 | HO | Access Request | Request for Additional Access Right. 1.Danica Cultura 2. Abigail Salas 3. Christine Suarez 4. Marisol Cabacungan 5. Jojiemar Villapando | Done | admin.Reymark B. Evangelista
CSR-0075-20 | CSR | Roda A. Dela Pena | 2020-01-14 15:26:00 | 2020-01-16 21:00:00 | 2020-01-20 14:31:00 | HO | Plotter Configuration | Kindly install the plotter driver of the new plotter 6057 to all Toyota group members. | Done | admin.Willem R. Leonardo
QA-0098-20 | QA | Ronalyn D. De Castro | 2020-01-14 19:10:00 | 2020-01-14 19:10:00 | 2020-01-14 19:20:00 | HO |  | installation of plotter 2 pc | Closed | admin.Willem R. Leonardo