## Worksheet
HO June 2019
New Request | Assigned | Work in Progress | Done | Closed | Total
0 | 0 | 1 | 46 | 135 | 182
| Completed Request | On-going Request | Delay Request | Total Request | Completion % | On Time %
CSR | 88 | 1 | 1 | 89 | 98.88 | 98.86
CPR | 14 | 0 | 0 | 14 | N/A | N/A
DRR | 11 | 0 | 0 | 11 | N/A | N/A
Member | Assigned | Work in Progress | Done | Closed
admin.Aaron Jet N. Sarreal | 0 | 0 | 0 | 8
admin.Abel D. Chaves | 0 | 0 | 0 | 1
admin.Charmaine F. Layawon | 0 | 0 | 0 | 1
admin.Chester Jed T. Banez | 0 | 0 | 3 | 11
admin.Christ John Dela Cruz | 0 | 0 | 1 | 3
admin.Greg Daniel E. Mojica | 0 | 0 | 2 | 14
admin.Jasper Labenia | 0 | 0 | 0 | 1
admin.Joe Nico T. Geronimo | 0 | 1 | 10 | 26
admin.Reymark B. Evangelista | 0 | 0 | 22 | 51
admin.Rommel Y. Bacus | 0 | 0 | 8 | 18
admin.Willem R. Leonardo | 0 | 0 | 0 | 1
Reference # | Process | Requestor | Date Request | Date Needed | Date Done | Site | Category | Details | Status | Assigned to
CSR-0517-19 | CSR | Cristine B. Suarez | 2019-05-16 09:16:00 | 2019-05-22 21:00:00 | 2019-06-28 19:03:00 | HO | Backup CAE file/s | Additional folder. /export/home/eucoodb/model/work/SZK-WSZ NAME OF ADDITIONAL FOLDER: YKCJ | Closed | admin.Greg Daniel E. Mojica
QA-1079-19 | QA | Marjorie Padilla | 2019-05-16 09:02:00 | 2019-05-16 09:02:00 | 2019-05-16 09:20:00 | HO |  | Printer Spooling in WH | Closed | admin.Reymark B. Evangelista
QA-1080-19 | QA | Albert M. Mangabay | 2019-05-16 09:50:00 | 2019-05-16 09:50:00 | 2019-05-16 09:52:00 | HO |  | add remote access 10.49.131.252 | Closed | admin.Reymark B. Evangelista
CSR-0511-19 | CSR | Nikee M. Ibarrientos | 2019-05-16 10:22:00 | 2019-06-07 08:52:00 | 2019-06-04 07:39:00 | HO | Borrow | Borrow laptop for business trip in China on Monday, May 20, 2019. | Done | admin.Reymark B. Evangelista
QA-1086-19 | QA | Aldrin S. De Guzman | 2019-05-16 11:11:00 | 2019-05-16 11:11:00 | 2019-05-16 11:16:00 | HO |  | activate MS office | Closed | admin.Reymark B. Evangelista
CSR-0508-19 | CSR | Bryan Mar R. Alvarez | 2019-05-16 14:40:00 | 2019-05-24 07:35:00 | 2019-05-31 11:09:00 | HO | Borrow | INSTALL SONY VEGAS FOR EDITING PURPOSES | Closed | admin.Reymark B. Evangelista
CSR-0510-19 | CSR | Maria Josefa G. Samson | 2019-05-16 16:43:00 | 2019-05-27 21:00:00 | 2019-05-27 13:20:00 | HO | Access Request | Deletion due to resignation ( Delos Reyes, Lorenzo M.) ID # PET1821 Email add lorenzo.delosreyes@ph.yazaki.com | Closed | admin.Reymark B. Evangelista
CSR-0515-19 | CSR | Emmanuel Jr. C. Jimenez | 2019-05-16 19:25:00 | 2019-05-27 21:00:00 | 2019-06-06 06:47:00 | HO | Access Request | Deletion of access rights of Dave Mark Ferrer(PET1452) | Done | admin.Reymark B. Evangelista
QA-1091-19 | QA | Corazon A. Coronel | 2019-05-16 23:36:00 | 2019-05-16 23:36:00 | 2019-05-24 23:36:00 | HO | CAE-Others | Update Department Layout of MIS | Closed | admin.Christ John Dela Cruz
CPR-0052-19 | CPR | Eurie A. Bandian | 2019-05-17 07:09:00 | 2019-05-17 07:09:00 | 2019-05-21 06:34:00 | HO | Mentor Graphics | License error when opening Siemens NX 11.0 | Done | admin.Chester Jed T. Banez
QA-1092-19 | QA | Erika Joyce C. Santiago | 2019-05-17 08:55:00 | 2019-05-17 08:55:00 | 2019-05-17 09:00:00 | HO |  | create scan folder in new plotter | Closed | admin.Reymark B. Evangelista
QA-1093-19 | QA | Eric T. Nealega | 2019-05-17 09:35:00 | 2019-05-17 09:35:00 | 2019-05-17 09:38:00 | HO |  | mouse check and replace mouse to old mouse | Closed | admin.Reymark B. Evangelista
CSR-0514-19 | CSR | Rhea Joy S. Alminaza | 2019-05-17 10:06:00 | 2019-05-20 21:00:00 | 2019-06-24 12:44:00 | HO | Access Request | Request Access rights for Mr. Mark Ian Mendoza ID 1999 new Employee of CON (HO), Location \\Petsvr1097\cdd\Monthly\Trainings\Performance Dashboard\HO & BO | Closed | admin.Chester Jed T. Banez
QA-1095-19 | QA | Jenie May A. Crispino | 2019-05-17 10:00:00 | 2019-05-17 10:00:00 | 2019-05-17 10:16:00 | HO |  | assist paper jam in oce | Closed | admin.Charmaine F. Layawon
QA-1096-19 | QA | Mark Joseph S. Quion | 2019-05-17 10:14:00 | 2019-05-17 10:14:00 | 2019-05-17 10:20:00 | HO |  | register new ID to colored printer | Closed | admin.Reymark B. Evangelista
CSR-0576-19 | CSR | Maria Josefa G. Samson | 2019-05-17 09:42:00 | 2019-05-31 21:00:00 | 2019-08-07 09:57:00 | HO | Transfer PC location | ES RC Members re-layout (May 31, 2019 4 45pm) | Closed | admin.Greg Daniel E. Mojica
CSR-0509-19 | CSR | Redemptor C. Batiduan | 2019-05-17 11:11:00 | 2019-05-20 21:00:00 | 2019-05-29 13:03:00 | HO | Install Software | 1) Install e-drawings 2018 2) Install OmniTrust | Closed | admin.Rommel Y. Bacus
CSR-0526-19 | CSR | Sharmaine T. Ingles | 2019-05-17 11:16:00 | 2019-05-27 06:48:00 | 2019-05-24 19:47:00 | HO | Borrow | (TCE) Borrow 3 Computers with Windows for 1 year. Location- 2 Documentation Area, 1 Cross Section Area | Closed | admin.Rommel Y. Bacus
CSR-0519-19 | CSR | Stefano S. Ranchez | 2019-05-17 12:42:00 | 2019-05-20 21:00:00 | 2019-05-20 17:01:00 | HO | Transfer Software location | Transfer Microsoft Outlook from 10.49.1.187 to 10.49.1.120, for better utilization of the software. | Done | admin.Reymark B. Evangelista
CSR-0535-19 | CSR | Rose P. JariÃ±o | 2019-05-17 15:07:00 | 2019-05-24 06:42:00 | 2019-06-28 19:04:00 | HO | Backup CAE file/s | Create folder for model J03A/F/E in /export/home/eucoodb/model/work/MAZDA. | Closed | admin.Greg Daniel E. Mojica
CSR-0513-19 | CSR | Patrick B. Martinez | 2019-05-17 15:49:00 | 2019-05-20 21:00:00 | 2019-07-11 21:09:00 | HO | Increase Capacity | Add "EV_HO_EXTENSION" Folder at EV Branch with capacity limit to 300 GB while other folders using remaining capacity of 350 GB out of 650 GB Please see attachment "User account form" For access limited only to individuals listed for the EV_HO_EXTENSION folder | Closed | admin.Abel D. Chaves
DRR-0049-19 | DRR | Annie C. Palo | 2019-05-17 16:01:00 | 2019-05-17 16:01:00 | 2019-06-26 14:48:00 | HO | Windows | COMMON;\\10.49.1.97\wh\HONDA\HONDA OLD\COMMON;\\10.49.1.97\wh\HONDA\7. COMMON\1. MEMBERS FOLDER\annie;No;Accidentally delete | Closed | admin.Rommel Y. Bacus
CPR-0054-19 | CPR | Chester Jed T. Banez | 2019-05-20 06:50:00 | 2019-05-03 06:50:00 | 2019-06-06 07:31:00 | HO | No Connection | Internet Connection on our Backup Line PLDT is down | Closed | admin.Chester Jed T. Banez
CPR-0061-19 | CPR | Chester Jed T. Banez | 2019-05-20 06:52:00 | 2019-05-17 06:52:00 | 2019-06-06 07:28:00 | HO | Server | File Server cannot access last May 18, 2019 @ 340 am | Closed | admin.Chester Jed T. Banez
CPR-0060-19 | CPR | Chester Jed T. Banez | 2019-05-20 06:54:00 | 2019-05-17 06:54:00 | 2019-06-06 07:27:00 | HO | Server | Replication of DB_Prod (database of MHT) having problem in replicating in iloilo | Closed | admin.Chester Jed T. Banez
DRR-0050-19 | DRR | Rosalinda P. Tayer | 2019-05-20 08:34:00 | 2019-04-08 08:34:00 | 2019-05-27 11:07:00 | HO | Windows | 1. BODY 2019 5. ENGINE LYX 772 2019 9. PASS DOOR TRIM 2. CONSOLE AUTO 6. HEADLINER WITH SUNROOF 10. RIGHT REAR DOOR 2019 3. DOOR PASSENGER 7. LEFT REAR DOOR 4. ENGINE LTG 770 2019 8. LIFTGATE;\\petsvr1097\WH\GMT\DOCUMENTS\PROGRESS LIST\D2UC\2019;Original Directory;No;accidentally deleted (unknown) | Done | admin.Reymark B. Evangelista
QA-1101-19 | QA | Jayson V. Oblea | 2019-05-20 08:47:00 | 2019-05-20 08:47:00 | 2019-05-20 09:00:00 | HO |  | network problem can't connect to server | Closed | admin.Reymark B. Evangelista
QA-1102-19 | QA | Marisol Cabacungan | 2019-05-20 09:15:00 | 2019-05-20 09:15:00 | 2019-05-20 09:19:00 | HO |  | install printer& plotter driver | Closed | admin.Reymark B. Evangelista
CSR-0553-19 | CSR | Marilou R. Aquino | 2019-05-20 09:28:00 | 2019-05-31 12:09:00 | 2019-06-14 07:47:00 | HO | Transfer Software location | Transfer of Cadra to other IP address. To minimize borrowing of CADRA to co-member. | Closed | admin.Christ John Dela Cruz
CSR-0520-19 | CSR | Rose Ane E. Flores | 2019-05-20 11:35:00 | 2019-05-21 21:00:00 | 2019-05-21 13:27:00 | HO | Modify Software | Good day. May we request to refresh TAB438. It is urgent. Deadline of harness today. Thank you. ^_^ | Closed | admin.Greg Daniel E. Mojica
DRR-0051-19 | DRR | Abigail E. Salas | 2019-05-20 14:28:00 | 2019-05-17 14:28:00 | 2019-06-28 19:00:00 | HO | Cae | PD_PET-3665076R20-00000;/export/home/eucoodb/model/work/SZK-WSZ/Y0C/ENGINE/3665076R20/00000;Original Directory;No;Need the back up file. | Closed | admin.Greg Daniel E. Mojica
CPR-0055-19 | CPR | Sharmaine T. Ingles | 2019-05-20 15:58:00 | 2019-05-20 15:58:00 | 2019-05-23 08:25:00 | HO | Mouse | Replacement of Mouse for Computer Name - pet2pc2025 | Closed | admin.Reymark B. Evangelista
QA-1110-19 | QA | Ronald Alan Y. Cabangal | 2019-05-21 08:40:00 | 2019-05-21 08:40:00 | 2019-05-21 08:51:00 | HO |  | connect Laptop to network | Closed | admin.Reymark B. Evangelista
CPR-0058-19 | CPR | Sharmaine T. Ingles | 2019-05-21 08:56:00 | 2019-05-24 06:40:00 | 2019-06-06 07:26:00 | HO | Keyboard | Replacement of Keyboard for Computer Name - pet2pc2025 Ip Add - 10.49.2.25 in Measurement Room Profile Projector | Closed | admin.Chester Jed T. Banez
QA-1111-19 | QA | Anna Liza E. Ilusorio | 2019-05-21 09:00:00 | 2019-05-21 09:00:00 | 2019-05-21 09:08:00 | HO |  | excel problem can't save | Closed | admin.Reymark B. Evangelista
QA-1112-19 | QA | Noli F. Baldeviso | 2019-05-21 10:25:00 | 2019-05-21 10:25:00 | 2019-05-21 10:30:00 | HO |  | Reset passowrd | Closed | admin.Aaron Jet N. Sarreal
QA-1113-19 | QA | Edwin F. Fulgar | 2019-05-21 10:20:00 | 2019-05-21 10:20:00 | 2019-05-21 10:26:00 | HO |  | Reset password in DMS | Closed | admin.Aaron Jet N. Sarreal
QA-1114-19 | QA | Edwin F. Fulgar | 2019-05-21 10:20:00 | 2019-05-21 10:20:00 | 2019-05-21 10:26:00 | HO |  | Reset password in DMS | Closed | admin.Aaron Jet N. Sarreal
QA-1115-19 | QA | Johanna Marie C. Dandan | 2019-05-17 09:20:00 | 2019-05-17 09:20:00 | 2019-05-17 12:38:00 | HO |  | Assist in OMS. data adjustment | Closed | admin.Aaron Jet N. Sarreal
CSR-0525-19 | CSR | Antonio R. Baltazar | 2019-05-21 10:31:00 | 2019-05-23 21:00:00 | 2019-05-22 18:02:00 | HO | Backup CAE file/s | excel file recovery location \\10.49.1.97\wh\GMT\MAXTOR\JOB RELATED FILES\PRINT CLARIFICATION\GM-YYA\2019 file name 2019 Print Clarification Form Control List-YYA-E2YB | Done | admin.Rommel Y. Bacus
QA-1119-19 | QA | Milamari Q. Isidoro | 2019-05-21 15:32:00 | 2019-05-21 15:32:00 | 2019-05-21 15:45:00 | HO |  | Printer Problem | Closed | admin.Aaron Jet N. Sarreal
QA-1121-19 | QA | Johanna D. Santos | 2019-05-17 17:30:00 | 2019-05-17 17:30:00 | 2019-05-17 18:30:00 | HO |  | Lan disconnected | Closed | admin.Aaron Jet N. Sarreal
QA-1122-19 | QA | Johanna D. Santos | 2019-05-17 19:00:00 | 2019-05-17 19:00:00 | 2019-05-17 19:32:00 | HO |  | telephone disconnected | Closed | admin.Aaron Jet N. Sarreal
CSR-0529-19 | CSR | Redemptor C. Batiduan | 2019-05-21 11:05:00 | 2019-05-24 21:00:00 | 2019-05-23 12:37:00 | HO | Install Software | Install LS Prepost V4.5 (64 bit) in the following PCs. 1) 10.49.1.209 2) 10.49.1.189 3) 10.49.1.234 LS Prepost can be downloaded in Livermore Software site. | Closed | admin.Rommel Y. Bacus
CPR-0056-19 | CPR | Joan M. Fortuna | 2019-05-21 12:50:00 | 2019-05-21 12:50:00 | 2019-05-23 08:26:00 | HO | Mouse | double clicks even when i single click. | Closed | admin.Reymark B. Evangelista
CSR-0534-19 | CSR | Sharmaine T. Ingles | 2019-05-21 13:00:00 | 2019-08-21 21:00:00 | 2019-08-08 10:00:00 | HO | Hardware Purchase | 79th Term July Budget 6 pcs Numeric Keypad | Done | admin.Reymark B. Evangelista
CSR-0522-19 | CSR | Rose Ane E. Flores | 2019-05-21 14:23:00 | 2019-05-22 21:00:00 | 2019-05-21 20:07:00 | HO | Modify Software | Good day Sir, May we request to refresh TAB438. Thank you for your understanding. | Closed | admin.Greg Daniel E. Mojica
CSR-0524-19 | CSR | Glenn L. Fabian | 2019-05-21 14:07:00 | 2019-05-31 06:43:00 | 2019-06-24 12:45:00 | HO | Access Request | Yesterday, my members told me that they can see sub-folder (4) MANAGEMENT in 23 HARDWARE Folder Partition. I requested MIS-Chester to look into the folder access right. We found out that on the HardwareManagement User Group, ECI-BMS groups is declared as well. ECI-BMS Member include Hardware group members and ECI-CUSTOMERS. This means, not only my members can access CONFIDENTIAL FILES, BUT MORE IMPORTANTLY, ECI CAN ACCESS HARDWARE GROUP's CONFIDENTIAL FILES. Thus, I request MIS to 1) Take a screen shot of all the User group that can access hardware folder, 2) Take a screen shot of all members in each user group in 1) Note, You should not edit anything before taking the screen shot. 3) Investigate who included the ECI-BMS user group as member of HardwareManagement. The above is a case for Hardware folder access, last month there is also a scenario in which ECI-Software members can also see/access other folders in 1097 other that 31 eci->pet and 32 pet->eci. Since I am very worried with what MIS did on EI folder access, I have additional request below. 4) Screen shot all EI user group. 5) Screen shot all the members in each of the EI user group. If you have any question, please contact me. | Closed | admin.Chester Jed T. Banez
CSR-0543-19 | CSR | Jean Michelle P. Andoy | 2019-05-22 08:26:00 | 2019-09-11 13:27:00 | 2019-09-11 13:28:00 | HO | Renewal License | Renewal of ESET licenses (July 2019 to June 2020 | Done | admin.Reymark B. Evangelista
QA-1129-19 | QA | Mark Joseph D. Asis | 2019-05-22 08:13:00 | 2019-05-22 08:13:00 | 2019-05-22 08:27:00 | HO |  | user can't paste the file on file server even if he have access | Closed | admin.Reymark B. Evangelista
CSR-0541-19 | CSR | Angelo I. Tajonera | 2019-05-22 08:50:00 | 2019-05-23 21:00:00 | 2019-06-07 12:52:00 | HO | Install Software | We need to install YZKtool.exe given by the customer for our job. Please install to following IP address - 10.49.1.145 and 10.49.1.163 Installer address- \\10.49.1.97\31 eciâ†’pet\ECIâ†’PET(SOFTWARE)\78th Term\SW1\Others\MBD\20190522_YZKtool | Closed | admin.Reymark B. Evangelista
CSR-0562-19 | CSR | Christian F. Dipasupil | 2019-05-22 09:55:00 | 2019-05-30 07:21:00 | 2019-07-01 20:58:00 | HO | Install Software | Install TABAQ version 3.8.1.1 in 10.49.5.119 | Closed | admin.Rommel Y. Bacus
CSR-0561-19 | CSR | Christian F. Dipasupil | 2019-05-22 10:07:00 | 2019-05-29 07:20:00 | 2019-06-24 12:44:00 | HO | Access Request | Jasper Mark B. Lim pet1609 Request of folder access from HBU to TBU due to transfer of group \\10.49.1.97\prt\TBU\ | Closed | admin.Chester Jed T. Banez
DRR-0052-19 | DRR | Karen M. Mercado | 2019-05-22 13:54:00 | 2019-05-22 13:54:00 | 2019-05-23 15:48:00 | HO | Windows | D22E2YB151_A00_4693646;\\10.49.1.97\wh\GMT\MAXTOR\JOB RELATED FILES\E-MOCHIKIN\YYA\E2YB\LIFTGATE RIGHT\D22E2YB151_A00_4693646;;No;Corrupted File | Closed | admin.Rommel Y. Bacus
CSR-0532-19 | CSR | Agnes P. Javillonar | 2019-05-22 14:42:00 | 2019-05-29 14:42:00 | 2019-06-03 07:37:00 | HO | Backup to CD/DVD | Burn the files in DVD. Files are located in Local Disk ( C ). | Done | admin.Reymark B. Evangelista
CSR-0531-19 | CSR | Sherwin M. Burgos | 2019-05-22 14:54:00 | 2019-05-31 21:00:00 | 2019-05-28 11:16:00 | HO | Access Request | Internet access Need to access sites for online canvassing and research purposes. | Closed | admin.Chester Jed T. Banez
CSR-0530-19 | CSR | Krishella Mae R. Espenido | 2019-05-22 15:11:00 | 2019-05-24 06:32:00 | 2019-07-04 08:13:00 | HO | Access Request | We need to have an access in transferring our data using USB and memory card for NDS Heat Temperature Bending to laptop (i.p add 10.49.1.248). | Closed | admin.Chester Jed T. Banez
CSR-0560-19 | CSR | Jason L Odtuhan | 2019-05-22 15:33:00 | 2019-06-03 06:34:00 | 2019-06-03 07:36:00 | HO | Decrease Capacity | We want to delete all users in 10.49.2.193,10.49.2.186,10.49.1.181 except for the following ID 0544,1953,1986,1981,1611,1609 because the drive C are already full. | Done | admin.Reymark B. Evangelista
CPR-0062-19 | CPR | Reynan Jr. D. Torrecampo | 2019-05-23 07:48:00 | 2019-05-23 07:48:00 | 2019-05-27 13:33:00 | HO | Mouse | hard touch, hard to click | Done | admin.Reymark B. Evangelista
CSR-0538-19 | CSR | Troy C. Gatchalian | 2019-05-23 08:23:00 | 2019-08-23 21:00:00 | 2019-10-08 13:59:00 | HO | Hardware Purchase | Laptop DELL Latitude 7490 For Manager, business trip use | Closed | admin.Rommel Y. Bacus
QA-1140-19 | QA | Rosano A. Buerano | 2019-05-23 09:40:00 | 2019-05-23 09:40:00 | 2019-05-23 09:48:00 | HO |  | PC check end user report the pc still running slow | Closed | admin.Reymark B. Evangelista
CPR-0059-19 | CPR | Raffy V. Dacara | 2019-05-23 10:05:00 | 2019-05-23 10:05:00 | 2019-05-29 12:49:00 | HO | Keyboard | Keyboard and mouse won't function. | Done | admin.Rommel Y. Bacus
CSR-0552-19 | CSR | Marilou R. Aquino | 2019-05-23 12:48:00 | 2019-06-03 21:00:00 | 2019-05-31 10:36:00 | HO | Account Request | Additional e-mail for Ms. Fiona Cathrina Simbulan (Direct e-mail regarding ISMS and other customer information related to processing.) | Closed | admin.Reymark B. Evangelista
QA-1141-19 | QA | Ralph Kevin B. Bongay | 2019-05-23 13:20:00 | 2019-05-23 13:20:00 | 2019-05-23 13:25:00 | HO |  | user cannot open cmms | Closed | admin.Reymark B. Evangelista
CSR-0578-19 | CSR | Franz Myka M. Dumlao | 2019-05-23 18:29:00 | 2019-05-24 21:00:00 | 2019-07-01 20:53:00 | HO | Install Software | Request to transfer the software ACROBAT DC from IP 10.49.5.188 (Toyota Group) to 10.49.3.99 (HONDA Group). We ask the members of the group if they are using this software, and they said that they are not using it. It's okay for them to transfer the ACROBAT DC. Since we (Honda Group) are experiencing error in converting PDF to TIFF and vv. in our original ADOBE, this software will help us in converting large files. | Closed | admin.Rommel Y. Bacus
CSR-0542-19 | CSR | Jean Michelle P. Andoy | 2019-05-24 09:26:00 | 2019-07-31 21:00:00 | 2019-07-10 06:55:00 | HO | Renewal License | Renewal of desknet Neo (800 users) July 1, 2019 to June 30, 2020 | Done | admin.Reymark B. Evangelista
CSR-0625-19 | CSR | Johanna Marie C. Dandan | 2019-05-24 13:16:00 | 2019-05-28 21:00:00 | 2019-06-17 08:59:00 | HO | Access Request | Request to Transfer Account Access From TBU To HBU. (PRT Department) Kindly see attached file for location 1.) Escarcha, Rafael Christian R. (pet1982) | Done | admin.Joe Nico T. Geronimo
CPR-0063-19 | CPR | Bryan Mar R. Alvarez | 2019-05-24 13:22:00 | 2019-05-24 13:22:00 | 2019-05-31 10:50:00 | HO | PC Power Supply | LOOSEN POWER CORD | Closed | admin.Reymark B. Evangelista
CSR-0551-19 | CSR | Christine K. Fang-asan | 2019-05-24 14:26:00 | 2019-06-14 08:00:00 | 2019-07-03 17:20:00 | HO | Backup CAE file/s | Request for archive of all CAE files. | Closed | admin.Greg Daniel E. Mojica
CSR-0550-19 | CSR | Catherine U. Bulalacao | 2019-05-24 14:42:00 | 2019-06-14 08:00:00 | 2019-11-11 23:14:00 | HO | Backup CAE file/s | For archive of all CAE files stored in /export/home/eucoodb/model/repository/NISSAN_YHV/FOR ARCHIVE | Closed | admin.Greg Daniel E. Mojica
CSR-0549-19 | CSR | Catherine U. Bulalacao | 2019-05-24 15:20:00 | 2019-06-14 08:00:00 | 2019-11-11 23:19:00 | HO | Backup CAE file/s | For archive of all CAE files located in /export/home/eucoodb/model/repository/NISSAN_YTMI/ARCHIVE/ARCHIVE2 | Closed | admin.Greg Daniel E. Mojica
CSR-0548-19 | CSR | Mark Joseph D. Asis | 2019-05-24 15:47:00 | 2019-06-07 11:40:00 | 2019-05-27 13:52:00 | HO | Access Request | Have access to the TSE room SYNOLOGY as archive for satellite jobs for pet 0520 Nieto Vicente | Done | admin.Chester Jed T. Banez
QA-1148-19 | QA | Shusaku Fujiki | 2019-05-27 08:30:00 | 2019-05-27 08:30:00 | 2019-05-27 08:36:00 | HO |  | can't connect to server | Closed | admin.Reymark B. Evangelista
CPR-0065-19 | CPR | Marie Rose A. Farala | 2019-05-27 09:45:00 | 2019-05-27 09:45:00 | 2019-06-06 08:33:00 | HO | Mouse | Mouse not functioning well | Closed | admin.Reymark B. Evangelista
DRR-0056-19 | DRR | Eslaine A. Altamera | 2019-05-27 10:22:00 | 2019-06-11 06:44:00 | 2019-06-13 09:44:00 | HO | Windows | see folder;\\10.49.1.97\wh\TOYOTA\â‘³ CAE Related Documents\4. CONTROL LISTS\2019\2019 PRINT CLARIFICATION ;Original Directory;No;accidentally deleted | Done | admin.Reymark B. Evangelista
CSR-0557-19 | CSR | John Hennsy C. Gamboa | 2019-05-27 11:13:00 | 2019-05-28 21:00:00 | 2019-06-06 07:20:00 | HO | Access Request | â‡’internet access on educational sites(mathematics, data gathering techniques, etc.) for a more reliable data management and result â‡’to be used for efficiency data monitoring | Closed | admin.Chester Jed T. Banez
CSR-0559-19 | CSR | Glenn L. Fabian | 2019-05-27 16:03:00 | 2019-05-29 21:00:00 | 2019-06-11 12:39:00 | HO | Modify Software | 1) Kindly Download VX 2.3 64-bit version of Xpedition Enterprise in support.mentor.com 2) Kindly Download VX 2.3 Update 18. 3) Please install on 5/27 Eveningï¼š 10.49.3.91 10.49.3.161 10.49.1.94 10.49.5.133 4) Please install on 5/28 Eveningï¼š 10.49.3.221 10.49.3.155 10.49.3.162 If there is any inquiry, please feel free to contact me on toll dial 603 | Closed | admin.Rommel Y. Bacus
CSR-0574-19 | CSR | Corazon A. Coronel | 2019-05-27 21:50:00 | 2019-06-05 21:00:00 | 2019-06-27 14:03:00 | HO | Access Request | deletion of account of Marc Jonathan Sioco Deletion of email address of Marc Jonathan Sioco marc.sioco@ph.yazaki.com | Closed | admin.Joe Nico T. Geronimo
CSR-0575-19 | CSR | Corazon A. Coronel | 2019-05-27 21:54:00 | 2019-06-05 21:00:00 | 2019-07-01 09:28:00 | HO | Access Request | Jasper Labenia Associate Technical Support Analyst 1. Windows account (user & admin) 2. Email Account - jasper.labenia@ph.yazaki.com 3. DeskNeo Account 4. Folder Permission (MIS Folder & MIS Utilities - user account) 5. Lansweeper Account for Jasper & CJ | Closed | admin.Reymark B. Evangelista
CSR-0571-19 | CSR | Kristine G. Boado | 2019-05-28 09:17:00 | 2019-08-28 21:00:00 | 2019-09-11 13:35:00 | HO | Hardware Purchase | Request for Purchase 1 HP Prodesk PC 400 8GB Memory (79th term budget July -55,000) 1 Mirosoft Office Standard (79th term budget July-15,000) 1 Lync (79th term budget July-1,500) This pc will be used by Sir Benito Pitas for job monitoring and process help jobs to other SCD Departments. | Done | admin.Reymark B. Evangelista
CSR-0565-19 | CSR | Jasper Mark B. Lim | 2019-05-28 13:29:00 | 2019-06-06 21:00:00 | 2019-06-07 12:44:00 | HO | Access Request | TRANSFER FROM HBU TO TBU | Done | admin.Joe Nico T. Geronimo
CSR-0568-19 | CSR | Sharmaine T. Ingles | 2019-05-28 14:15:00 | 2019-06-06 21:00:00 | 2019-05-31 09:46:00 | HO | Account Request | Access Deletion of Resigned Employee TMO Jerico Argente ID No. 1136 | Closed | admin.Reymark B. Evangelista
CSR-0564-19 | CSR | Marife A. De Guzman | 2019-05-28 15:12:00 | 2019-05-29 21:00:00 | 2019-06-28 19:01:00 | HO | Modify Software | Kindly refresh immediately the PTM Registration of X1WS9C18 in server kih1ws1100(10.8.201.19) because it is deadline today 05/28/19. Thank you very much. | Closed | admin.Greg Daniel E. Mojica
DRR-0053-19 | DRR | Ma. Cecilia B. Bermejo | 2019-05-28 16:10:00 | 2019-05-28 16:10:00 | 2019-06-26 14:47:00 | HO | Windows | All files inside BONG folder.;\\10.49.1.97\wh\HONDA\HONDA OLD\OTHERS\BONG;\\10.49.1.97\wh\TQM\Activities\BONG;Yes;Files deleted are still need for creating report. | Closed | admin.Rommel Y. Bacus
QA-1156-19 | QA | Miriam S. Barin | 2019-05-29 07:30:00 | 2019-05-29 07:30:00 | 2019-05-29 07:32:00 | HO |  | cannot open powerpoint presentation. | Closed | admin.Joe Nico T. Geronimo
CSR-0600-19 | CSR | Bee-Jay R. Abad | 2019-05-29 08:05:00 | 2019-06-07 21:00:00 | 2019-06-11 14:31:00 | HO | Account Request | Request an email account for Maria Gazel A. Gile a TMO from TCE department. She need to have an access on email so that she will be aware on the current job situation or any job related concerns. | Done | admin.Reymark B. Evangelista
QA-1157-19 | QA | Judelyn E. Rosales | 2019-05-29 09:00:00 | 2019-05-29 09:00:00 | 2019-05-29 09:14:00 | HO |  | Assist on Video Conference room | Closed | admin.Reymark B. Evangelista
CSR-0569-19 | CSR | Grace A. Rivera | 2019-05-29 08:50:00 | 2019-06-07 21:00:00 | 2019-06-07 12:54:00 | HO | Access Request | Request: Windows Log-in, Access in EV Folder (pls. see attached file for the list) and Printer for New Employee in EV Dept. Mr. Mart Aviz L. PeÃ±amante - 2006 | Closed | admin.Reymark B. Evangelista
CSR-0587-19 | CSR | Redemptor C. Batiduan | 2019-05-29 10:19:00 | 2019-05-31 21:00:00 | 2019-06-11 12:35:00 | HO | Install Software | Install MTF Reader in the following workstations. 1) 10.49.1.189 2) 10.49.1.234 We already asked permission to WHE department (TBU Group) regarding the installation of the said application. You can call Jovic Nieto with local 674 for confirmation. | Closed | admin.Rommel Y. Bacus
QA-1159-19 | QA | Francisco III T. Javines | 2019-05-29 15:38:00 | 2019-05-29 15:38:00 | 2019-05-29 15:52:00 | HO |  | 5s in aseana 2 | Closed | admin.Reymark B. Evangelista
CSR-0626-19 | CSR | Johanna Marie C. Dandan | 2019-05-30 09:18:00 | 2019-06-21 06:49:00 | 2019-06-21 12:33:00 | HO | Account Request | Request for DELETION of Account and folder Access, CMMS, SEINE2 of Resigned PRT Employees. Kindly see the attached file for reference. Thank You 1. Lendyll Alipio (pet1603) 2. Jeffrey Mabayad (pet1935) | Done | admin.Reymark B. Evangelista
CPR-0066-19 | CPR | Jean Michelle P. Andoy | 2019-05-30 12:05:00 | 2019-05-30 12:05:00 | 2019-07-11 06:49:00 | HO | Projector | Acer Projector in Guest Room automatically shutdown after a minute. | Done | admin.Reymark B. Evangelista
QA-1162-19 | QA | Glenn L. Fabian | 2019-05-30 13:56:00 | 2019-05-30 13:56:00 | 2019-05-30 14:08:00 | HO |  | install purchase software CSR-0090-19 | Closed | admin.Reymark B. Evangelista
QA-1163-19 | QA | Samuel F. Samson | 2019-05-30 16:13:00 | 2019-05-30 16:13:00 | 2019-05-30 16:20:00 | HO |  | assist on print and scan for new plotter | Closed | admin.Reymark B. Evangelista
QA-1164-19 | QA | Bryan Allan B. Ching | 2019-05-30 16:30:00 | 2019-05-30 16:30:00 | 2019-05-30 16:33:00 | HO |  | add remote access to PC | Closed | admin.Reymark B. Evangelista
QA-1165-19 | QA | Bryan Allan B. Ching | 2019-05-30 16:30:00 | 2019-05-30 16:30:00 | 2019-05-30 16:33:00 | HO |  | add remote access to PC | Closed | admin.Reymark B. Evangelista
CSR-0577-19 | CSR | Franz Myka M. Dumlao | 2019-05-30 17:40:00 | 2019-05-31 21:00:00 | 2019-06-03 15:45:00 | HO | Backup CAE file/s | Request for the CAE back up of Honda Head Office. export/home/eucoodb/model/work/HONDA/ FOLDER: T14F, 3M0A & 3L1A | Closed | admin.Greg Daniel E. Mojica
QA-1166-19 | QA | Ervie C. Paular | 2019-05-31 08:40:00 | 2019-05-31 08:40:00 | 2019-05-31 08:46:00 | HO |  | PC can't turn on hardisk error | Closed | admin.Reymark B. Evangelista
QA-1167-19 | QA | Shusaku Fujiki | 2019-05-31 10:25:00 | 2019-05-31 10:25:00 | 2019-05-31 10:35:00 | HO |  | Assist on PDF/adobe acrobat also in printer | Closed | admin.Reymark B. Evangelista
QA-1168-19 | QA | Judelyn E. Rosales | 2019-05-31 14:11:00 | 2019-05-31 14:11:00 | 2019-05-31 14:31:00 | HO |  | assist mam judelyn on training room 1 because can't access on laptop | Closed | admin.Reymark B. Evangelista
CSR-0586-19 | CSR | Anthony N. Boado | 2019-05-31 14:24:00 | 2019-06-04 21:00:00 | 2019-07-23 20:49:00 | HO | Modify Software | To return CATIA license to stand alone license from floating licesnse 10.49.2.193= HD2+KWA+ST1 and STI 10.49.1.182= MD2 | Closed | admin.Rommel Y. Bacus
DRR-0055-19 | DRR | Jennygene P. Toding | 2019-05-31 15:22:00 | 2019-05-31 15:22:00 | 2019-07-29 11:59:00 | HO | Windows | 2. 2018 AP GROUP SCHED.xls;\\10.49.1.97\wh\TOYOTA\â‘³ CAE Related Documents\JOB RELATED FILES\MEMBERS FOLDER\PEACHY;\\10.49.1.97\wh\TOYOTA\â‘³ CAE Related Documents\JOB RELATED FILES\MEMBERS FOLDER\PEACHY\recovered;No;the file dated 02/19/2019 is corrupted, please recover a file with date prior to 02/19/2019. | Closed | admin.Rommel Y. Bacus
CSR-0585-19 | CSR | Aumer A. Velasquez | 2019-05-31 18:51:00 | 2019-06-11 21:00:00 | 2019-06-28 19:00:00 | HO | Add Interenet Connection | Good day, We would like to request refresh for TABGE3. Thank you | Closed | admin.Greg Daniel E. Mojica
CSR-0584-19 | CSR | Rosalinda P. Tayer | 2019-06-03 08:35:00 | 2019-06-04 21:00:00 | 2019-06-04 14:26:00 | HO | Install Software | Install Japanese Language in the following IP addresses. 10.49.1.222 10.49.5.35 10.49.2.107 10.49.5.130 10.49.1.198 10.49.3.65 10.49.2.134 10.49.3.97 10.49.5.117 10.49.1.110 10.49.2.229 10.49.2.151 | Done | admin.Rommel Y. Bacus
QA-1169-19 | QA | Jonalyn R. Sucion | 2019-06-03 08:00:00 | 2019-06-03 08:00:00 | 2019-06-03 08:15:00 | HO |  | can't connect to network due to ES change sitting arrangement | Closed | admin.Reymark B. Evangelista
QA-1170-19 | QA | Alexander C. Niza | 2019-06-03 08:50:00 | 2019-06-03 08:50:00 | 2019-06-03 09:02:00 | HO |  | cannot connect to network | Closed | admin.Reymark B. Evangelista
CPR-0067-19 | CPR | Julius Christian M. Mallari | 2019-06-03 09:14:00 | 2019-06-03 09:14:00 | 2019-06-03 19:10:00 | HO | Mouse | Left click doesn't work well | Done | admin.Rommel Y. Bacus
CSR-0599-19 | CSR | Yam Tweeven C. Lucerna | 2019-06-03 08:44:00 | 2019-06-14 08:44:00 | 2019-06-13 06:53:00 | HO | Backup to CD/DVD | To transfer files into CD for retention. | Done | admin.Reymark B. Evangelista
CSR-0598-19 | CSR | Jayson V. Oblea | 2019-06-03 14:28:00 | 2019-06-04 21:00:00 | 2019-06-10 15:18:00 | HO | Install Software | Installation of Software of camera Shodensha and SKM-Z300C-PC for picture of Battery Cable samples. | Done | admin.Rommel Y. Bacus
CSR-0597-19 | CSR | Vicente Z. Nieto | 2019-06-03 15:05:00 | 2019-06-06 21:00:00 | 2019-06-07 14:35:00 | HO | Account Request | Account request access for MTF (please check the list of employees at the attached file). Please install MTF reader and designer in computer with IP address (10.49.1.71) to be use during the job explanation with customer. | Done | admin.Rommel Y. Bacus
CSR-0596-19 | CSR | Ross Ma. Angelie S. Flores | 2019-06-03 15:14:00 | 2019-06-04 21:00:00 | 2019-06-26 09:58:00 | HO | Account Request | 1. Add windows and MHT of Neslie O. Borgonia(PET2004) and Joffa Dericka M. Raguindin (PET2005) 2. Give access to \\10.49.1.97\eed\HELP JOBS and \\10.49.1.97\common Account and Access to folders for new employees. | Closed | admin.Joe Nico T. Geronimo
CSR-0589-19 | CSR | Ronalyn G. Imana | 2019-06-04 08:38:00 | 2019-06-14 21:00:00 | 2019-07-02 15:17:00 | HO | Access Request | Request of temporary login of the following customers from 6/4/2019-6/7/2019 only Kentaro Okayama Naoki Kusagaya in folder \\10.49.1.97\ei\93 Temporary\Guest only | Done | admin.Reymark B. Evangelista
CSR-0609-19 | CSR | Rafael S. Fontenuela | 2019-06-04 09:46:00 | 2019-06-17 06:30:00 | 2019-11-05 14:52:00 | HO | Borrow | 3 Workstations for Head Office and 1 Workstation for Branch Office to be used for SolidWorks licenses while waiting for purchased PCs. The SW licenses will be separated from ANSYS PCs. | Closed | admin.Rommel Y. Bacus
QA-1171-19 | QA | Julius R. Fabonan | 2019-06-04 10:19:00 | 2019-06-04 10:19:00 | 2019-06-04 10:20:00 | HO |  | request for folder permission of guest | Closed | admin.Joe Nico T. Geronimo
QA-1172-19 | QA | Miriam M. Esquivel | 2019-06-04 10:20:00 | 2019-06-04 10:20:00 | 2019-06-04 10:25:00 | HO |  | request for internet access(previously have internet access) | Closed | admin.Joe Nico T. Geronimo
QA-1173-19 | QA | Marielle B. Esula | 2019-06-04 10:25:00 | 2019-06-04 10:25:00 | 2019-06-04 10:26:00 | HO |  | problem with adobe acrobat | Closed | admin.Joe Nico T. Geronimo
QA-1174-19 | QA | Jayson P. Gabilo | 2019-06-04 10:29:00 | 2019-06-04 10:29:00 | 2019-06-04 10:30:00 | HO |  | transfer picture from camera to file server | Closed | admin.Joe Nico T. Geronimo
QA-1176-19 | QA | Jeffrey S. Bernales | 2019-06-04 10:47:00 | 2019-06-04 10:47:00 | 2019-06-04 10:48:00 | HO |  | assist user for lock screen of computer | Closed | admin.Joe Nico T. Geronimo
QA-1177-19 | QA | Julius R. Fabonan | 2019-06-04 10:19:00 | 2019-06-04 10:19:00 | 2019-06-04 10:59:00 | HO |  | create windows log-in for guest until friday and connect it to lan | Closed | admin.Reymark B. Evangelista
CSR-0640-19 | CSR | Annabelle D. Capada | 2019-06-04 11:32:00 | 2019-06-25 07:21:00 | 2019-07-01 09:43:00 | HO | Backup to CD/DVD | 1. Transfer files to CD \\10.49.1.97\wh\FUJIJU\21 CAE RELATED DOCUMENTS\OTHERS\FOR CD\2016 FILES 2. Please delete folder "2018 SCANNED DRAWINGS" in this directory \\10.49.1.97\wh\FUJIJU\21 CAE RELATED DOCUMENTS\OTHERS\FOR CD | Done | admin.Reymark B. Evangelista
DRR-0058-19 | DRR | Stephanie Pauline T. Cesa | 2019-06-04 14:13:00 | 2019-06-04 14:13:00 | 2019-06-07 14:15:00 | HO | Cae | PD_24010C2C0A-0000M.ModelRoot;/export/home/eucoodb/model/work/NISSAN_RFQ/2019/06_JUNE/XC2C/24010C2C0A;Original Directory;No;Due to Critical Message occur. | Closed | admin.Greg Daniel E. Mojica
CSR-0639-19 | CSR | Carlo Gringo O. Saballa | 2019-06-04 14:11:00 | 2019-07-17 21:00:00 | 2019-06-27 10:10:00 | HO | Renewal License | Lightup license key . for Detail making comparison | Done | admin.Joe Nico T. Geronimo
DRR-0057-19 | DRR | Rosselle Salinas | 2019-06-04 14:36:00 | 2019-06-04 14:36:00 | 2019-06-28 18:45:00 | HO | Cae | 8524A343-0D011;/export/home/eucoodb/model/work/MITSU/GG2W/;Original Directory;No;Retrieval of data. | Closed | admin.Greg Daniel E. Mojica
CSR-0590-19 | CSR | Jovielet B. Caintoy | 2019-06-04 15:55:00 | 2019-06-14 21:00:00 | 2019-07-10 20:43:00 | HO | Account Request | Delete windows log-in, Seine 2 & Folder Access right of Girome Trasmer | Closed | admin.Joe Nico T. Geronimo
CSR-0591-19 | CSR | Jovielet B. Caintoy | 2019-06-04 16:03:00 | 2019-06-14 21:00:00 | 2019-06-11 13:36:00 | HO | Access Request | Request Access right. 1. Rudy Obina 2. Krispearl Belano 3. Rosalinda Tayer 4. Lyka Pajarilla 5. Florie Rose Mateo | Closed | admin.Reymark B. Evangelista
QA-1178-19 | QA | Miriam M. Esquivel | 2019-06-06 08:09:00 | 2019-06-06 08:09:00 | 2019-06-06 08:20:00 | HO |  | PC can't boot Operating System not found | Closed | admin.Reymark B. Evangelista
DRR-0060-19 | DRR | Jordan Dale B. Caldo | 2019-06-06 13:00:00 | 2019-06-06 13:00:00 | 2019-06-26 14:44:00 | HO | Windows | EKIK-1906003_(807W)_KATO_SAN_14T;\\10.49.1.97\jbrb\01_JBRB Design\00 JOB ORDERS\ECI-14T\TOYOTA\06_JUN;\\10.49.1.97\jbrb\01_JBRB Design\00 JOB ORDERS\ECI-14T\TOYOTA\06_JUN\RESTORED;No;need the original file(6/5)... file was overwritten (6/6) | Closed | admin.Rommel Y. Bacus
CSR-0592-19 | CSR | Grace A. Rivera | 2019-06-06 14:12:00 | 2019-06-18 21:00:00 | 2019-06-13 14:24:00 | HO | Access Request | Request: Windows Log-in, Access in EV Folder (pls. see attached file for the list) and Printer for New Employee in EV Dept. Mr. Michael Joshua C. Wage - 2011 | Done | admin.Joe Nico T. Geronimo
CSR-0628-19 | CSR | Johanna Marie C. Dandan | 2019-06-06 14:09:00 | 2019-06-21 06:50:00 | 2019-06-24 09:26:00 | HO | Account Request | Request for Account Log-In (Windows, SEINE2, CMMS) of Newly Hired Employee of PRT Dept. 1. Eduard Sacbibit (pet2008) | Done | admin.Reymark B. Evangelista
CSR-0608-19 | CSR | Ronalyn G. Imana | 2019-06-06 14:21:00 | 2019-06-18 21:00:00 | 2019-09-13 14:37:00 | HO | Access Request | Request of folder access of ECI customer YUSUKE TAKAGI (ID No. Y051442) in folders \\10.49.1.97\32 petâ†’eci\PETâ†’ECI(SOFTWARE) \\10.49.1.97\31 eciâ†’pet\ECIâ†’PET(SOFTWARE) | Closed | admin.Chester Jed T. Banez
CSR-0595-19 | CSR | Camille Marjorie B. Dela Vega | 2019-06-06 15:38:00 | 2019-06-07 21:00:00 | 2019-06-17 14:03:00 | HO | Backup CAE file/s | Need to create new folder for new model. Location : /export/home/eucoodb/model/work/MITSU Folder name or New model : GL0W | Done | admin.Greg Daniel E. Mojica
CSR-0594-19 | CSR | Ross Ma. Angelie S. Flores | 2019-06-06 16:17:00 | 2019-06-14 16:17:00 | 2019-06-10 14:29:00 | HO | Account Request | Request for Personal Email Account of Nikee M. Ibarrientos (PET1608) for communication with new Customer. | Done | admin.Joe Nico T. Geronimo
QA-1180-19 | QA | Jessica A. Benal | 2019-06-07 07:39:00 | 2019-06-07 07:39:00 | 2019-06-07 07:52:00 | HO |  | PC cannot open | Closed | admin.Reymark B. Evangelista
QA-1181-19 | QA | Milamari Q. Isidoro | 2019-06-07 08:30:00 | 2019-06-07 08:30:00 | 2019-06-07 08:40:00 | HO |  | printer assist OCE colored plotter | Closed | admin.Reymark B. Evangelista
CSR-0606-19 | CSR | Francis Benjamin C. Cagampan | 2019-06-07 09:28:00 | 2019-06-10 09:28:00 | 2019-06-18 12:30:00 | HO | Transfer PC location | Store WORK STATION (10.49.2.179, 10.49.1.12) to MIS side work station will be transfer back on the request of Sir Edwin/Sir Richard | Closed | admin.Rommel Y. Bacus
CSR-0605-19 | CSR | Ann Gymverlyn O. Mendoza | 2019-06-07 09:48:00 | 2019-06-19 21:00:00 | 2019-06-13 07:01:00 | HO | Account Request | Request of Windows log-in, CMMS, SEINE2, CIMS and DMS for new employee 1. Marvin L. Murallos- ID No. 2009 | Done | admin.Reymark B. Evangelista
QA-1182-19 | QA | Grace A. Rivera | 2019-06-07 10:00:00 | 2019-06-07 10:00:00 | 2019-06-07 10:03:00 | HO |  | installation of colorwave OCE | Closed | admin.Joe Nico T. Geronimo
CSR-0604-19 | CSR | Ann Gymverlyn O. Mendoza | 2019-06-07 09:56:00 | 2019-06-19 21:00:00 | 2019-06-11 08:04:00 | HO | Access Request | Folder access of new employee 1. Marvin L. Murallos- ID No. 2009 Please Urgent Thank you! | Done | admin.Chester Jed T. Banez
QA-1183-19 | QA | Alvin B. Raposon | 2019-06-07 10:00:00 | 2019-06-07 10:00:00 | 2019-06-07 10:04:00 | HO |  | remote desktop access to 10.49.1.51 | Closed | admin.Reymark B. Evangelista
CSR-0602-19 | CSR | Ma. Joelette L. Montemar | 2019-06-07 10:43:00 | 2019-11-29 07:44:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | PC Replacement for 10.49.3.97 (GM) PC Replacement for 10.49.2.149 (SZK) | Work in Progress | admin.Joe Nico T. Geronimo
CSR-0603-19 | CSR | Ross Ma. Angelie S. Flores | 2019-06-07 12:39:00 | 2019-06-10 12:39:00 | 2019-06-11 07:03:00 | HO | Account Request | 1. Add windows and MHT for Joel A. Vergara (PET2010). 2. Give access to \\10.49.1.97\eed\HELP JOBS and \\10.49.1.97\common Account and access to folder/s for new employee. | Done | admin.Reymark B. Evangelista
CSR-0614-19 | CSR | Roner B. Paguirigan | 2019-06-07 12:50:00 | 2019-06-13 12:50:00 | 2019-06-20 12:28:00 | HO | Account Request | Set Roner Paguirigan (pet0718) SRS account as exclusive checker for all WHE members related to any access and account addition, deletetion and change.Including PC transfer and Replacement This is for the proper monitoring of WHE members access and account inline with ISMS rules.In to maintain the integrity of PC layout and Inventory | Closed | admin.Willem R. Leonardo
CSR-0613-19 | CSR | Belinda C. Cabico | 2019-06-07 13:17:00 | 2019-06-10 08:00:00 | 2019-06-10 15:20:00 | HO | PC Configuration | Figures does not load properly when opening CD. Allow access of cabling folder (cdsymbol and cr5000). | Closed | admin.Rommel Y. Bacus
CSR-0612-19 | CSR | Roner B. Paguirigan | 2019-06-07 15:00:00 | 2019-10-31 11:44:00 | 2019-09-18 06:50:00 | HO | Renewal License | NX for NISSAN, annual renewal | Done | admin.Joe Nico T. Geronimo
QA-1184-19 | QA | Takashi Watanabe | 2019-06-10 08:00:00 | 2019-06-10 08:00:00 | 2019-06-10 08:10:00 | HO |  | Assist guest in guest room to connect his laptop to the network | Closed | admin.Reymark B. Evangelista
QA-1185-19 | QA | Grace A. Rivera | 2019-06-10 08:25:00 | 2019-06-10 08:25:00 | 2019-06-10 08:27:00 | HO |  | transfer picture from camera to phone | Closed | admin.Joe Nico T. Geronimo
QA-1186-19 | QA | Grace A. Rivera | 2019-06-10 08:25:00 | 2019-06-10 08:25:00 | 2019-06-10 08:27:00 | HO |  | transfer picture from camera to phone | Closed | admin.Joe Nico T. Geronimo
QA-1194-19 | QA | Francisco III T. Javines | 2019-06-10 13:00:00 | 2019-06-10 13:00:00 | 2019-06-10 13:04:00 | HO |  | temporary replace printer to guest room. | Closed | admin.Joe Nico T. Geronimo
QA-1195-19 | QA | Leandro B. Ventenilla | 2019-06-10 13:40:00 | 2019-06-10 13:40:00 | 2019-06-10 13:59:00 | HO |  | Problem with excel. Cannot edit excel | Closed | admin.Joe Nico T. Geronimo
QA-1196-19 | QA | John Elly C. Javier | 2019-06-10 13:55:00 | 2019-06-10 13:55:00 | 2019-06-10 14:00:00 | HO |  | not responding outlook and lync | Closed | admin.Joe Nico T. Geronimo
QA-1197-19 | QA | Johanna Marie C. Dandan | 2019-06-10 14:00:00 | 2019-06-10 14:00:00 | 2019-06-10 14:02:00 | HO |  | problem with printer | Closed | admin.Joe Nico T. Geronimo
QA-1198-19 | QA | Sarah Mae R. Bagis | 2019-06-10 14:02:00 | 2019-06-10 14:02:00 | 2019-06-10 14:04:00 | HO |  | Problem with printer | Closed | admin.Joe Nico T. Geronimo
QA-1199-19 | QA | John Elly C. Javier | 2019-06-10 14:00:00 | 2019-06-10 14:00:00 | 2019-06-10 14:51:00 | HO |  | Assist modify VBA code. | Closed | admin.Aaron Jet N. Sarreal
CSR-0615-19 | CSR | Rose Ane E. Flores | 2019-06-10 15:41:00 | 2019-06-11 21:00:00 | 2019-06-14 07:48:00 | HO | Modify Software | Good day Sir/Ma'am, May we request to refresh PARTS MASTER of HO server. Urgent po sana. Thank you po in advance. ^_^ Regards, Rose | Closed | admin.Christ John Dela Cruz
CSR-0616-19 | CSR | Sharmaine T. Ingles | 2019-06-10 15:58:00 | 2019-06-20 21:00:00 | 2019-06-26 09:56:00 | HO | Account Request | Access Deletion of Resigned Employee TMO Reymark Rapal ID No. 1314 | Closed | admin.Joe Nico T. Geronimo
CSR-0617-19 | CSR | Sharmaine T. Ingles | 2019-06-10 16:38:00 | 2019-06-20 21:00:00 | 2019-06-13 09:37:00 | HO | Access Request | TCE - Change of access rights of 3 TCE members CE home with access to modify. Belano, Comadre & Medina to Access EVC Actual Sales Monitoring CE , Jona Mae to Access TED Common Management for Mistake Summary Access & Deletion of Resigned Employee Reymark Rapal | Closed | admin.Joe Nico T. Geronimo
CSR-0620-19 | CSR | Mary Katherine Kaye F. Decena | 2019-06-11 08:16:00 | 2019-07-05 10:37:00 | 2019-07-24 14:27:00 | HO | Install Software | We need to install YZKtool.exe given by the customer for our job. Please install to following IP address - 10.49.1.145 10.49.3.151 10.49.1.172 10.49.3.153 10.49.1.14 10.49.3.15 10.49.3.13 10.49.1.152 Installer address- \\10.49.1.97\31 eciâ†’pet\ECIâ†’PET(SOFTWARE)\78th Term\SW1\Others\MBD\20190522_YZKtool | Closed | admin.Joe Nico T. Geronimo
CSR-0618-19 | CSR | Rose Ane E. Flores | 2019-06-11 08:36:00 | 2019-06-12 21:00:00 | 2019-06-14 07:49:00 | HO | Modify Software | Good morning Sir/Ma'am, May we request to refresh the Parts Master of BO to be reflected here in HO. Thank you. | Done | admin.Christ John Dela Cruz
CSR-0627-19 | CSR | Jason L Odtuhan | 2019-06-11 09:25:00 | 2019-06-12 21:00:00 | 2019-07-05 14:47:00 | HO | Install Software | TO INSTALL CATIA VERSION 2016 FOR OUR CUSTOMER YNA. PC LOCATION 10.49.1.181. | Done | admin.Rommel Y. Bacus
QA-1200-19 | QA | Sherwin M. Burgos | 2019-06-11 09:30:00 | 2019-06-11 09:30:00 | 2019-06-11 09:50:00 | HO |  | PC is running slow. | Closed | admin.Joe Nico T. Geronimo
QA-1201-19 | QA | Karmalou Sasaki | 2019-06-11 09:50:00 | 2019-06-11 09:50:00 | 2019-06-11 10:10:00 | HO |  | Unable to use PC | Closed | admin.Joe Nico T. Geronimo
CSR-0629-19 | CSR | Anthony N. Boado | 2019-06-11 12:42:00 | 2019-06-21 21:00:00 | 2019-08-07 22:50:00 | HO | Download | Update of PRT Layout prt (\\10.49.1.97):\@NON SALES@\(2) ISMS\(5) LAYOUT | Closed | admin.Jasper Labenia
CSR-0619-19 | CSR | Emmanuel Jr. C. Jimenez | 2019-06-11 13:10:00 | 2019-06-13 21:00:00 | 2019-06-18 12:49:00 | HO | Transfer PC location | Return 5 units of PC from branch Office see attached excel lay-out | Done | admin.Rommel Y. Bacus
QA-1202-19 | QA | Yam Tweeven C. Lucerna | 2019-06-11 13:35:00 | 2019-06-11 13:35:00 | 2019-06-11 13:42:00 | HO |  | requestor call mis for additional file transfer to CD | Closed | admin.Reymark B. Evangelista
CSR-0660-19 | CSR | Ronalyn G. Imana | 2019-06-11 15:46:00 | 2019-06-21 21:00:00 | 2019-06-26 09:55:00 | HO | Account Request | Request of account deletion for Mr. Sonny Dollente (pet1631) also in account deactivation in DMS, add Ivy IbaÃ±ez in DMS. | Done | admin.Joe Nico T. Geronimo
CSR-0630-19 | CSR | Christian F. Dipasupil | 2019-06-12 13:21:00 | 2019-06-17 07:15:00 | 2019-06-19 12:12:00 | HO | Transfer PC location | transfer CATIA Workstation with IP 10.49.4.199 from TSE Room to PRT work area for TANSHIN KOGYO Training. Must be approve by Sir Melvin Vera. For temporary use of Japanese visitor. | Closed | admin.Rommel Y. Bacus
QA-1203-19 | QA | Alvin B. Raposon | 2019-06-13 07:20:00 | 2019-06-13 07:20:00 | 2019-06-13 07:29:00 | HO |  | File transfer from SD card to file server | Closed | admin.Reymark B. Evangelista
QA-1204-19 | QA | Joan M. Fortuna | 2019-06-13 08:25:00 | 2019-06-13 08:25:00 | 2019-06-13 08:29:00 | HO |  | network assist | Closed | admin.Reymark B. Evangelista
QA-1205-19 | QA | Roda A. Dela Pena | 2019-06-13 08:31:00 | 2019-06-13 08:31:00 | 2019-06-13 08:39:00 | HO |  | Assist on BT reservation in aseana 2 | Closed | admin.Reymark B. Evangelista
QA-1206-19 | QA | Christian F. Dipasupil | 2019-06-13 09:00:00 | 2019-06-13 09:00:00 | 2019-06-13 09:04:00 | HO |  | Assist on Video Meeting room laptop set-up to remote his PC 3.96 | Closed | admin.Reymark B. Evangelista
QA-1207-19 | QA | Blinky Vasquez | 2019-06-13 10:30:00 | 2019-06-13 10:30:00 | 2019-06-13 10:35:00 | HO |  | Unable to print | Closed | admin.Joe Nico T. Geronimo
QA-1208-19 | QA | Danica D. Cultura | 2019-06-13 08:35:00 | 2019-06-13 08:35:00 | 2019-06-13 10:36:00 | HO |  | unable to use computer. do not proceed to log in screen | Closed | admin.Joe Nico T. Geronimo
CSR-0623-19 | CSR | Milamari Q. Isidoro | 2019-06-13 10:36:00 | 2019-06-24 21:00:00 | 2019-08-16 10:39:00 | HO | Access Request | 1. Update/ad the following (attached) access rights on QMS and KPM folders. 2. Set Read-only to files inside \\10.49.1.97\iso\QMS\Forms and \\10.49.1.97\iso\QMS\Documents under process\Documents Template to all users except Top management, Managers, pet0575, pet1698, pet6073. -- you may refer to CSR-0398-19 | Closed | admin.Joe Nico T. Geronimo
QA-1209-19 | QA | Michelle Anselle R. De los Santos | 2019-06-13 09:00:00 | 2019-06-13 09:00:00 | 2019-06-13 09:10:00 | HO |  | notepad ++ plugins | Closed | admin.Joe Nico T. Geronimo
QA-1210-19 | QA | Takashi Watanabe | 2019-06-13 11:00:00 | 2019-06-13 11:00:00 | 2019-06-13 11:06:00 | HO |  | assist YTMI personel to register email address via service now | Closed | admin.Reymark B. Evangelista
CSR-0624-19 | CSR | Joe Nico T. Geronimo | 2019-06-13 13:26:00 | 2019-06-14 21:00:00 | 2019-07-03 13:34:00 | HO | Hardware Purchase | purchase of mouse and keyboard for stock | Done | admin.Joe Nico T. Geronimo
DRR-0063-19 | DRR | Stephanie Shayne T. Cruz | 2019-06-13 13:58:00 | 2019-06-13 13:58:00 | 2019-06-17 10:28:00 | HO | Windows | 240179NT0A-030 (TR & PRE-ASSY);\\10.49.1.97\wh\NISSAN\NISSAN_YHV\2. SCANNED DRAWINGS\P42J\20MY\CONV\240179NT0A\030;Original Directory;No;Deleted the wrong file. | Done | admin.Joe Nico T. Geronimo
QA-1213-19 | QA | Melvin P. Vera | 2019-06-14 08:50:00 | 2019-06-14 08:50:00 | 2019-06-14 09:01:00 | HO |  | Assist guest to connect to WIFI | Closed | admin.Reymark B. Evangelista
QA-1214-19 | QA | Noel B. Cruz | 2019-06-14 09:33:00 | 2019-06-14 09:33:00 | 2019-06-14 09:40:00 | HO |  | Assist on confidential posting file upload | Closed | admin.Reymark B. Evangelista
CPR-0071-19 | CPR | Edgar R. Medina | 2019-06-14 14:12:00 | 2019-06-14 14:12:00 | 2019-06-17 10:27:00 | HO | Mouse | Mouse right click operation malfunctioning. | Done | admin.Reymark B. Evangelista
CSR-0638-19 | CSR | Jerome P. Tamayo | 2019-06-14 14:25:00 | 2019-06-17 21:00:00 | 2019-06-24 17:42:00 | HO | CAE Request | rename CAE files see attached | Done | admin.Greg Daniel E. Mojica
CSR-0633-19 | CSR | Marisol Cabacungan | 2019-06-14 14:31:00 | 2019-06-17 21:00:00 | 2019-06-19 08:39:00 | HO | Install Software | Light Up Installation | Done | admin.Joe Nico T. Geronimo