## Worksheet
HO September 2019
New Request | Assigned | Work in Progress | Done | Closed | Total
0 | 1 | 4 | 96 | 26 | 127
| Completed | On-going | Delay | Total Request | Completion % | On Time %
CSR | 95 | 0 | 5 | 100 | 95 | 94.74
CPR | 13 | 0 | 0 | 13 | N/A | N/A
DRR | 14 | 0 | 0 | 14 | N/A | N/A
Member | Assigned | Work in Progress | Done | Closed
admin.Aaron Jet N. Sarreal | 0 | 0 | 0 | 1
admin.Chester Jed T. Banez | 0 | 1 | 3 | 3
admin.Christ John Dela Cruz | 0 | 0 | 3 | 0
admin.Corazon A. Coronel | 0 | 0 | 1 | 1
admin.Greg Daniel E. Mojica | 0 | 1 | 1 | 1
admin.Jasper Labenia | 1 | 2 | 1 | 2
admin.Joe Nico T. Geronimo | 0 | 0 | 37 | 47
admin.Joel Jr. M. Chavez | 0 | 0 | 0 | 2
admin.John Christian Lovitos | 0 | 0 | 3 | 0
admin.Kiel Antaran | 0 | 0 | 0 | 2
admin.Patrick Robin Vinas | 0 | 0 | 0 | 1
admin.Reymark B. Evangelista | 0 | 0 | 40 | 40
admin.Rommel Y. Bacus | 0 | 0 | 5 | 5
admin.Willem R. Leonardo | 0 | 0 | 2 | 1
Reference # | Process | Requestor | Date Request | Date Needed | Date Done | Site | Category | Details | Status | Assigned to
CSR-1018-19 | CSR | Corazon A. Coronel | 2019-08-16 05:43:00 | 2019-08-19 21:00:00 | 2019-08-23 15:31:00 | HO | PC Configuration | Transfer PC of Patrick Vinas | Closed | admin.Jasper Labenia
DRR-0113-19 | DRR | Maria Cristina D. Sumaya | 2019-08-16 07:13:00 | 2019-08-16 07:13:00 | 2019-08-23 09:19:00 | HO | Cae | X31954-PZ24M#00#;\\10.49.1.97\cdd\CDE\01CDC Start 16 June\43T\CE19-PK-0274(190809);Original Directory;No;error data | Done | admin.Reymark B. Evangelista
CSR-1039-19 | CSR | Cristine B. Suarez | 2019-08-16 09:53:00 | 2019-08-19 21:00:00 | 2019-08-23 09:25:00 | HO | Transfer Software location | Transfer of Email account ( SUZUKI COMMON ) From 10.49.1.103 to 10.49.1.115 | Done | admin.Reymark B. Evangelista
CSR-1119-19 | CSR | Sharmaine T. Ingles | 2019-08-16 10:01:00 | 2019-08-27 21:00:00 | 2019-09-10 10:48:00 | HO | Account Request | Email Address Request for the following TCE members pet1675 Jeremeeh S. Ramuram Jr. Testing Evaluator pet1946 Bryan John B. Sabiano Jr. Testing Evaluator | Done | admin.Reymark B. Evangelista
CSR-1045-19 | CSR | Emmanuel Jr. C. Jimenez | 2019-08-16 11:28:00 | 2019-08-27 21:00:00 | 2019-10-15 07:27:00 | HO | Access Request | Request of modified access for 1. Ramona Chariz Amon (1187) - \\10.49.1.97\cdd\monthly\ISO 2. Dolli Vee Joy Haro (6016) - \\10.49.1.97\cdd\monthly\ISO 3. Jeannah Mae Tijam (6018) - \\10.49.1.97\cdd\monthly\ISO 4. Aubrey Esmas (1690) - \\10.49.1.97\cdd\monthly\SHE-WSR , in \\10.49.1.97\cdd\monthly folder | Closed | admin.Joe Nico T. Geronimo
CSR-1062-19 | CSR | Jaedicke C. Gaerlan | 2019-08-16 12:52:00 | 2019-08-27 21:00:00 | 2019-10-21 20:30:00 | HO | Access Request | Request to add "CE" root folder in the Document Management page, Root Folder of the Desknet NEO (DMS), Accessible by All CE members | Closed | admin.Willem R. Leonardo
QA-1505-19 | QA | John Robert I. Galvez | 2019-08-19 06:43:00 | 2019-08-19 06:43:00 | 2019-08-19 06:52:00 | HO |  | Install and set to default PDFxchange editor | Closed | admin.Reymark B. Evangelista
CPR-0122-19 | CPR | Christine K. Fang-asan | 2019-08-19 08:54:00 | 2019-08-19 08:54:00 | 2019-08-29 09:20:00 | HO | Mouse | Difficult to move | Done | admin.Reymark B. Evangelista
CSR-1147-19 | CSR | Franz Myka M. Dumlao | 2019-08-19 09:05:00 | 2019-08-20 21:00:00 | 2019-09-11 12:58:00 | HO | Transfer Telephone location | Changing of phone name of Loc. 755 - Dioza Mula Cruz to Franz Myka Dumlao | Done | admin.Reymark B. Evangelista
CPR-0121-19 | CPR | Rosselle Salinas | 2019-08-19 09:44:00 | 2019-08-19 09:44:00 | 2019-09-02 11:10:00 | HO | Keyboard | Deffective keyboard. | Done | admin.Joe Nico T. Geronimo
CSR-1035-19 | CSR | Kristine G. Boado | 2019-08-19 10:04:00 | 2019-08-20 21:00:00 | 2019-08-20 12:39:00 | HO | PC Configuration | Kindly set DPA Screensaver for ALL PET PC using attached file (powerpoint). Screensaver will run from Aug 19-23 as discussed on DPA meeting last 8/13. | Done | admin.Joe Nico T. Geronimo
DRR-0114-19 | DRR | Agridon D. Del Rosario | 2019-08-19 12:15:00 | 2019-08-19 12:15:00 | 2019-08-29 10:07:00 | HO | Cae | 201908 Data from SCT;\\10.49.1.97\cdd\CDE\01CDC Start 16 June\SCT\201908;Original Directory;No;Accidentally deleted | Done | admin.Reymark B. Evangelista
CSR-1143-19 | CSR | Marvin Andrew H. David | 2019-08-19 12:48:00 | 2019-08-20 21:00:00 | 2019-09-11 11:36:00 | HO | Outsources Request | PARTS MASTER REFRESH | Done | admin.John Christian Lovitos
CSR-1041-19 | CSR | Ann Gymverlyn O. Mendoza | 2019-08-19 14:18:00 | 2019-08-28 21:00:00 | 2019-08-28 06:53:00 | HO | Account Request | Request of email address 1. Rolando Fernandez Jr. | Done | admin.Reymark B. Evangelista
CSR-1036-19 | CSR | Cherrie-Lou G. Caasi | 2019-08-20 08:05:00 | 2019-08-21 21:00:00 | 2019-08-22 07:45:00 | HO | Borrow | Good morning. We need to borrow USB inorder to save our data for temperature rise test. We want to borrow USB no. 10 because it's the flashdrive that works, other USB that we tried didn't work last time. Thank you. | Done | admin.Reymark B. Evangelista
CSR-1081-19 | CSR | Eurie A. Bandian | 2019-08-20 08:27:00 | 2019-09-09 12:01:00 | 2019-09-12 07:06:00 | HO | Borrow | Borrow of laptop for CFR Activity in YTMI and EMI visit. From 08/28 to 09/4. | Done | admin.Joe Nico T. Geronimo
QA-1514-19 | QA | Vicente Z. Nieto | 2019-08-20 09:00:00 | 2019-08-20 09:00:00 | 2019-08-20 09:17:00 | HO |  | Connect guest to network | Closed | admin.Reymark B. Evangelista
QA-1515-19 | QA | Julie Anne T. Tud | 2019-08-20 10:30:00 | 2019-08-20 10:30:00 | 2019-08-20 10:39:00 | HO |  | Connect to colored printer connected to sir jaedicke | Closed | admin.Reymark B. Evangelista
CSR-1042-19 | CSR | Maria Josefa G. Samson | 2019-08-20 12:14:00 | 2019-08-23 21:00:00 | 2019-10-15 07:27:00 | HO | Backup Windows file/s | My email was always full. Need auto archive. | Closed | admin.Joe Nico T. Geronimo
QA-1516-19 | QA | Dominic S. Baylon | 2019-08-20 13:00:00 | 2019-08-20 13:00:00 | 2019-08-20 13:18:00 | HO |  | Connect to network in basbas san workplace | Closed | admin.Reymark B. Evangelista
CSR-1043-19 | CSR | Kristine G. Boado | 2019-08-20 13:22:00 | 2019-10-01 21:00:00 | 2019-11-26 08:08:00 | HO | Software Purchase | Request for Purchase 1. Microsoft Lync for Ann Gymverlyn Mendoza (Budget October 2019 - P1,500) To be use for coordinating the KPI Monitoring of JBRB HO/BO | Done | admin.Reymark B. Evangelista
CSR-1148-19 | CSR | Donn M. Carlos | 2019-08-20 13:40:00 | 2019-08-22 21:00:00 | 2019-09-16 21:17:00 | HO | Transfer PC location | Changes in WHD PC location | Closed | admin.Jasper Labenia
DRR-0143-19 | DRR | Axl Rose S. Landicho | 2019-08-20 13:54:00 | 2019-08-20 13:54:00 | 2019-11-19 18:38:00 | HO | Cae | PD_240149PS7A-01000.Modelroot MD_240149PS7A-01000.Modelroot AP_240149PS7A-01000.Modelroot;/export/home/eucoodb/model/work/NISSAN_YHV/P42K/RHD/20MY/240149PS7A/010;Original Directory;No;DATA LOSS | Closed | admin.Greg Daniel E. Mojica
CSR-1146-19 | CSR | Gretchen C. Magsino | 2019-08-20 15:25:00 | 2019-08-21 21:00:00 | 2019-09-12 10:57:00 | HO | Transfer Telephone location | Change the telephone name from Marilou Aquino to Gretchen Magsino | Done | admin.Joe Nico T. Geronimo
CSR-1055-19 | CSR | Redemptor C. Batiduan | 2019-08-20 15:24:00 | 2019-08-30 21:00:00 | 2019-10-08 14:03:00 | HO | Modify Software | Transfer the license server of Enovia DMU Navigator V5-6R2015 from MIS server to 10.49.5.138. Relink the Enovia DMU Navigator installed on the following PCs to the new location of license server mentioned above. 1) 10.49.5.119 2) 10.49.1.189 3) 10.49.1.234 4) 10.49.1.209 5) 10.49.3.96 6) 10.49.1.14 7) 10.49.1.161 8) 10.49.5.138 Prior to this request, I already informed Sir Rommel Bacus regarding this matter. | Closed | admin.Rommel Y. Bacus
DRR-0112-19 | DRR | Anabelle B. Albiola | 2019-08-20 16:07:00 | 2019-08-20 16:07:00 | 2019-08-23 15:26:00 | HO | Cae | R SIDE/0700A;/export/home/eucoodb/model/work/HONDA/TY2;Original Directory;No;As per Sir Phil's request | Closed | admin.Kiel Antaran
CSR-1044-19 | CSR | Donn M. Carlos | 2019-08-20 16:21:00 | 2019-08-22 21:00:00 | 2019-08-27 08:16:00 | HO | Modify Software | Change SRS Checker for Subaru group | Closed | admin.Aaron Jet N. Sarreal
CSR-1107-19 | CSR | Jayson L. Toding | 2019-08-20 17:08:00 | 2019-10-02 16:00:00 | 2019-10-02 11:41:00 | HO | Account Request | Request for Y-WEB search system. Jayson Toding and Roda dela Pena | Done | admin.Joe Nico T. Geronimo
QA-1520-19 | QA | Maria Josefa G. Samson | 2019-08-22 07:35:00 | 2019-08-22 07:35:00 | 2019-08-22 07:44:00 | HO |  | Beams log-in and guide how to change password base on manuals | Closed | admin.Reymark B. Evangelista
CPR-0120-19 | CPR | Marilou R. Aquino | 2019-08-22 07:44:00 | 2019-08-22 07:44:00 | 2019-11-05 14:51:00 | HO | PC Power Supply | For IP 10.49.2.110, CPU Fan Error during power on of PC. In addition, error when opening of power point file that are save in the network and e-mail attachment. See attachment. | Closed | admin.Rommel Y. Bacus
QA-1521-19 | QA | Keiji P. Takahashi | 2019-08-22 08:18:00 | 2019-08-22 08:18:00 | 2019-08-22 08:30:00 | HO |  | cannot log in to pc | Closed | admin.Joe Nico T. Geronimo
CSR-1050-19 | CSR | Corazon A. Coronel | 2019-08-22 08:20:00 | 2019-09-02 21:00:00 | 2019-08-30 06:39:00 | HO | Account Request | Access & Account Request of John Christian Lovitos *Lansweeper *admin account *DMS *File Servers | Done | admin.Reymark B. Evangelista
QA-1522-19 | QA | Danica D. Cultura | 2019-08-22 08:25:00 | 2019-08-22 08:25:00 | 2019-08-22 08:50:00 | HO |  | PC Boot loop due to driver missing | Closed | admin.Reymark B. Evangelista
QA-1523-19 | QA | Allan Edward A. Arabia | 2019-08-22 08:45:00 | 2019-08-22 08:45:00 | 2019-08-22 08:54:00 | HO |  | Assist in lync meeting | Closed | admin.Joe Nico T. Geronimo
CSR-1145-19 | CSR | Gretchen C. Magsino | 2019-08-22 09:17:00 | 2019-08-23 21:00:00 | 2019-09-17 10:41:00 | HO | Transfer Software location | Please transfer the LYNC of PC 10.49.2.116 to PC 10.49.2.225. | Done | admin.Joe Nico T. Geronimo
QA-1524-19 | QA | Michael Angelo H. Escalona | 2019-08-22 09:02:00 | 2019-08-22 09:02:00 | 2019-08-22 09:20:00 | HO |  | Connect guest to network | Closed | admin.Reymark B. Evangelista
QA-1525-19 | QA | Milamari Q. Isidoro | 2019-08-22 10:40:00 | 2019-08-22 10:40:00 | 2019-08-22 10:43:00 | HO |  | keyboard malfunctioning | Closed | admin.Joe Nico T. Geronimo
QA-1526-19 | QA | Janice O. Darjuan | 2019-08-22 10:35:00 | 2019-08-22 10:35:00 | 2019-08-22 10:46:00 | HO |  | outlook Archive assist ASAP | Closed | admin.Reymark B. Evangelista
QA-1527-19 | QA | Milamari Q. Isidoro | 2019-08-22 10:42:00 | 2019-08-22 10:42:00 | 2019-08-22 10:48:00 | HO |  | cannot connect projector | Closed | admin.Joe Nico T. Geronimo
QA-1528-19 | QA | Mariel R. Santos | 2019-08-22 10:50:00 | 2019-08-22 10:50:00 | 2019-08-22 10:59:00 | HO |  | change folder location for scan | Closed | admin.Joe Nico T. Geronimo
QA-1529-19 | QA | Nazarine John P. Gesalan | 2019-08-22 10:45:00 | 2019-08-22 10:45:00 | 2019-08-22 10:52:00 | HO |  | Check printer. as per report printer encountering Paper jam | Closed | admin.Reymark B. Evangelista
QA-1530-19 | QA | Emmanuel Jr. C. Jimenez | 2019-08-22 11:00:00 | 2019-08-22 11:00:00 | 2019-08-22 11:05:00 | HO |  | install total commander | Closed | admin.Reymark B. Evangelista
CPR-0117-19 | CPR | Reymark B. Evangelista | 2019-08-22 11:48:00 | 2019-08-22 10:00:00 | 2019-09-12 06:36:00 | HO | Printer/Plotter | Paper jam on tray 3&4 | Done | admin.Joe Nico T. Geronimo
CSR-1054-19 | CSR | Charito B. Canonizado | 2019-08-22 13:11:00 | 2019-08-23 13:11:00 | 2019-09-03 08:22:00 | HO | Backup to CD/DVD | Back-up of MC jobs files on DVD. File location \\10.49.1.97\emd\EMD1102\Resource Center\MC-Parts\MC Job Requests(79th term_January 2019) | Done | admin.Reymark B. Evangelista
QA-1531-19 | QA | Jordan Dale B. Caldo | 2019-08-22 13:50:00 | 2019-08-22 13:50:00 | 2019-08-22 13:59:00 | HO |  | remote connection | Closed | admin.Joe Nico T. Geronimo
QA-1532-19 | QA | Dominic S. Baylon | 2019-08-22 14:03:00 | 2019-08-22 14:03:00 | 2019-08-22 14:20:00 | HO |  | Installation of printer | Closed | admin.Joe Nico T. Geronimo
QA-1533-19 | QA | Jessica A. Benal | 2019-08-22 14:16:00 | 2019-08-22 14:16:00 | 2019-08-22 14:20:00 | HO |  | Assist user to print in colored plotter | Closed | admin.Joe Nico T. Geronimo
CSR-1065-19 | CSR | Ronalyn G. Imana | 2019-08-22 14:12:00 | 2019-09-02 21:00:00 | 2019-09-12 06:37:00 | HO | Account Request | 1. Request of account deletion, windows login, folder access, printer access and email, Seine, CMMS of the following resigned members Mr. Cristhian Jinayon (pet1587) Mr. Brian Dollente (pet0904) 2. Add the following members in DMS Mr. Adrian Cris Colago (pet6174) Mr. Amiel Gopiteo (pet6175) | Done | admin.Joe Nico T. Geronimo
QA-1534-19 | QA | Dominic S. Baylon | 2019-08-22 14:15:00 | 2019-08-22 14:15:00 | 2019-08-22 14:33:00 | HO |  | Connect and register in printer in TED | Closed | admin.Reymark B. Evangelista
QA-1535-19 | QA | Angelly P. Bagaloyos | 2019-08-22 15:10:00 | 2019-08-22 15:10:00 | 2019-08-22 15:18:00 | HO |  | User cannot print on printer | Closed | admin.Joe Nico T. Geronimo
CSR-1196-19 | CSR | Leo N. Retome | 2019-08-22 15:29:00 | 2019-11-08 08:18:00 | 2019-11-05 13:01:00 | HO | Borrow | Need extra monitor for the usage of LS-Dyna Software (remote desktop in Japan) (dual monitor) | Done | admin.Rommel Y. Bacus
QA-1536-19 | QA | Ernesto L. Basbas | 2019-08-23 08:15:00 | 2019-08-23 08:15:00 | 2019-08-23 08:28:00 | HO |  | no network and telephone connection | Closed | admin.Joe Nico T. Geronimo
QA-1537-19 | QA | Lucky Bien M. De Vera | 2019-08-23 07:00:00 | 2019-08-23 07:00:00 | 2019-08-23 07:15:00 | HO |  | delete other user profile in 2.25 | Closed | admin.Reymark B. Evangelista
QA-1538-19 | QA | Dominic S. Baylon | 2019-08-23 08:15:00 | 2019-08-23 08:15:00 | 2019-08-23 08:30:00 | HO |  | cannot log in to pc | Closed | admin.Joe Nico T. Geronimo
QA-1539-19 | QA | Dominic S. Baylon | 2019-08-23 08:15:00 | 2019-08-23 08:15:00 | 2019-08-23 08:30:00 | HO |  | cannot log in to pc | Closed | admin.Joe Nico T. Geronimo
QA-1540-19 | QA | Ma. Rebecca B. Pualon | 2019-08-23 07:40:00 | 2019-08-23 07:40:00 | 2019-08-23 07:45:00 | HO |  | Can't print on colored printer | Closed | admin.Reymark B. Evangelista
QA-1541-19 | QA | Noel B. Oafallas | 2019-08-23 08:33:00 | 2019-08-23 08:33:00 | 2019-08-23 08:38:00 | HO |  | Reservation in video conference room | Closed | admin.Joe Nico T. Geronimo
QA-1542-19 | QA | Vicente Z. Nieto | 2019-08-23 07:50:00 | 2019-08-23 07:50:00 | 2019-08-23 08:00:00 | HO |  | Connect guest to network | Closed | admin.Reymark B. Evangelista
QA-1543-19 | QA | Rosano A. Buerano | 2019-08-23 08:37:00 | 2019-08-23 08:37:00 | 2019-08-23 08:39:00 | HO |  | Cancellation of reservation on Video Con Room | Closed | admin.Joe Nico T. Geronimo
QA-1544-19 | QA | Ranilyn Rose M. Mernilo | 2019-08-23 08:40:00 | 2019-08-23 08:40:00 | 2019-08-23 08:48:00 | HO |  | user cannot log-in due to start-up repair | Closed | admin.Reymark B. Evangelista
QA-1545-19 | QA | Noime V Balleser | 2019-08-23 09:30:00 | 2019-08-23 09:30:00 | 2019-08-23 09:43:00 | HO |  | Register ID in pritner | Closed | admin.Joe Nico T. Geronimo
CSR-1051-19 | CSR | Rommel E. Aguilon | 2019-08-23 13:46:00 | 2019-09-03 21:00:00 | 2019-08-28 09:20:00 | HO | Account Request | please see attached file | Done | admin.Joe Nico T. Geronimo
CSR-1064-19 | CSR | Ronalyn G. Imana | 2019-08-23 14:21:00 | 2019-11-22 21:00:00 | 2020-01-02 12:24:00 | HO | Hardware Purchase | Request for IP Phone for Sir Ernesto Basbas (SCD-TQM) Use remaining budget from July-August. | Done | admin.Joe Nico T. Geronimo
CSR-1052-19 | CSR | Takashi Watanabe | 2019-08-23 15:11:00 | 2019-09-05 08:49:00 | 2019-10-15 07:26:00 | HO | Access Request | I would like to share our PET data of "Data Management for Visualization System" with Mr. Takeshi Sugiyama (YC ICT Division). Please register his account to folder permission of the following. \\10.49.1.97\common\â˜…â˜…YC EVP Mr. Watanabe Projectâ˜…â˜…\003. Data Management Access right --- Only read | Closed | admin.Joe Nico T. Geronimo
CPR-0144-19 | CPR | Katherine Q. Ronquillo | 2019-08-23 15:26:00 | 2019-11-26 08:32:00 | 2019-11-26 08:37:00 | HO | PC Harddisk | Please retain the following users for the C drive clean up. pet1399 and pet1529 Kindly delete all remaining users, I already asked for their permission. Thank you very much. | Done | admin.Reymark B. Evangelista
CPR-0119-19 | CPR | Joe Nico T. Geronimo | 2019-08-23 17:03:00 | 2019-08-23 17:03:00 | 2019-09-23 12:21:00 | HO | Printer/Plotter | fault error 062-392 | Done | admin.Joe Nico T. Geronimo
CSR-1067-19 | CSR | Grace A. Rivera | 2019-08-23 17:10:00 | 2019-09-17 13:12:00 | 2019-09-17 13:17:00 | HO | Borrow | Borrowed PC to MIS for Mr. Dominic Baylon in TE Dept. | Done | admin.Reymark B. Evangelista
QA-1553-19 | QA | Blinky Vasquez | 2019-08-27 07:00:00 | 2019-08-27 07:00:00 | 2019-08-27 07:15:00 | HO |  | register new regular id | Closed | admin.Reymark B. Evangelista
QA-1554-19 | QA | Gelli A. Merene | 2019-08-27 07:17:00 | 2019-08-27 07:17:00 | 2019-08-27 07:25:00 | HO |  | assistance on replacing of toner | Closed | admin.Reymark B. Evangelista
QA-1555-19 | QA | Rene Mark C. Duro | 2019-08-27 08:00:00 | 2019-08-27 08:00:00 | 2019-08-27 08:08:00 | HO |  | cannot log-in due to network problem | Closed | admin.Reymark B. Evangelista
CSR-1150-19 | CSR | Christopher P. Adit | 2019-08-27 08:42:00 | 2019-08-28 21:00:00 | 2019-09-11 11:37:00 | HO | Outsources Request | Refresh of Parts Master(Urgent). | Done | admin.John Christian Lovitos
QA-1556-19 | QA | Jeniline Trina M. Jamora | 2019-08-27 08:25:00 | 2019-08-27 08:25:00 | 2019-08-27 08:45:00 | HO |  | setup laptop in training room1,2 and meeting room5b | Closed | admin.Reymark B. Evangelista
QA-1557-19 | QA | April D. Dayapan | 2019-08-27 09:07:00 | 2019-08-27 09:07:00 | 2019-08-27 09:23:00 | HO |  | USB port not functioning well | Closed | admin.Reymark B. Evangelista
QA-1558-19 | QA | Rommel E. Aguilon | 2019-08-27 08:15:00 | 2019-08-27 08:15:00 | 2019-08-27 08:24:00 | HO |  | Set up windows log in for new employee | Closed | admin.Joe Nico T. Geronimo
QA-1559-19 | QA | Edgar Allan A. Beley | 2019-08-27 08:26:00 | 2019-08-27 08:26:00 | 2019-08-27 08:35:00 | HO |  | unable to print | Closed | admin.Joe Nico T. Geronimo
QA-1560-19 | QA | Ederlin M. Domingo | 2019-08-27 09:23:00 | 2019-08-27 09:23:00 | 2019-08-27 09:30:00 | HO |  | product activation failed | Closed | admin.Reymark B. Evangelista
QA-1561-19 | QA | Jave Rudy M. Velasco | 2019-08-27 10:12:00 | 2019-08-27 10:12:00 | 2019-08-27 10:14:00 | HO |  | transfer picture from camera to file server | Closed | admin.Joe Nico T. Geronimo
DRR-0121-19 | DRR | Anabelle B. Albiola | 2019-08-27 11:33:00 | 2019-08-27 11:33:00 | 2019-10-10 13:05:00 | HO | Cae | FLOOR;/export/home/eucoodb/model/work/HONDA/FEDW/FLOOR/0000A;Original Directory;No;for sending of MD Data | Closed | admin.Patrick Robin Vinas
CSR-1106-19 | CSR | Grace A. Rivera | 2019-08-27 12:53:00 | 2019-09-05 21:00:00 | 2019-09-03 07:29:00 | HO | Access Request | Request : access in EVD - EVC Shared Folder (10.49.1.97) for Mr. Edvin Pantoni (pet0499) and Mr. Joseph Pauly (pet0611) Date Needed - 8/27/2019 | Done | admin.Chester Jed T. Banez
DRR-0142-19 | DRR | Charmaine D.C. Dadua | 2019-08-27 11:36:00 | 2019-08-27 11:36:00 | 2019-11-11 08:36:00 | HO | Cae | MD_240511PA3A-0B000.ModelRoot MD_240521PA3A-0B000.ModelRoot MD_241679JE0A-00000.ModelRoot;export/home/eucoodb/model/work/NISSAN_YTMI/HARN BACK DOOR RH export/home/eucoodb/model/work/NISSAN_YTMI/HARN BACK DOOR LH export/home/eucoodb/model/work/NISSAN_YTMI/SUB HARNESS ASSY INVERTER;export/home/eucoodb/model/work/NISSAN_YTMI/X61F;No;CUSTOMER REQUEST OF CAE DATA. | Done | admin.Corazon A. Coronel
CSR-1080-19 | CSR | Fiona Cathrina L. Simbulan | 2019-08-27 14:26:00 | 2019-08-28 21:00:00 | 2019-08-29 15:57:00 | HO | Backup CAE file/s | Request for back-up of CAE files. Please refer to attached for details. | Done | admin.Christ John Dela Cruz
QA-1562-19 | QA | Noel B. Cruz | 2019-08-27 14:40:00 | 2019-08-27 14:40:00 | 2019-08-27 14:57:00 | HO |  | Assist user for Health and Awareness presentation | Closed | admin.Joe Nico T. Geronimo
QA-1563-19 | QA | Dominic S. Baylon | 2019-08-27 13:00:00 | 2019-08-27 13:00:00 | 2019-08-27 13:20:00 | HO |  | unable to login to pc | Closed | admin.Joe Nico T. Geronimo
QA-1564-19 | QA | Sarah Mae R. Bagis | 2019-08-27 15:00:00 | 2019-08-27 15:00:00 | 2019-08-27 15:10:00 | HO |  | assist for genba | Closed | admin.Joe Nico T. Geronimo
QA-1565-19 | QA | Sarah Mae R. Bagis | 2019-08-27 15:00:00 | 2019-08-27 15:00:00 | 2019-08-27 15:10:00 | HO |  | assist for genba | Closed | admin.Joe Nico T. Geronimo
CSR-1096-19 | CSR | Ma. Reina Monserrat A. Abalos | 2019-08-27 15:17:00 | 2019-08-28 21:00:00 | 2019-09-02 06:44:00 | HO | Install Software | INSTALL MS OUTLOOK FOR LYKA 10.49.2.32 FOR ECI PURPOSES | Done | admin.Joe Nico T. Geronimo
CSR-1095-19 | CSR | Marielle B. Esula | 2019-08-27 16:40:00 | 2019-08-28 21:00:00 | 2019-09-02 08:46:00 | HO | Add Internet Connection | To have an access on the internet for Benchmark research and investigation for Benchmark Japan CDC. | Done | admin.Joe Nico T. Geronimo
CSR-1068-19 | CSR | Rommel Y. Bacus | 2019-08-27 17:51:00 | 2019-08-28 21:00:00 | 2019-09-02 12:49:00 | HO | Software Purchase | Upgrade Catia Hotfix for TMC (TOYOTA) from HFX 124 to HFX 134. See attached file for all Catia Workstations to be upgraded. | Done | admin.Rommel Y. Bacus
QA-1566-19 | QA | Rosemarie M. Niere | 2019-08-28 08:36:00 | 2019-08-28 08:36:00 | 2019-08-28 08:46:00 | HO |  | Set Up default printer for ma'am Rose. | Closed | admin.Joe Nico T. Geronimo
QA-1567-19 | QA | Moises N. Fajardo | 2019-08-28 09:00:00 | 2019-08-28 09:00:00 | 2019-08-28 09:20:00 | HO |  | Lan disconnection | Closed | admin.Joe Nico T. Geronimo
CSR-1123-19 | CSR | Franz Myka M. Dumlao | 2019-08-28 08:52:00 | 2019-09-06 21:00:00 | 2019-09-19 09:58:00 | HO | Access Request | Add Franz Myka Dumlao in access (see attached sheet). | Closed | admin.Joe Nico T. Geronimo
CSR-1092-19 | CSR | Ma. Filipina G. Del Rosario | 2019-08-28 08:47:00 | 2019-09-06 21:00:00 | 2019-09-19 06:56:00 | HO | Account Request | Request for windows Login, CMMS, SEINE2, CDD Archive 2/â‘ PERSONAL, PET1097/Favorites, & PET1097/Job Monitoring for CON member Emerson P. Molina. | Done | admin.Joe Nico T. Geronimo
QA-1568-19 | QA | Archie Anthony Huevos | 2019-08-28 09:10:00 | 2019-08-28 09:10:00 | 2019-08-28 09:15:00 | HO |  | Set up lync and outlook | Closed | admin.Joe Nico T. Geronimo
QA-1569-19 | QA | Danevie Alvarez | 2019-08-28 09:25:00 | 2019-08-28 09:25:00 | 2019-08-28 09:30:00 | HO |  | set up lync and outlook | Closed | admin.Joe Nico T. Geronimo
QA-1570-19 | QA | Harold B. Balanay | 2019-08-28 09:35:00 | 2019-08-28 09:35:00 | 2019-08-28 09:42:00 | HO |  | need access to remote PC | Closed | admin.Reymark B. Evangelista
CSR-1069-19 | CSR | Analy B. Babatio | 2019-08-28 10:01:00 | 2019-08-29 21:00:00 | 2019-08-28 10:16:00 | HO | Install Software | Download music for wellness | Done | admin.Joe Nico T. Geronimo
CSR-1079-19 | CSR | Jovielet B. Caintoy | 2019-08-28 09:51:00 | 2019-09-06 21:00:00 | 2019-09-10 13:09:00 | HO | Account Request | Delete windows log-in and Seine 2 account Angelly Bagaloyos Elfren Bacinillo Rechelle Alegar | Done | admin.Reymark B. Evangelista
DRR-0117-19 | DRR | Ariel V. Almira | 2019-08-28 10:01:00 | 2019-08-28 10:01:00 | 2019-08-30 07:19:00 | HO | Cae | (1) ã¯ã‚åˆã„;Z:\201909\CE19-PK-C058(190806)\â‘§WORKING DATA\DESIGN STUDY\(1) ã¯ã‚åˆã„;Original Directory;No;ERROR 2D DRAWING | Done | admin.Reymark B. Evangelista
DRR-0141-19 | DRR | Axl Rose S. Landicho | 2019-08-28 10:33:00 | 2019-08-28 10:33:00 | 2019-11-11 14:42:00 | HO | Cae | PD_240339NF0A-03000.Modelroot PD_240339NF0B-03000.Modelroot;/export/home/eucoodb/model/repository/NISSAN_YHV/P42J/16MY/240339NF0A /export/home/eucoodb/model/repository/NISSAN_YHV/P42J/16MY/240339NF0B;Original Directory;No;Data Retrieval | Closed | admin.Corazon A. Coronel
CSR-1105-19 | CSR | Grace A. Rivera | 2019-08-28 10:42:00 | 2019-09-06 21:00:00 | 2019-09-09 09:14:00 | HO | Access Request | Request: Windows Log-in, Access in EV Folder (pls. see attached file for the list) and Printer for New Employee in EV Dept. Ms. Ayen G. Panganiban - 2033 | Done | admin.Reymark B. Evangelista
CSR-1077-19 | CSR | Chester Jed T. Banez | 2019-08-28 11:03:00 | 2019-08-29 21:00:00 | 2019-10-09 08:10:00 | HO | Add Internet Connection | allow https://drive.google.com/ as per request of our Directory (Takashi Matsui) purpose of this YC used online storage and the service provider of the storage is google Drive | Closed | admin.Chester Jed T. Banez
CSR-1094-19 | CSR | Aubrey P. Esmas | 2019-08-28 12:21:00 | 2019-08-29 21:00:00 | 2019-09-19 09:56:00 | HO | Add Internet Connection | To have an access on the internet for benchmark research and investigation for benchmark japan CDC. | Closed | admin.Joe Nico T. Geronimo
CSR-1093-19 | CSR | Rodelio Jr. A. Perin | 2019-08-28 12:22:00 | 2019-08-29 21:00:00 | 2019-09-19 09:55:00 | HO | Add Internet Connection | To have an access on the internet for benchmark research and investigation for benchmark japan CDC. | Closed | admin.Joe Nico T. Geronimo
CSR-1070-19 | CSR | Ruby A. Maghilum | 2019-08-28 12:29:00 | 2019-08-29 21:00:00 | 2019-09-17 13:18:00 | HO | Access Request | 1.Request to save file in \\10.49.1.97\common\â˜…â˜…YC EVP Mr. Watanabe Projectâ˜…â˜…\000.KPI with file name 79th term Vehicle Program KPIs.xlsx (see attached for details) 2. Set Access Right for the file Vehicle Program KPIs.xlsx (see attached for details) | Done | admin.Reymark B. Evangelista
QA-1573-19 | QA | Jennifer V. Chua | 2019-08-28 13:55:00 | 2019-08-28 13:55:00 | 2019-08-28 14:04:00 | HO |  | CMMS cannot log-in 1720&1903 | Closed | admin.Reymark B. Evangelista
QA-1574-19 | QA | Jose V. Samson | 2019-08-28 15:10:00 | 2019-08-28 15:10:00 | 2019-08-28 15:21:00 | HO |  | PC not working after restart & something blinking sound | Closed | admin.Reymark B. Evangelista
CSR-1075-19 | CSR | Jean Michelle P. Andoy | 2019-08-28 15:35:00 | 2019-11-27 21:00:00 | 2019-12-17 13:16:00 | HO | Hardware Purchase | Replacement of PABX battery | Done | admin.Joe Nico T. Geronimo
CSR-1078-19 | CSR | Jovielet B. Caintoy | 2019-08-28 16:20:00 | 2019-10-04 09:52:00 | 2019-10-03 09:53:00 | HO | Access Request | Request for folder access control See attached file | Done | admin.Reymark B. Evangelista
QA-1576-19 | QA | Edgardo Jr. O. Oracion | 2019-08-29 07:00:00 | 2019-08-29 07:00:00 | 2019-08-29 07:05:00 | HO |  | Add remote access to 2.212 | Closed | admin.Reymark B. Evangelista
QA-1577-19 | QA | Rafael Christian R. Escarcha | 2019-08-29 07:12:00 | 2019-08-29 07:12:00 | 2019-08-29 07:30:00 | HO |  | register regular ID to Printer | Closed | admin.Reymark B. Evangelista
CSR-1109-19 | CSR | Jovielet B. Caintoy | 2019-08-29 09:06:00 | 2019-10-04 09:55:00 | 2019-10-03 09:56:00 | HO | Access Request | Request for folder access right see attached file. | Done | admin.Reymark B. Evangelista
CSR-1185-19 | CSR | Sharmaine T. Ingles | 2019-08-29 09:03:00 | 2019-08-30 21:00:00 | 2019-10-08 13:52:00 | HO | Transfer Telephone location | Please only change the names of the following Local Numbers local 546 - Mr. John Elly Javier change to - Mr. Jaedicke Gaerlan local 510 - CE COMMON 2 change to - Julie / Joan local 509 - CE COMMON 1 change to - Loraine / Elly local 529 - Mr. Ernesto Basbas change to - Mr. Dominic Baylon | Closed | admin.Rommel Y. Bacus
DRR-0125-19 | DRR | Jim Mark O. Barot | 2019-08-29 09:36:00 | 2019-08-29 09:36:00 | 2019-09-19 12:52:00 | HO | Cae | PD_PET-821540A030K-00000 DP_PET-821540A030K-00000 MD_PET-821540A030K-00000-G AP_PET-821540A030K-00000;SEE ATTACHED FILE;SEE ATTACHED FILE OR SAME LOCATION;No;MISSING DATA WITH NEW JOB REQUEST | Done | admin.Greg Daniel E. Mojica
QA-1579-19 | QA | Edgardo Jr. O. Oracion | 2019-08-29 09:40:00 | 2019-08-29 09:40:00 | 2019-08-29 09:56:00 | HO |  | Add remote access to sir Edgardo | Closed | admin.Reymark B. Evangelista
QA-1580-19 | QA | Aumer A. Velasquez | 2019-08-29 09:56:00 | 2019-08-29 09:56:00 | 2019-08-29 09:59:00 | HO |  | Support in SIENNE2 error | Closed | admin.Reymark B. Evangelista
CSR-1108-19 | CSR | Jean Michelle P. Andoy | 2019-08-29 10:57:00 | 2019-10-10 21:00:00 | 2020-01-06 06:47:00 | HO | Renewal License | Renewal of polycom maintenace with serial number of 8211420E7230CN for Asena 1 | Done | admin.Joe Nico T. Geronimo
CSR-1101-19 | CSR | Jean Michelle P. Andoy | 2019-08-29 10:58:00 | 2019-10-10 21:00:00 | 2019-11-26 08:16:00 | HO | Renewal License | Renewal of Netapp licenses October 1, 2019 to September 30, 2020 for serial numbers 451636000129 451636000130 | Done | admin.Reymark B. Evangelista
CSR-1100-19 | CSR | Jean Michelle P. Andoy | 2019-08-29 11:05:00 | 2019-10-10 21:00:00 | 2020-01-02 06:52:00 | HO | Renewal License | Renewal of Asset tagging System. | Done | admin.Joe Nico T. Geronimo
CSR-1104-19 | CSR | Ronalyn G. Imana | 2019-08-29 11:10:00 | 2019-09-09 21:00:00 | 2019-10-07 10:24:00 | HO | Access Request | Rectifying folder access to the following: (The attachment is the list of EI members per group) \\10.49.1.97\EI Archive\Hardware - to all Hardware members \\10.49.1.97\EI Archive\Mechanical - to all Mechanical members \\10.49.1.97\EI Archive\Software - to all Software members (SCD Staffs must have NO access in EI Archive) | Work in Progress | admin.Chester Jed T. Banez
CSR-1103-19 | CSR | Ronalyn G. Imana | 2019-08-29 12:36:00 | 2019-09-09 21:00:00 | 2019-09-13 14:31:00 | HO | Access Request | Remove access of Hardware group in the following folders \\10.49.1.97\ei\31 ECIâ†’PET\ECIâ†’PET(BM) \\10.49.1.97\ei\32 PETâ†’ECI\PETâ†’ECI(BM) Hardware members 1047 Rosano Buerano 1442 Mark John Tiongson 1561 Ralph Anthony Calubaquib 1629 Almar Abner Q. Cenizal 1633 Brian M. Sarmiento 6063 Rodas, Rutchard Jhon C. 6065 Tejada, Jenielyn B. 1893 Canilanza , Gabriel Dominic H. 1984 Balleser, Noime V. 6174 Colago, Adrian Cris 6176 Lima, Lenard O. 6177 Ta-asan, Roylin L. 6191 Daryll M. Alorro | Done | admin.Chester Jed T. Banez
CSR-1102-19 | CSR | Grace A. Rivera | 2019-08-29 13:55:00 | 2019-09-09 21:00:00 | 2019-09-20 12:22:00 | HO | Account Request | Kindly update the email address and telephone no. of EV in PET INTRANET. Please see attached file for the details. | Done | admin.Willem R. Leonardo
CPR-0127-19 | CPR | Annabelle Rose E. Gallegos | 2019-08-29 14:16:00 | 2019-08-29 14:16:00 | 2019-09-12 11:50:00 | HO | Keyboard | keyboard deffect | Done | admin.Joe Nico T. Geronimo
CSR-1128-19 | CSR | May Angely A. Ramos | 2019-08-29 14:32:00 | 2019-09-09 21:00:00 | 2019-09-17 13:20:00 | HO | Access Request | \\10.49.1.97\eed\EED_Hardisk 5S\IVS_BMC\03_IVS (new employee) | Done | admin.Reymark B. Evangelista
QA-1581-19 | QA | Abigail E. Salas | 2019-08-29 14:10:00 | 2019-08-29 14:10:00 | 2019-08-29 14:35:00 | HO |  | Check oce paper did not feed | Closed | admin.Reymark B. Evangelista
QA-1582-19 | QA | Rens Nicko M. Santos | 2019-08-29 15:45:00 | 2019-08-29 15:45:00 | 2019-08-29 15:53:00 | HO |  | Set up jammasheet | Closed | admin.Joe Nico T. Geronimo
CPR-0123-19 | CPR | Joe Nico T. Geronimo | 2019-08-29 16:26:00 | 2019-08-29 16:26:00 | 2019-09-09 07:19:00 | HO | Printer/Plotter | oce colorwave problem | Done | admin.Joe Nico T. Geronimo
QA-1583-19 | QA | Darren F. Eugenio | 2019-08-30 07:00:00 | 2019-08-30 07:00:00 | 2019-08-30 07:05:00 | HO |  | support in video conference room | Closed | admin.Reymark B. Evangelista
QA-1584-19 | QA | Reynan Jr. D. Torrecampo | 2019-08-30 07:08:00 | 2019-08-30 07:08:00 | 2019-08-30 07:16:00 | HO |  | MS office activation of license | Closed | admin.Reymark B. Evangelista
CPR-0124-19 | CPR | Reymark B. Evangelista | 2019-08-30 07:24:00 | 2019-08-30 07:30:00 | 2019-08-30 07:46:00 | HO | Mouse | Mouse left click not functioning well | Done | admin.Reymark B. Evangelista
QA-1585-19 | QA | Jeniline Trina M. Jamora | 2019-08-30 09:00:00 | 2019-08-30 09:00:00 | 2019-08-30 09:04:00 | HO |  | Support in LMS via remote | Closed | admin.Reymark B. Evangelista
CSR-1131-19 | CSR | Anna Liza E. Ilusorio | 2019-08-30 09:30:00 | 2019-12-10 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | 2 desktop PC for replacement of BORROWED PC to MIS (July budget on Engineering) 2 MS office professional IP address 10.49.1.57 and 10.49.1.67 pls see attached budget and PC layout | Work in Progress | admin.Jasper Labenia
CSR-1134-19 | CSR | Roner B. Paguirigan | 2019-08-30 09:13:00 | 2019-09-10 21:00:00 | 2019-09-12 10:52:00 | HO | Access Request | access to MS PTM forlder for checking of input of sales and productivity | Done | admin.Joe Nico T. Geronimo
CSR-1135-19 | CSR | Roner B. Paguirigan | 2019-08-30 14:47:00 | 2019-09-10 21:00:00 | 2019-09-12 08:26:00 | HO | Access Request | access to MS PTM folder for checking of input of WHE sales and productivity | Done | admin.Joe Nico T. Geronimo
DRR-0119-19 | DRR | Jennygene P. Toding | 2019-08-30 14:27:00 | 2019-08-30 14:27:00 | 2019-09-17 12:22:00 | HO | Windows | Corrective Preventive Action Plan Control List - 79th Term;\\10.49.1.97\wh\COMMON\QUALITY\COUNTERMEASURE\CONTROL LISTS\NEW CONTROL LIST;Original Directory;No;Kindly recover excel file "Corrective Preventive Action Plan Control List - 79th Term" dated 08/26 or 08/27 or 08/28. We have to compare some details with the latest file. | Done | admin.Willem R. Leonardo
CSR-1111-19 | CSR | Jovielet B. Caintoy | 2019-08-30 16:02:00 | 2019-09-10 21:00:00 | 2019-09-03 16:24:00 | HO | Access Request | Additional access right for Dioza Mula Cruz | Done | admin.Reymark B. Evangelista
CPR-0130-19 | CPR | Patrick B. Martinez | 2019-09-02 06:41:00 | 2019-09-02 06:41:00 | 2019-09-23 09:46:00 | HO | Mouse | Mouse double clicking although single click was done. | Done | admin.Reymark B. Evangelista
QA-1590-19 | QA | Emerson Simon V. Prado | 2019-09-02 06:40:00 | 2019-09-02 06:40:00 | 2019-09-02 06:45:00 | HO |  | activate office | Closed | admin.Joe Nico T. Geronimo
QA-1591-19 | QA | Elaine D. Italia | 2019-09-02 06:45:00 | 2019-09-02 06:45:00 | 2019-09-02 06:50:00 | HO |  | activate office | Closed | admin.Joe Nico T. Geronimo
QA-1592-19 | QA | Jerico C. Cando | 2019-09-02 06:55:00 | 2019-09-02 06:55:00 | 2019-09-02 07:00:00 | HO |  | activate office | Closed | admin.Joe Nico T. Geronimo
QA-1593-19 | QA | Ederlin M. Domingo | 2019-09-02 07:10:00 | 2019-09-02 07:10:00 | 2019-09-02 07:15:00 | HO |  | activate office | Closed | admin.Joe Nico T. Geronimo
QA-1594-19 | QA | Emerson Simon V. Prado | 2019-09-02 07:15:00 | 2019-09-02 07:15:00 | 2019-09-02 07:33:00 | HO |  | Problem in solidworks | Closed | admin.Chester Jed T. Banez
QA-1595-19 | QA | Joan M. Fortuna | 2019-09-02 08:10:00 | 2019-09-02 08:10:00 | 2019-09-02 08:19:00 | HO |  | set up lms | Closed | admin.Joe Nico T. Geronimo
CPR-0135-19 | CPR | John Elly C. Javier | 2019-09-02 08:24:00 | 2019-09-27 12:54:00 | 2019-09-27 12:55:00 | HO | Keyboard | I would like to request to replace the keyboard that I'm using, was wet due to air-condition leak. | Done | admin.Reymark B. Evangelista
QA-1596-19 | QA | Aubrey P. Esmas | 2019-09-02 08:25:00 | 2019-09-02 08:25:00 | 2019-09-02 08:31:00 | HO |  | transfer picture camera to File server | Closed | admin.Joe Nico T. Geronimo
CSR-1122-19 | CSR | Bryan Mar R. Alvarez | 2019-09-02 09:17:00 | 2019-09-03 21:00:00 | 2019-09-23 10:09:00 | HO | Install Software | please install light up needed for comparison of drawing | Done | admin.Reymark B. Evangelista
CSR-1175-19 | CSR | Mario Carlo J. Dizon | 2019-09-02 09:52:00 | 2019-09-11 21:00:00 | 2019-09-19 10:09:00 | HO | Add Internet Connection | Need a full access on https://www.a2mac1.com. Purpose, CDC YC needs us to investigate for benchmarking of a certain OEM components using this site. | Done | admin.Joe Nico T. Geronimo
CSR-1133-19 | CSR | Belinda C. Cabico | 2019-09-02 10:01:00 | 2019-09-11 21:00:00 | 2019-10-15 07:26:00 | HO | Access Request | Modify Access Right of Bautista, Francis Ryan (2000). He can access the following folder Head Office - HBU, MBU, SUBARU Branch Office - HBU, SUBARU | Closed | admin.Joe Nico T. Geronimo
CSR-1140-19 | CSR | Alster James J. Callo | 2019-09-02 10:55:00 | 2019-09-11 21:00:00 | 2019-09-12 08:23:00 | HO | Access Request | BO access (WHE-HBU) | Done | admin.Joe Nico T. Geronimo
QA-1605-19 | QA | Kimberson M. Reyes | 2019-09-02 10:45:00 | 2019-09-02 10:45:00 | 2019-09-02 10:55:00 | HO |  | Register new ID in printer | Closed | admin.Reymark B. Evangelista
CSR-1129-19 | CSR | Vicente Z. Nieto | 2019-09-02 12:25:00 | 2019-09-11 21:00:00 | 2019-09-19 08:29:00 | HO | Account Request | Delete the account of resigned employee and additional of account request for (old employee) Mark Joseph Asis and Vicente Nieto. | Done | admin.Reymark B. Evangelista
CSR-1136-19 | CSR | Belinda C. Cabico | 2019-09-02 13:22:00 | 2019-09-11 21:00:00 | 2019-10-15 07:26:00 | HO | Access Request | Request access for Ms. Jennygene Toding(1248) for WHE Record monitoring Purposes. \\10.49.1.97\eed\EDS (Non Sales) | Closed | admin.Joe Nico T. Geronimo
CSR-1137-19 | CSR | Vicente Z. Nieto | 2019-09-02 14:52:00 | 2019-09-11 21:00:00 | 2019-09-17 15:14:00 | HO | Account Request | Deletion of Design Source Web etc of resigned employee | Done | admin.Joe Nico T. Geronimo
CSR-1118-19 | CSR | Jovielet B. Caintoy | 2019-09-02 14:41:00 | 2019-09-11 21:00:00 | 2019-09-09 07:58:00 | HO | Access Request | Delete Access right of Cris Myla Orandain in Suzuki group. | Closed | admin.Joe Nico T. Geronimo
CSR-1139-19 | CSR | May Angely A. Ramos | 2019-09-02 15:18:00 | 2019-09-11 21:00:00 | 2019-09-09 09:44:00 | HO | Account Request | New employee | Done | admin.Reymark B. Evangelista
CSR-1117-19 | CSR | Jovielet B. Caintoy | 2019-09-02 16:23:00 | 2019-09-11 21:00:00 | 2019-10-10 07:54:00 | HO | Access Request | Request for additional access right. See attached file. Please restrict HINO Folders in all members in the attached file only. | Done | admin.Chester Jed T. Banez
CSR-1116-19 | CSR | Jayson L. Toding | 2019-09-02 17:00:00 | 2019-09-16 07:07:00 | 2019-09-12 12:11:00 | HO | Transfer Software location | Please transfer the KD viewer application from IP add 10.49.3.64(SUBARU) to IP address 10.49.3.24(TOYOTA) | Done | admin.Joe Nico T. Geronimo
CSR-1115-19 | CSR | Sharmaine T. Ingles | 2019-09-03 08:35:00 | 2019-09-12 21:00:00 | 2019-09-10 08:16:00 | HO | Account Request | Windows Log In of TCE New Employee Testing Machine Operator (TCE) 1. Jeric B. Segurola- ID No. 2035 | Done | admin.Reymark B. Evangelista
CPR-0129-19 | CPR | Czarina D. Soliven | 2019-09-03 08:58:00 | 2019-09-03 08:58:00 | 2019-09-23 09:40:00 | HO | Mouse | Mouse when clicked has different execution against commanded. It does not work efficiently. | Done | admin.Reymark B. Evangelista
CSR-1152-19 | CSR | Carolyn B. EspeÃ±a | 2019-09-03 10:40:00 | 2019-09-04 21:00:00 | 2019-09-11 14:43:00 | HO | Outsources Request | PLEASE REFRESH TAB007, SYM113 | Done | admin.John Christian Lovitos
CSR-1114-19 | CSR | Juvelyn S. Ambrocio | 2019-09-03 10:51:00 | 2019-10-07 07:05:00 | 2019-10-22 09:24:00 | HO | Borrow | To borrow Laptop for JP Business Trip (9/7/2019 - 9/29/2019) | Done | admin.Joe Nico T. Geronimo
CSR-1190-19 | CSR | Ann Gymverlyn O. Mendoza | 2019-09-03 10:59:00 | 2019-12-03 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | Purchase of 3 Solidworks Workstation for JBRB (HO) | Work in Progress | admin.Jasper Labenia
CSR-1130-19 | CSR | Marilou P. De Luna | 2019-09-03 10:41:00 | 2019-12-03 21:00:00 | 0000-00-00 00:00:00 | HO | Hardware Purchase | 10.49.1.197 and 10.49.2.149 (Ford/Chrysler) PC replacement (per WHD3 79th Term Budget Plan on Engineering Cost for the month of Aug and Sept) | Assigned | admin.Jasper Labenia
CSR-1149-19 | CSR | Donn M. Carlos | 2019-09-03 13:37:00 | 2019-10-15 21:00:00 | 2019-11-18 15:07:00 | HO | Renewal License | Cadra renewal 10.49.1.88 (Honda) 10.49.2.148 (Honda) 10.49.3.64 (Subaru) | Closed | admin.Kiel Antaran
CSR-1113-19 | CSR | Sherwin M. Burgos | 2019-09-03 13:39:00 | 2019-09-04 21:00:00 | 2019-09-04 10:28:00 | HO | Install Software | Screen Recorder To record video on screen activity(Test Report Making) for QCC purpose. | Done | admin.Joe Nico T. Geronimo
CSR-1112-19 | CSR | Jovielet B. Caintoy | 2019-09-03 16:45:00 | 2019-09-12 21:00:00 | 2019-09-11 13:15:00 | HO | Account Request | Delete windows log in of resigned employee 1. Leopoldo Jr. Rollon 2.Lalaine Joy Vispo | Done | admin.Reymark B. Evangelista
QA-1607-19 | QA | Patrick B. Martinez | 2019-09-04 07:30:00 | 2019-09-04 07:30:00 | 2019-09-04 07:37:00 | HO |  | activate office | Closed | admin.Joe Nico T. Geronimo
QA-1608-19 | QA | John Robert I. Galvez | 2019-09-04 07:38:00 | 2019-09-04 07:38:00 | 2019-09-04 07:50:00 | HO |  | unable to print | Closed | admin.Joe Nico T. Geronimo
QA-1609-19 | QA | Judelyn E. Rosales | 2019-09-04 07:59:00 | 2019-09-04 07:59:00 | 2019-09-04 08:10:00 | HO |  | problem with outlook. | Closed | admin.Joe Nico T. Geronimo
DRR-0120-19 | DRR | Cristina Marie Pasion | 2019-09-04 10:14:00 | 2019-09-04 10:14:00 | 2019-09-10 06:54:00 | HO | Cae | PD_86102-8541B071-0U011.ModelRoot MD_86102-8541B071-0U011.ModelRoot;/export/home/eucoodb/model/work/MITSU/V80;Original Directory;No;Recovery of reference data. Urgent. | Done | admin.Christ John Dela Cruz
CSR-1132-19 | CSR | Redemptor C. Batiduan | 2019-09-04 16:53:00 | 2019-10-16 21:00:00 | 2020-01-08 08:55:00 | HO | Renewal License | Request for renewal of KSWAD license. | Done | admin.Joe Nico T. Geronimo
CSR-1124-19 | CSR | Rommel Y. Bacus | 2019-09-04 18:51:00 | 2019-09-13 21:00:00 | 2019-09-30 13:21:00 | HO | Access Request | Give folder access right temporarily until September 11, 2019. This is for viewing only or as read only. Path \\10.49.1.97\admin\ARCHIVE\Supplier 1. Johanna Marie Dandan 2. Ronalyn Imana | Done | admin.Rommel Y. Bacus
CSR-1125-19 | CSR | Jovielet B. Caintoy | 2019-09-05 08:21:00 | 2019-09-16 21:00:00 | 2019-09-23 10:07:00 | HO | Access Request | Delete folder access right. See attached file | Done | admin.Reymark B. Evangelista
CSR-1120-19 | CSR | Jennygene P. Toding | 2019-09-05 09:27:00 | 2019-09-16 21:00:00 | 2019-09-13 14:36:00 | HO | Access Request | Request to access \\10.49.1.97\tdc\Investment_Plan-è¨­å‚™æŠ•è³‡è¨ˆç”»ã‚·ã‚¹ãƒ†ãƒ é–¢ä¿‚\Investment_Budget_Sheet\CIP-2019\79-83term_5years_Investment_Budget_Sheet_Head Office_20190321_All.xlsx | Closed | admin.Chester Jed T. Banez
QA-1623-19 | QA | Erika Joyce C. Santiago | 2019-09-06 08:04:00 | 2019-09-06 08:04:00 | 2019-09-06 08:10:00 | HO |  | unlock password in Active directory | Closed | admin.Reymark B. Evangelista
CSR-1163-19 | CSR | Charlie M. Zulueta | 2019-09-06 08:35:00 | 2019-10-03 10:12:00 | 2019-10-03 10:13:00 | HO | Backup to CD/DVD | Cd burn \\10.49.1.97\eed\EED_Hardisk 5S\HBU\HBU 77FY\01_HBUç¬¬ä¸€è¨­è¨ˆ\SCL | Done | admin.Joe Nico T. Geronimo
DRR-0123-19 | DRR | Lariza R. Calara | 2019-09-06 09:16:00 | 2019-09-06 09:16:00 | 2019-09-19 09:53:00 | HO | Windows | F-MIS-006 rev. 2 F-MIS-007 rev. 1 F-MIS-009 rev. 2;\\10.49.1.97\iso\QMS\Obsolete Documents\Forms\Management Information System;Original Directory;No;to recover accidentally deleted files | Closed | admin.Joe Nico T. Geronimo
DRR-0122-19 | DRR | Raffy P. Ubaldo | 2019-09-06 11:34:00 | 2019-09-05 11:33:00 | 2019-09-11 09:52:00 | HO | Cae | TLAA644-44C EDIT;\\10.49.1.97\wh\HONDA\MAXTOR\SCANNED DRAWINGS\TLA\32117TLAZZ29YHV-2902C\CADRA\9-04;Original Directory;No;accidentally deleted file. | Done | admin.Joe Nico T. Geronimo
CSR-1177-19 | CSR | Rafael S. Fontenuela | 2019-09-06 12:57:00 | 2019-09-09 21:00:00 | 2019-09-30 14:07:00 | HO | PC Configuration | Need to configure to access the ANSYS Global blanket license. | Closed | admin.Rommel Y. Bacus
QA-1629-19 | QA | Patrick B. Martinez | 2019-09-09 07:00:00 | 2019-09-09 07:00:00 | 2019-09-09 07:35:00 | HO |  | Fix EV Branch storage Quota problem | Closed | admin.Joel Jr. M. Chavez
CSR-1187-19 | CSR | John Elly C. Javier | 2019-09-09 08:52:00 | 2019-09-10 08:52:00 | 2019-09-23 20:57:00 | HO | Transfer Telephone location | Would like to request to update the location of telephone locals and names of user. Please check red text on the attached for detail. | Done | admin.Rommel Y. Bacus
CSR-1186-19 | CSR | Grace A. Rivera | 2019-09-09 10:26:00 | 2019-12-09 21:00:00 | 2019-11-26 08:39:00 | HO | Hardware Purchase | Kindly purchased the following item - Jabra Speaker 1 pc - Jabra Headset 1 pc For BOX and CON (Job Coordination-Aug. Budget) - Desktop for replacement 2 pcs For Replacement of 10.49.1.235 and 10.49.1.144 - Aug. Budget - Samsung 1TB 860 EVO SSD Data 1 pc For Existing Workstation w/o SSD - Nov. Budget | Done | admin.Reymark B. Evangelista
CSR-1183-19 | CSR | Grace A. Rivera | 2019-09-09 10:33:00 | 2019-10-21 21:00:00 | 2020-01-02 06:51:00 | HO | Software Purchase | Kindly purchased the following items - Lync System-SkypefBus Dev SL 2 pcs. For Box and Con (job coordination from HO to BO-Sept. Budget) - Acrobat Standard 5 pcs. For Edvin, Jae, Alex, Gami Joseph (easy documentation-Oct. Budget) | Done | admin.Joe Nico T. Geronimo
CSR-1141-19 | CSR | Jovielet B. Caintoy | 2019-09-09 10:38:00 | 2020-01-30 19:12:00 | 2020-01-30 19:12:00 | HO | Access Request | Request Access to 10.49.1.97-Admin-Archive-Supplier | Done | admin.Reymark B. Evangelista
CSR-1170-19 | CSR | Johanna Marie C. Dandan | 2019-09-09 13:02:00 | 2019-12-09 21:00:00 | 2019-12-10 12:12:00 | HO | Hardware Purchase | Request For hardware Purchase for PRT HO (Phildata (Replacement HP prodesk 400 G4 SFF PC) IP Address = 10.49.2.194 | Done | admin.Reymark B. Evangelista
CSR-1169-19 | CSR | Johanna Marie C. Dandan | 2019-09-09 13:07:00 | 2019-12-09 21:00:00 | 2019-12-10 12:12:00 | HO | Hardware Purchase | Request For hardware Purchase for PRT HO (Phildata (Replacement HP prodesk 400 G4 SFF PC) IP Address = 10.49.1.127 | Done | admin.Reymark B. Evangelista
QA-1639-19 | QA | Joan M. Rivera | 2019-09-09 14:02:00 | 2019-09-09 14:02:00 | 2019-09-09 17:02:00 | HO |  | Gather Software Installed Data for PEZA inventory | Closed | admin.Joel Jr. M. Chavez
CSR-1155-19 | CSR | Glenn L. Fabian | 2019-09-10 15:08:00 | 2019-09-11 21:00:00 | 2019-09-30 14:05:00 | HO | Modify Software | Please connect/change the settings of the following PC to YC server to access the ANSYS-ICEPAK License for 90 Days. 10.49.3.221 10.49.3.40 - Instruction "ANSYS License Server Connection setting change procedure " on how to connect was sent by Mochizuki-san from Digital Design Technology Development Department | Closed | admin.Rommel Y. Bacus
CSR-1227-19 | CSR | Sharmaine T. Ingles | 2019-09-10 15:40:00 | 2019-10-03 09:57:00 | 2019-10-03 10:25:00 | HO | Account Request | Access Deletion of Resigned Employee pet1547 Jade Lauren C. Lopez pet1958 Emil A. Cobarrubia | Done | admin.Reymark B. Evangelista
QA-1645-19 | QA | Patrick B. Martinez | 2019-09-11 06:40:00 | 2019-09-11 06:40:00 | 2019-09-11 06:45:00 | HO |  | Activation of microsoft office. | Closed | admin.Joe Nico T. Geronimo
QA-1646-19 | QA | Edgar R. Medina | 2019-09-11 08:28:00 | 2019-09-11 08:28:00 | 2019-09-11 08:59:00 | HO |  | Outlook teach how to archived folder | Closed | admin.Reymark B. Evangelista
CSR-1178-19 | CSR | Mary Joy L. De Belen | 2019-09-11 10:01:00 | 2020-01-31 08:10:00 | 0000-00-00 00:00:00 | HO | Renewal License | CAE Oracle Solaris Premier Support for Systems (Nov) | Work in Progress | admin.Greg Daniel E. Mojica
QA-1651-19 | QA | Yolanda D. Cinco | 2019-09-11 10:19:00 | 2019-09-11 10:19:00 | 2019-09-11 10:50:00 | HO |  | Assist on archiving email | Closed | admin.Reymark B. Evangelista
CSR-1153-19 | CSR | Lorenie M. Maullon | 2019-09-11 11:05:00 | 2019-09-20 21:00:00 | 2019-09-12 08:19:00 | HO | Access Request | Account Deletion request Ms. Anna Marie O. Busmente PET ID: 2020 (IP 10.49.3.198) | Done | admin.Joe Nico T. Geronimo
DRR-0128-19 | DRR | Karen M. Mercado | 2019-09-11 13:06:00 | 2019-09-11 13:06:00 | 2019-09-30 09:37:00 | HO | Windows | GM QCC-NEW11;\\10.49.1.97\qc\QC_OFFICE\PLEASE_DO_NOT_EDIT\Quality Control Circle\2019\WHD3\GM QCC\GM QCC-NEW11;;;Corrupted Fle | Done | admin.Reymark B. Evangelista
CSR-1154-19 | CSR | Lorenie M. Maullon | 2019-09-11 17:04:00 | 2019-10-25 12:05:00 | 2019-10-10 06:48:00 | HO | Account Request | 2 Lync Account use for more effective communications and other job related matters 1. Sarah mae,Bagis (IP10.49.3.140 , PET1802) 2. Merene,Gelli (IP10.49.5.209 , PET1832) | Done | admin.Joe Nico T. Geronimo
QA-1652-19 | QA | Rens Nicko M. Santos | 2019-09-12 08:20:00 | 2019-09-12 08:20:00 | 2019-09-12 08:33:00 | HO |  | adobe acrobat license activation | Closed | admin.Reymark B. Evangelista
CSR-1162-19 | CSR | Francis Benjamin C. Cagampan | 2019-09-12 08:37:00 | 2019-10-31 16:57:00 | 2020-01-06 06:46:00 | HO | Access Request | Request for Access to 11 JBRB Members to PNAS2. please see attached data below for the Official request form for PNAS2 | Done | admin.Joe Nico T. Geronimo
CSR-1206-19 | CSR | Cris-Myla A. Orandain | 2019-09-12 09:39:00 | 2019-09-23 21:00:00 | 2019-10-08 22:29:00 | HO | PC Configuration | Share Extes App (LEXD63BB) from the user of IP address 10.49.2.30 -with approval of Ms. Michelle dela Cruz (9/6/19) | Done | admin.Christ John Dela Cruz
QA-1653-19 | QA | Vicente Z. Nieto | 2019-09-12 08:38:00 | 2019-09-12 08:38:00 | 2019-09-12 09:40:00 | HO |  | Uninstall MS office pro 64 bit & MS office visio and install 32bit version | Closed | admin.Reymark B. Evangelista
QA-1654-19 | QA | Raffy V. Dacara | 2019-09-12 10:00:00 | 2019-09-12 10:00:00 | 2019-09-12 10:26:00 | HO |  | Black screen monitor. check PC driver and hardisk check | Closed | admin.Reymark B. Evangelista
CPR-0132-19 | CPR | Ross Ma. Angelie S. Flores | 2019-09-12 10:50:00 | 2019-09-12 10:50:00 | 2019-09-23 10:11:00 | HO | Mouse | Need new mouse because of left and right click not responding. | Done | admin.Reymark B. Evangelista
QA-1655-19 | QA | Edmund C. Abadiez | 2019-09-12 12:40:00 | 2019-09-12 12:40:00 | 2019-09-12 12:54:00 | HO |  | Register regular ID 1980&1979 | Closed | admin.Reymark B. Evangelista
CSR-1179-19 | CSR | Jasper Labenia | 2019-09-12 21:14:00 | 2019-10-24 21:00:00 | 2019-09-17 21:56:00 | HO | Renewal License | (ZFS) Oracle Solaris Premier Subscription Renewal for Oct. 2019 - 2020 10.49.2.71 Mask245328 fujitsu primergy RX2520 M2 | Done | admin.Jasper Labenia
CSR-1164-19 | CSR | Jovielet B. Caintoy | 2019-09-13 08:48:00 | 2019-10-16 07:18:00 | 2019-10-15 07:19:00 | HO | Access Request | Additional access right of Norbert Bustarga in \\10.49.1.97\wh\MS_PTM\MS FOLDER 2011\KPM\MS SALESHOUR REPORT | Done | admin.Joe Nico T. Geronimo
CSR-1188-19 | CSR | Mark Erwin B. Gorospe | 2019-09-13 11:19:00 | 2019-09-16 21:00:00 | 2019-09-30 13:57:00 | HO | Install Software | please install - MTvs WS for AP checking | Done | admin.Rommel Y. Bacus
CSR-1173-19 | CSR | Rodelio Jr. A. Perin | 2019-09-13 15:03:00 | 2019-09-18 06:36:00 | 2019-09-18 06:36:00 | HO | Add Internet Connection | To have an access on the internet for benchmark research and investigation for benchmark japan CDC. Till Oct. 15, 2019. For my user number only. 1. CE19-PK-0297 (A2mac1) 2. Other connector supplier catalog. (9P 0.64mm sealed connector) | Done | admin.Joe Nico T. Geronimo
CSR-1244-19 | CSR | Ronalyn G. Imana | 2019-09-13 16:11:00 | 2019-10-18 12:44:00 | 2019-10-21 15:04:00 | HO | Access Request | 1. Request of denied access for folders in "94 Help Jobs" for all SCD Staffs (pet1531, 6052, 6074, 6162 (HO and BO) Locations \\10.49.1.97\ei \\10.49.128.7\ei_(branch) 2. Only EI members can access on these 2 folders. | Done | admin.Reymark B. Evangelista